## 01 Project
Setting | Value | Guidance
Project / scenario name | Offshore installation campaign | Descriptive name used in results and exported files.
Planning year | 2026 | Future year used for planning dates, for example 2026.
Campaign start month | 1 | Number from 1 to 12.
Campaign start day | 1 | Number from 1 to 31.
Positions per cycle | 6 | Number of Type 2 positions completed in each cycle.
Total positions | 60 | Total number of installation positions in the campaign.
Percentile 1 | 50 | Normally 50.
Percentile 2 | 75 | Normally 75.
Percentile 3 | 90 | Normally 90.
Simulation time step [h] | 1 | Use 1, 0.5, or 0.25 hours.
Detailed results basis | Percentile 1 representative hindcast year | Use P0 (no weather), Percentile 1, 2 or 3 representative hindcast year, or enter a specific historical year.
Hindcast start year |  | First historical start year to simulate. May be blank.
Hindcast end year |  | Last historical start year to simulate. May be blank.
Default safe-to-safe method | MOST_STRINGENT | MOST_STRINGENT or TIME_PHASED. Individual groups may override this on 04 Safe-to-Safe Groups.

## 02 Locations
Location ID | Location name | Type | Time zone | Weather file name | Notes
PORT | Base port | Port | UTC |  | Upload the port hindcast CSV.
TRANSIT | Transit route | Transit | UTC |  | Upload the route hindcast CSV.
OFFSHORE | Offshore site | Offshore | UTC |  | Upload the offshore hindcast CSV.
Each activity must reference a Location ID. Upload one weather CSV for every used location in the app.

## 03 Activities
Activity ID | Type | No learning curve | Position complete | Description | Work location | Duration [h] | Weather window [h] | Safe-to-safe group | Wind 10 m limit [m/s] | Wind 100 m limit [m/s] | Hs limit [m] | Tp limit [s] | Current limit [m/s] | Start time [HH:MM] | End time [HH:MM] | Hs-Tp curve | Remarks
1 | 1 | Yes | No | Ready for loadout in port | PORT | 3 | 3 |  | 18 | 100 | 100 | 100 | 100 | 00:00 | 00:00 | None
2 | 1 | No | No | Loading 6 MPs in port | PORT | 18 | 4 |  | 15 | 100 | 100 | 100 | 100 | 00:00 | 00:00 | None
3 | 1 | No | No | Loading 6 TPs in port | PORT | 18 | 4 |  | 16 | 100 | 100 | 100 | 100 | 00:00 | 00:00 | None
4 | 1 | Yes | No | Prepare to sail | PORT | 1 | 1 |  | 20 | 100 | 100 | 100 | 100 | 00:00 | 00:00 | None
5 | 1 | Yes | No | Sail out of port | PORT | 1 | 2 |  | 16 | 100 | 100 | 100 | 100 | 00:00 | 00:00 | None
6 | 1 | Yes | No | Transit to offshore site | TRANSIT | 10 | 15 |  | 16 | 100 | 2 | 10 | 100 | 00:00 | 00:00 | None
7 | 2 | Yes | No | Vessel move to location | OFFSHORE | 1 | 2 |  | 15 | 100 | 1.8 | 100 | 100 | 00:00 | 00:00 | None
8 | 2 | No | No | Preparation works for MP installation | OFFSHORE | 1 | 2 |  | 14 | 100 | 1.8 | 100 | 100 | 00:00 | 00:00 | None
9 | 2 | No | No | Lift and install MP | OFFSHORE | 6 | 8 |  | 100 | 15 | 1.8 | 10 | 100 | 00:00 | 00:00 | None
10 | 2 | No | Yes | Lift and install TP | OFFSHORE | 3 | 5 |  | 13 | 100 | 1.5 | 9 | 100 | 00:00 | 00:00 | None
11 | 2 | No | No | Final works on TP | OFFSHORE | 4 | 5 |  | 14 | 100 | 2 | 100 | 100 | 00:00 | 00:00 | None
12 | 3 | Yes | No | Transit back to port | TRANSIT | 8 | 10 |  | 16 | 100 | 2 | 100 | 100 | 00:00 | 00:00 | None
13 | 3 | Yes | No | Arrival to port | PORT | 1 | 1 |  | 16 | 100 | 100 | 100 | 100 | 00:00 | 00:00 | None

## 04 Safe-to-Safe Groups
Group ID | Description | Assessment method | Assessment location | Notes
MOST_STRINGENT applies the lowest group limits for the full continuous group duration. TIME_PHASED applies each activity's own limits during its expected part of the sequence.

## 05 HsTp Curves
Curve | Tp from [s] | Tp to [s] | Hs maximum [m]
Curve1 | 0 | 5 | 2.75
Curve1 | 5 | 6 | 2.5
Curve1 | 6 | 7 | 2.25
Curve1 | 7 | 8 | 2
Curve1 | 8 | 9 | 1.75
Curve1 | 9 | 10 | 1.5
Curve1 | 10 | 11 | 1.75
Curve1 | 11 | 12 | 2
Curve1 | 12 | 13 | 2.25
Curve1 | 13 | 14 | 2.5
Curve1 | 14 | 16 | 2.75
Curve2 | 0 | 6 | 2.5
Curve2 | 6 | 7 | 2
Curve2 | 7 | 8 | 1.75
Curve2 | 8 | 10 | 1.5
Curve2 | 10 | 11 | 1.75
Curve2 | 11 | 12 | 2
Curve2 | 12 | 15 | 2.5
Curve3 | 0 | 3 | 1.6
Curve3 | 3 | 4 | 1.5
Curve3 | 4 | 5 | 1.25
Curve3 | 5 | 6 | 1
Curve3 | 6 | 7 | 0.75
Curve3 | 7 | 8 | 0.5
Curve3 | 8 | 9 | 0.75
Curve3 | 9 | 10 | 1
Curve3 | 10 | 11 | 1.25
Curve3 | 11 | 12 | 1.5
Curve3 | 12 | 14 | 1.6
Curve4 | 0 | 5 | 3
Curve4 | 5 | 6 | 2.75
Curve4 | 6 | 7 | 2.5
Curve4 | 7 | 8 | 2.25
Curve4 | 8 | 15 | 2
Curve5 | 0 | 5 | 2
Curve5 | 5 | 6 | 2.25
Curve5 | 6 | 7 | 2.5
Curve5 | 7 | 8 | 2.75
Curve5 | 8 | 15 | 3
Curve6 | 0 | 5 | 1.5
Curve6 | 5 | 6 | 1.6
Curve6 | 6 | 7 | 1.75
Curve6 | 7 | 8 | 2
Curve6 | 8 | 9 | 2.25
Curve6 | 9 | 10 | 2.5
Curve6 | 10 | 11 | 2.25
Curve6 | 11 | 12 | 2
Curve6 | 12 | 13 | 1.75
Curve6 | 13 | 14 | 1.6
Curve6 | 14 | 16 | 1.5

## 06 Learning Curve
Cycle | Duration multiplier
1 | 1
2 | 1
3 | 1
4 | 1
5 | 1
6 | 1
7 | 1
8 | 1
9 | 1
10 | 1
11 | 1
12 | 1
13 | 1
14 | 1
15 | 1
16 | 1
17 | 1
18 | 1
19 | 1
20 | 1

## 07 Instructions
Weather Assessment — v0.10.6
Important | This workbook is an input format, not an approved installation procedure. Verify all durations and weather limits.
Item | Explanation
How to use | Complete the yellow cells, save as .xlsx, upload it on page 02, and review validation before running.
Locations | Define each work location on 02 Locations. A separate weather CSV can be uploaded for Port, Transit, Offshore or other locations.
Work location | Select the Location ID whose weather conditions control the activity.
Safe-to-safe group | Enter the same Group ID, for example G1, on consecutive activities that must have one complete forecast window before the first activity starts. Leave blank for standalone activities.
Activity Type 1 | Performed once at the start of every cycle.
Activity Type 2 | Repeated for every position in the cycle.
Activity Type 3 | Performed once at the end of every cycle.
No learning curve | Yes keeps the original duration; No applies the cycle multiplier.
Position complete | Mark Yes on exactly one Type 2 activity.
Weather window | Minimum continuous workable period required before the activity can start or continue.
Safe-to-safe methods | MOST_STRINGENT applies the group's lowest limits over the full continuous group duration. TIME_PHASED assesses each activity using its own limits at its expected execution time. Group overrides are set on 04 Safe-to-Safe Groups.
Safe-to-safe execution | Both methods pre-check the complete committed sequence before the first activity starts. Once started, no weather waiting is allowed until the group end.
Percentile direction | P90 is higher for duration/downtime, but lower for positions completed/workable hours.
Historical synchronization | A hindcast scenario uses the same historical year at every work location.
P0 and timestep | P0 uses exact learning-adjusted durations and does not change with the simulation timestep. Timestep-grid adjustment is reported separately from weather downtime.
Downtime attribution | Downtime is attributed to the exact blocking weather criterion or criterion combination. Direct exceedance and Window pre-check are mechanisms only; Hs-Tp curve use remains recorded as the assessment basis.
Data coverage | A scenario that reaches the end of the available weather data before completion is marked incomplete and excluded from percentile calculations.
Display precision | Calculated decimal values and percentages are displayed to three decimal places. Raw uploaded weather values retain their source precision.
Detailed results basis | Select P0 (no weather), Percentile 1, 2 or 3 representative hindcast year, or enter one historical hindcast year for detailed review.
Reports | Page 15 exports the detailed Excel workbook, executive PDF summary and a cycle-grouped Microsoft Project XML schedule based on the selected detailed-results basis.