## 01 Project
Setting | Value | Guidance
Project / scenario name | YHO_FEM2 (alternative 2030_42 locations)_30072026 | Descriptive name used in results and exported files.
Planning year | 2030 | Future year used for planning dates, for example 2026.
Campaign start month | 4 | Number from 1 to 12.
Campaign start day | 1 | Number from 1 to 31.
Positions per cycle | 2 | Number of Type 2 positions completed in each cycle.
Total positions | 42 | Total number of installation positions in the campaign.
Percentile 1 | 50 | Normally 50.
Percentile 2 | 75 | Normally 75.
Percentile 3 | 90 | Normally 90.
Simulation time step [h] | 0.25 | Use 1, 0.5, or 0.25 hours.
Detailed results basis | Percentile 1 representative hindcast year | Use Percentile 1, 2 or 3 representative hindcast year, or enter a specific historical year.
Hindcast start year |  | First historical start year to simulate. May be blank.
Hindcast end year |  | Last historical start year to simulate. May be blank.
Default safe-to-safe method | MOST_STRINGENT | MOST_STRINGENT or TIME_PHASED. Individual groups may override this on 04 Safe-to-Safe Groups.

## 02 Locations
Location ID | Location name | Type | Time zone | Weather file name | Notes
PORT | Installation port (project-specific) | Port | Asia/Taipei |  | Port is not named in G09B. Upload the project port hindcast CSV.
TRANSIT | Port–Fengmiao 2 transit route | Transit | Asia/Taipei |  | Ahead/astern operating limits are used as the G09B optimal-case basis.
OFFSHORE | Fengmiao 2 offshore site | Offshore | Asia/Taipei |  | WTG installation location. Upload the offshore hindcast CSV.
Each activity must reference a Location ID. Upload one weather CSV for every used location in the app.

## 03 Activities
Activity ID | Type | No learning curve | Position complete | Description | Work location | Duration [h] | Weather window [h] | Safe-to-safe group | Wind 10 m limit [m/s] | Wind 100 m limit [m/s] | Hs limit [m] | Tp limit [s] | Current limit [m/s] | Start time [HH:MM] | End time [HH:MM] | Hs-Tp curve | Remarks
1 | 1 | Yes | No | Port maneuvering | OFFSHORE | 1 | 1 |  | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
2 | 1 | Yes | No | Preload and jacking up at port | OFFSHORE | 2 | 2 |  | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
3 | 1 | Yes | No | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 |  | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
4 | 1 | No | No | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 |  | 10.2 | 14 | 20 | 20 | 100 | 00:00 | 00:00 | None
5 | 1 | No | No | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 |  | 10.2 | 14 | 20 | 20 | 100 | 00:00 | 00:00 | None
6 | 1 | No | No | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 |  | 10.2 | 14 | 20 | 20 | 100 | 00:00 | 00:00 | None
7 | 1 | No | No | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 |  | 8.2 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
8 | 1 | No | No | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 |  | 8.2 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
9 | 1 | No | No | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 |  | 8.2 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
10 | 1 | No | No | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 |  | 10.2 | 14 | 20 | 20 | 100 | 00:00 | 00:00 | None
11 | 1 | No | No | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 |  | 10.2 | 14 | 20 | 20 | 100 | 00:00 | 00:00 | None
12 | 1 | No | No | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 |  | 10.2 | 14 | 20 | 20 | 100 | 00:00 | 00:00 | None
13 | 1 | No | No | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 |  | 8.2 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
14 | 1 | No | No | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 |  | 8.2 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
15 | 1 | No | No | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 |  | 8.2 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
16 | 1 | Yes | No | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 |  | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
17 | 1 | Yes | No | Jacking down at port | OFFSHORE | 2 | 3 |  | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
18 | 1 | Yes | No | Port maneuvering | OFFSHORE | 1 | 1.5 |  | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
19 | 1 | Yes | No | Transit from port to site | OFFSHORE | 4.3 | 6.45 |  | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None
20 | 1 | Yes | No | DP field check | OFFSHORE | 0.5 | 0.75 |  | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None
21 | 2 | Yes | No | Transit to next foundation | OFFSHORE | 1 | 6.45 |  | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None
22 | 2 | Yes | No | Positioning at WTG location | OFFSHORE | 1 | 1.5 |  | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None
23 | 2 | Yes | No | Preload and jacking up at site | OFFSHORE | 4 | 6 |  | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None
24 | 2 | Yes | No | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 |  | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
25 | 2 | No | No | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 |  | 8.8 | 12 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
26 | 2 | No | No | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 |  | 11.7 | 16 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
27 | 2 | No | No | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | G1 | 11.7 | 16 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
28 | 2 | No | No | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | G1 | 10.2 | 14 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
29 | 2 | No | No | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | G1 | 10.2 | 14 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
30 | 2 | No | No | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | G2 | 11.7 | 16 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
31 | 2 | No | No | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | G2 | 10.2 | 14 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
32 | 2 | No | No | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | G2 | 11.7 | 16 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
33 | 2 | No | No | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | G3 | 10.2 | 14 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
34 | 2 | No | No | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | G3 | 8.8 | 12 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
35 | 2 | No | No | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | G3 | 8.8 | 12 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
36 | 2 | No | No | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | G4 | 8.8 | 12 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
37 | 2 | No | No | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | G4 | 8.8 | 12 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
38 | 2 | No | No | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | G5 | 8.8 | 12 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
39 | 2 | No | No | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | G5 | 8.8 | 12 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
40 | 2 | No | No | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 |  | 10.2 | 14 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
41 | 2 | No | No | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 |  | 10.2 | 14 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
42 | 2 | No | No | Turbine general completion works | OFFSHORE | 3 | 3 |  | 13.1 | 18 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
43 | 2 | Yes | No | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 |  | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
44 | 2 | Yes | Yes | Jacking down at site | OFFSHORE | 2 | 2 |  | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None
45 | 3 | Yes | No | Transit from site to port | OFFSHORE | 4.3 | 4.3 |  | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None

## 04 Safe-to-Safe Groups
Group ID | Description | Assessment method | Assessment location | Notes
G1 | Tower installation safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Tower preparation through tower derigging.
G2 | Nacelle installation safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Nacelle preparation through nacelle derigging.
G3 | Blade 1 safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Blade 1 preparation through blade derigging.
G4 | Blade 2 safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Blade 2 preparation through blade derigging.
G5 | Blade 3 safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Blade 3 preparation through blade derigging.
MOST_STRINGENT applies the lowest group limits for the full continuous group duration. TIME_PHASED applies each activity's own limits during its expected part of the sequence.

## 05 HsTp Curves
Curve | Tp from [s] | Tp to [s] | Hs maximum [m]

## 06 Learning Curve
Cycle | Duration multiplier
1 | 1.5
2 | 1.5
3 | 1.5
4 | 1.5
5 | 1
6 | 1
7 | 1
8 | 1
9 | 1
10 | 1
11 | 1
12 | 1
13 | 1
14 | 1
15 | 1
16 | 1
17 | 1
18 | 1
19 | 1
20 | 1
21 | 1

## 07 Instructions
Weather Assessment — v0.10.4
Important | This workbook is an input format, not an approved installation procedure. Verify all durations and weather limits.
Item | Explanation
How to use | Complete the yellow cells, save as .xlsx, upload it on page 02, and review validation before running.
Locations | Define each work location on 02 Locations. A separate weather CSV can be uploaded for Port, Transit, Offshore or other locations.
Work location | Select the Location ID whose weather conditions control the activity.
Safe-to-safe group | Enter the same Group ID, for example G1, on consecutive activities that must have one complete forecast window before the first activity starts. Leave blank for standalone activities.
Activity Type 1 | Performed once at the start of every cycle.
Activity Type 2 | Repeated for every position in the cycle.
Activity Type 3 | Performed once at the end of every cycle.
No learning curve | Yes keeps the original duration; No applies the cycle multiplier.
Position complete | Mark Yes on exactly one Type 2 activity.
Weather window | Minimum continuous workable period required before the activity can start or continue.
Safe-to-safe methods | MOST_STRINGENT applies the group's lowest limits over the full continuous group duration. TIME_PHASED assesses each activity using its own limits at its expected execution time. Group overrides are set on 04 Safe-to-Safe Groups.
Safe-to-safe execution | Both methods pre-check the complete committed sequence before the first activity starts. Once started, no weather waiting is allowed until the group end.
Percentile direction | P90 is higher for duration/downtime, but lower for positions completed/workable hours.
Historical synchronization | A hindcast scenario uses the same historical year at every work location.
P0 and timestep | P0 uses exact learning-adjusted durations and does not change with the simulation timestep. Timestep-grid adjustment is reported separately from weather downtime.
Downtime attribution | Insufficient weather-window downtime is attributed to the first future blocking factor. Hs-Tp curve failures are reported under Hs, Tp or Multiple criteria, while the curve remains the assessment basis.
Data coverage | A scenario that reaches the end of the available weather data before completion is marked incomplete and excluded from percentile calculations.
Display precision | Calculated decimal values and percentages are displayed to three decimal places. Raw uploaded weather values retain their source precision.
Detailed results basis | Select Percentile 1, 2 or 3 representative hindcast year, or enter one historical hindcast year for detailed review.
Reports | Page 15 exports the detailed Excel workbook, executive PDF summary and a P50 cycle-grouped Microsoft Project XML schedule.