## Assessment metadata
Assessment metadata
Project, weather-data and assessment basis used for this results workbook.
Field | Value
Application | Weather Assessment
Version | 0.10.6
Project / scenario | YHO_FEM2 (base 2030_42 locations)_Rev.2K_3
Generated | 2026-09-16 15:29
Planning start | 2030-04-01
Positions / positions per cycle | 42 / 2
Simulation timestep [h] | 0.25
Detailed results basis | P0 (no weather)
P0 duration [days] | 114.4958
P0 weather downtime [h] | 0
P0 timestep adjustment [h] | 0
Successful simulations | 44
Total simulations | 45
Weather files | OFFSHORE: FM2_WF_weathe_reconciled_Rev.0.csv; PORT: FM2_WF_weathe_reconciled_Rev.0.csv; TRANSIT: FM2_WF_weathe_reconciled_Rev.0.csv
Exact P0 [h] | 2747.9
Microsoft Project output | Selected-basis cycle-grouped XML (P0) available on page 15

## IN_general
IN_general
Campaign settings and activity definitions. Boolean values are shown as TRUE/FALSE.
Campaign settings
Setting |  | Value
project_name |  | YHO_FEM2 (base 2030_42 locations)_Rev.2K_3
planning_year |  | 2030
campaign_start_month |  | 4
campaign_start_day |  | 1
positions_per_cycle |  | 2
total_positions |  | 42
percentiles |  | P50, P75, P90
simulation_timestep_hours |  | 0.25
detailed_results_basis |  | P0 (no weather)
hindcast_start_year |  | 1979
hindcast_end_year |  | 2023
default_safe_to_safe_method |  | MOST_STRINGENT
Activity definitions
activity_id | activity_type | no_learning_curve | milestone | description | location_id | duration_hours | weather_window_hours | safe_to_safe_group | wind10_limit | wind100_limit | hs_limit | tp_limit | current_limit | time_start | time_end | hstp_curve | remarks
1 | 1 | TRUE | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 |  | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
2 | 1 | TRUE | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 |  | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
3 | 1 | TRUE | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 |  | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
4 | 1 | FALSE | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 |  | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
5 | 1 | FALSE | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 |  | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
6 | 1 | FALSE | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 |  | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
7 | 1 | FALSE | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 |  | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
8 | 1 | FALSE | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 |  | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
9 | 1 | FALSE | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 |  | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
10 | 1 | FALSE | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 |  | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
11 | 1 | FALSE | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 |  | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
12 | 1 | FALSE | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 |  | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
13 | 1 | FALSE | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 |  | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
14 | 1 | FALSE | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 |  | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
15 | 1 | FALSE | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 |  | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
16 | 1 | TRUE | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 |  | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None
17 | 1 | TRUE | FALSE | Jacking down at port | OFFSHORE | 2 | 3 |  | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None
18 | 1 | TRUE | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 |  | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None
19 | 1 | TRUE | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 |  | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None
20 | 1 | TRUE | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 |  | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None
21 | 2 | TRUE | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 |  | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None
22 | 2 | TRUE | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 |  | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None
23 | 2 | TRUE | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 |  | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None
24 | 2 | TRUE | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 |  | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
25 | 2 | FALSE | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 |  | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
26 | 2 | FALSE | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 |  | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
27 | 2 | FALSE | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | G1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
28 | 2 | FALSE | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | G1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
29 | 2 | FALSE | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | G1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
30 | 2 | FALSE | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | G2 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
31 | 2 | FALSE | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | G2 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
32 | 2 | FALSE | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | G2 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
33 | 2 | FALSE | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | G3 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
34 | 2 | FALSE | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | G3 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
35 | 2 | FALSE | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | G3 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
36 | 2 | FALSE | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | G4 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
37 | 2 | FALSE | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | G4 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
38 | 2 | FALSE | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | G5 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
39 | 2 | FALSE | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | G5 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
40 | 2 | FALSE | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 |  | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
41 | 2 | FALSE | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 |  | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
42 | 2 | FALSE | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 |  | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
43 | 2 | TRUE | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 |  | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None
44 | 2 | TRUE | TRUE | Jacking down at site | OFFSHORE | 2 | 3 |  | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None
45 | 3 | TRUE | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 |  | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None

## IN_locations
IN_locations
Work locations and weather-file mapping.
location_id | name | location_type | timezone | weather_filename | notes
PORT | Installation port (project-specific) | Port | Asia/Taipei |  | Port is not named in G09B. Upload the project port hindcast CSV.
TRANSIT | Port–Fengmiao 2 transit route | Transit | Asia/Taipei |  | Ahead/astern operating limits are used as the G09B optimal-case basis.
OFFSHORE | Fengmiao 2 offshore site | Offshore | Asia/Taipei |  | WTG installation location. Upload the offshore hindcast CSV.

## IN_safe to safe
IN_safe to safe
Safe-to-safe group definitions, assessment methods, assessment location and notes.
group_id | description | assessment_method | assessment_location | notes
G1 | Tower installation safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Tower preparation through tower derigging.
G2 | Nacelle installation safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Nacelle preparation through nacelle derigging.
G3 | Blade 1 safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Blade 1 preparation through blade derigging.
G4 | Blade 2 safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Blade 2 preparation through blade derigging.
G5 | Blade 3 safe-to-safe sequence | MOST_STRINGENT | OFFSHORE | Blade 3 preparation through blade derigging.

## IN_HsTp curve
IN_HsTp curve
Hs-Tp curve bins used by activity criteria.

## IN_learning curve
IN_learning curve
Cycle duration multipliers applied to learning-enabled activities.
cycle | multiplier
1 | 1.5
2 | 1.5
3 | 1.5
4 | 1.5
5 | 1
6 | 1
7 | 1
8 | 1
9 | 1
10 | 1
11 | 1
12 | 1
13 | 1
14 | 1
15 | 1
16 | 1
17 | 1
18 | 1
19 | 1
20 | 1
21 | 1

## IN_sequence
IN_sequence
Generated campaign sequence with learning multipliers, safe-to-safe group definitions and activity criteria.
sequence_no | cycle | position | activity_id | activity_type | learning_multiplier | milestone | description | location_id | duration_hours | weather_window_hours | wind10_limit | wind100_limit | hs_limit | tp_limit | current_limit | time_start | time_end | hstp_curve | remarks | safe_to_safe_group | group_role | group_method | group_assessment_location
1 | 1 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
2 | 1 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
3 | 1 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
4 | 1 |  | 4 | 1 | 1.5 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1.5 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
5 | 1 |  | 5 | 1 | 1.5 | FALSE | Loadout Nacelle #1 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
6 | 1 |  | 6 | 1 | 1.5 | FALSE | Loadout Tower #1 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
7 | 1 |  | 7 | 1 | 1.5 | FALSE | Loadout Blade 1 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
8 | 1 |  | 8 | 1 | 1.5 | FALSE | Loadout Blade 2 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
9 | 1 |  | 9 | 1 | 1.5 | FALSE | Loadout Blade 3 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
10 | 1 |  | 10 | 1 | 1.5 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
11 | 1 |  | 11 | 1 | 1.5 | FALSE | Loadout Nacelle #2 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
12 | 1 |  | 12 | 1 | 1.5 | FALSE | Loadout Tower #2 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
13 | 1 |  | 13 | 1 | 1.5 | FALSE | Loadout Blade 1 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
14 | 1 |  | 14 | 1 | 1.5 | FALSE | Loadout Blade 2 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
15 | 1 |  | 15 | 1 | 1.5 | FALSE | Loadout Blade 3 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
16 | 1 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
17 | 1 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
18 | 1 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
19 | 1 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
20 | 1 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
21 | 1 | 1 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
22 | 1 | 1 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
23 | 1 | 1 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
24 | 1 | 1 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
25 | 1 | 1 | 25 | 2 | 1.5 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1.5 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
26 | 1 | 1 | 26 | 2 | 1.5 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 3 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
27 | 1 | 1 | 27 | 2 | 1.5 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1.5 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
28 | 1 | 1 | 28 | 2 | 1.5 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 5.25 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
29 | 1 | 1 | 29 | 2 | 1.5 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
30 | 1 | 1 | 30 | 2 | 1.5 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
31 | 1 | 1 | 31 | 2 | 1.5 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
32 | 1 | 1 | 32 | 2 | 1.5 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
33 | 1 | 1 | 33 | 2 | 1.5 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.75 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
34 | 1 | 1 | 34 | 2 | 1.5 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
35 | 1 | 1 | 35 | 2 | 1.5 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
36 | 1 | 1 | 36 | 2 | 1.5 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
37 | 1 | 1 | 37 | 2 | 1.5 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
38 | 1 | 1 | 38 | 2 | 1.5 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
39 | 1 | 1 | 39 | 2 | 1.5 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
40 | 1 | 1 | 40 | 2 | 1.5 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
41 | 1 | 1 | 41 | 2 | 1.5 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
42 | 1 | 1 | 42 | 2 | 1.5 | FALSE | Turbine general completion works | OFFSHORE | 4.5 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
43 | 1 | 1 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
44 | 1 | 1 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
45 | 1 | 2 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
46 | 1 | 2 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
47 | 1 | 2 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
48 | 1 | 2 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
49 | 1 | 2 | 25 | 2 | 1.5 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1.5 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
50 | 1 | 2 | 26 | 2 | 1.5 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 3 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
51 | 1 | 2 | 27 | 2 | 1.5 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1.5 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
52 | 1 | 2 | 28 | 2 | 1.5 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 5.25 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
53 | 1 | 2 | 29 | 2 | 1.5 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
54 | 1 | 2 | 30 | 2 | 1.5 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
55 | 1 | 2 | 31 | 2 | 1.5 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
56 | 1 | 2 | 32 | 2 | 1.5 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
57 | 1 | 2 | 33 | 2 | 1.5 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.75 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
58 | 1 | 2 | 34 | 2 | 1.5 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
59 | 1 | 2 | 35 | 2 | 1.5 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
60 | 1 | 2 | 36 | 2 | 1.5 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
61 | 1 | 2 | 37 | 2 | 1.5 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
62 | 1 | 2 | 38 | 2 | 1.5 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
63 | 1 | 2 | 39 | 2 | 1.5 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
64 | 1 | 2 | 40 | 2 | 1.5 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
65 | 1 | 2 | 41 | 2 | 1.5 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
66 | 1 | 2 | 42 | 2 | 1.5 | FALSE | Turbine general completion works | OFFSHORE | 4.5 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
67 | 1 | 2 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
68 | 1 | 2 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
69 | 1 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
70 | 2 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
71 | 2 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
72 | 2 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
73 | 2 |  | 4 | 1 | 1.5 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1.5 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
74 | 2 |  | 5 | 1 | 1.5 | FALSE | Loadout Nacelle #1 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
75 | 2 |  | 6 | 1 | 1.5 | FALSE | Loadout Tower #1 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
76 | 2 |  | 7 | 1 | 1.5 | FALSE | Loadout Blade 1 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
77 | 2 |  | 8 | 1 | 1.5 | FALSE | Loadout Blade 2 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
78 | 2 |  | 9 | 1 | 1.5 | FALSE | Loadout Blade 3 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
79 | 2 |  | 10 | 1 | 1.5 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
80 | 2 |  | 11 | 1 | 1.5 | FALSE | Loadout Nacelle #2 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
81 | 2 |  | 12 | 1 | 1.5 | FALSE | Loadout Tower #2 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
82 | 2 |  | 13 | 1 | 1.5 | FALSE | Loadout Blade 1 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
83 | 2 |  | 14 | 1 | 1.5 | FALSE | Loadout Blade 2 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
84 | 2 |  | 15 | 1 | 1.5 | FALSE | Loadout Blade 3 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
85 | 2 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
86 | 2 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
87 | 2 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
88 | 2 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
89 | 2 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
90 | 2 | 3 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
91 | 2 | 3 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
92 | 2 | 3 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
93 | 2 | 3 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
94 | 2 | 3 | 25 | 2 | 1.5 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1.5 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
95 | 2 | 3 | 26 | 2 | 1.5 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 3 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
96 | 2 | 3 | 27 | 2 | 1.5 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1.5 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
97 | 2 | 3 | 28 | 2 | 1.5 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 5.25 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
98 | 2 | 3 | 29 | 2 | 1.5 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
99 | 2 | 3 | 30 | 2 | 1.5 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
100 | 2 | 3 | 31 | 2 | 1.5 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
101 | 2 | 3 | 32 | 2 | 1.5 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
102 | 2 | 3 | 33 | 2 | 1.5 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.75 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
103 | 2 | 3 | 34 | 2 | 1.5 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
104 | 2 | 3 | 35 | 2 | 1.5 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
105 | 2 | 3 | 36 | 2 | 1.5 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
106 | 2 | 3 | 37 | 2 | 1.5 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
107 | 2 | 3 | 38 | 2 | 1.5 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
108 | 2 | 3 | 39 | 2 | 1.5 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
109 | 2 | 3 | 40 | 2 | 1.5 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
110 | 2 | 3 | 41 | 2 | 1.5 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
111 | 2 | 3 | 42 | 2 | 1.5 | FALSE | Turbine general completion works | OFFSHORE | 4.5 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
112 | 2 | 3 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
113 | 2 | 3 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
114 | 2 | 4 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
115 | 2 | 4 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
116 | 2 | 4 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
117 | 2 | 4 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
118 | 2 | 4 | 25 | 2 | 1.5 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1.5 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
119 | 2 | 4 | 26 | 2 | 1.5 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 3 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
120 | 2 | 4 | 27 | 2 | 1.5 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1.5 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
121 | 2 | 4 | 28 | 2 | 1.5 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 5.25 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
122 | 2 | 4 | 29 | 2 | 1.5 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
123 | 2 | 4 | 30 | 2 | 1.5 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
124 | 2 | 4 | 31 | 2 | 1.5 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
125 | 2 | 4 | 32 | 2 | 1.5 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
126 | 2 | 4 | 33 | 2 | 1.5 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.75 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
127 | 2 | 4 | 34 | 2 | 1.5 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
128 | 2 | 4 | 35 | 2 | 1.5 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
129 | 2 | 4 | 36 | 2 | 1.5 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
130 | 2 | 4 | 37 | 2 | 1.5 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
131 | 2 | 4 | 38 | 2 | 1.5 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
132 | 2 | 4 | 39 | 2 | 1.5 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
133 | 2 | 4 | 40 | 2 | 1.5 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
134 | 2 | 4 | 41 | 2 | 1.5 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
135 | 2 | 4 | 42 | 2 | 1.5 | FALSE | Turbine general completion works | OFFSHORE | 4.5 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
136 | 2 | 4 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
137 | 2 | 4 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
138 | 2 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
139 | 3 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
140 | 3 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
141 | 3 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
142 | 3 |  | 4 | 1 | 1.5 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1.5 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
143 | 3 |  | 5 | 1 | 1.5 | FALSE | Loadout Nacelle #1 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
144 | 3 |  | 6 | 1 | 1.5 | FALSE | Loadout Tower #1 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
145 | 3 |  | 7 | 1 | 1.5 | FALSE | Loadout Blade 1 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
146 | 3 |  | 8 | 1 | 1.5 | FALSE | Loadout Blade 2 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
147 | 3 |  | 9 | 1 | 1.5 | FALSE | Loadout Blade 3 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
148 | 3 |  | 10 | 1 | 1.5 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
149 | 3 |  | 11 | 1 | 1.5 | FALSE | Loadout Nacelle #2 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
150 | 3 |  | 12 | 1 | 1.5 | FALSE | Loadout Tower #2 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
151 | 3 |  | 13 | 1 | 1.5 | FALSE | Loadout Blade 1 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
152 | 3 |  | 14 | 1 | 1.5 | FALSE | Loadout Blade 2 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
153 | 3 |  | 15 | 1 | 1.5 | FALSE | Loadout Blade 3 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
154 | 3 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
155 | 3 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
156 | 3 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
157 | 3 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
158 | 3 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
159 | 3 | 5 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
160 | 3 | 5 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
161 | 3 | 5 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
162 | 3 | 5 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
163 | 3 | 5 | 25 | 2 | 1.5 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1.5 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
164 | 3 | 5 | 26 | 2 | 1.5 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 3 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
165 | 3 | 5 | 27 | 2 | 1.5 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1.5 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
166 | 3 | 5 | 28 | 2 | 1.5 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 5.25 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
167 | 3 | 5 | 29 | 2 | 1.5 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
168 | 3 | 5 | 30 | 2 | 1.5 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
169 | 3 | 5 | 31 | 2 | 1.5 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
170 | 3 | 5 | 32 | 2 | 1.5 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
171 | 3 | 5 | 33 | 2 | 1.5 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.75 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
172 | 3 | 5 | 34 | 2 | 1.5 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
173 | 3 | 5 | 35 | 2 | 1.5 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
174 | 3 | 5 | 36 | 2 | 1.5 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
175 | 3 | 5 | 37 | 2 | 1.5 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
176 | 3 | 5 | 38 | 2 | 1.5 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
177 | 3 | 5 | 39 | 2 | 1.5 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
178 | 3 | 5 | 40 | 2 | 1.5 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
179 | 3 | 5 | 41 | 2 | 1.5 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
180 | 3 | 5 | 42 | 2 | 1.5 | FALSE | Turbine general completion works | OFFSHORE | 4.5 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
181 | 3 | 5 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
182 | 3 | 5 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
183 | 3 | 6 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
184 | 3 | 6 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
185 | 3 | 6 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
186 | 3 | 6 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
187 | 3 | 6 | 25 | 2 | 1.5 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1.5 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
188 | 3 | 6 | 26 | 2 | 1.5 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 3 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
189 | 3 | 6 | 27 | 2 | 1.5 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1.5 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
190 | 3 | 6 | 28 | 2 | 1.5 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 5.25 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
191 | 3 | 6 | 29 | 2 | 1.5 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
192 | 3 | 6 | 30 | 2 | 1.5 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
193 | 3 | 6 | 31 | 2 | 1.5 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
194 | 3 | 6 | 32 | 2 | 1.5 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
195 | 3 | 6 | 33 | 2 | 1.5 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.75 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
196 | 3 | 6 | 34 | 2 | 1.5 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
197 | 3 | 6 | 35 | 2 | 1.5 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
198 | 3 | 6 | 36 | 2 | 1.5 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
199 | 3 | 6 | 37 | 2 | 1.5 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
200 | 3 | 6 | 38 | 2 | 1.5 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
201 | 3 | 6 | 39 | 2 | 1.5 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
202 | 3 | 6 | 40 | 2 | 1.5 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
203 | 3 | 6 | 41 | 2 | 1.5 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
204 | 3 | 6 | 42 | 2 | 1.5 | FALSE | Turbine general completion works | OFFSHORE | 4.5 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
205 | 3 | 6 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
206 | 3 | 6 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
207 | 3 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
208 | 4 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
209 | 4 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
210 | 4 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
211 | 4 |  | 4 | 1 | 1.5 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1.5 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
212 | 4 |  | 5 | 1 | 1.5 | FALSE | Loadout Nacelle #1 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
213 | 4 |  | 6 | 1 | 1.5 | FALSE | Loadout Tower #1 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
214 | 4 |  | 7 | 1 | 1.5 | FALSE | Loadout Blade 1 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
215 | 4 |  | 8 | 1 | 1.5 | FALSE | Loadout Blade 2 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
216 | 4 |  | 9 | 1 | 1.5 | FALSE | Loadout Blade 3 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
217 | 4 |  | 10 | 1 | 1.5 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
218 | 4 |  | 11 | 1 | 1.5 | FALSE | Loadout Nacelle #2 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
219 | 4 |  | 12 | 1 | 1.5 | FALSE | Loadout Tower #2 | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
220 | 4 |  | 13 | 1 | 1.5 | FALSE | Loadout Blade 1 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
221 | 4 |  | 14 | 1 | 1.5 | FALSE | Loadout Blade 2 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
222 | 4 |  | 15 | 1 | 1.5 | FALSE | Loadout Blade 3 | OFFSHORE | 2.25 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
223 | 4 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
224 | 4 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
225 | 4 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
226 | 4 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
227 | 4 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
228 | 4 | 7 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
229 | 4 | 7 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
230 | 4 | 7 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
231 | 4 | 7 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
232 | 4 | 7 | 25 | 2 | 1.5 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1.5 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
233 | 4 | 7 | 26 | 2 | 1.5 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 3 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
234 | 4 | 7 | 27 | 2 | 1.5 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1.5 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
235 | 4 | 7 | 28 | 2 | 1.5 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 5.25 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
236 | 4 | 7 | 29 | 2 | 1.5 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
237 | 4 | 7 | 30 | 2 | 1.5 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
238 | 4 | 7 | 31 | 2 | 1.5 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
239 | 4 | 7 | 32 | 2 | 1.5 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
240 | 4 | 7 | 33 | 2 | 1.5 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.75 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
241 | 4 | 7 | 34 | 2 | 1.5 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
242 | 4 | 7 | 35 | 2 | 1.5 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
243 | 4 | 7 | 36 | 2 | 1.5 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
244 | 4 | 7 | 37 | 2 | 1.5 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
245 | 4 | 7 | 38 | 2 | 1.5 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
246 | 4 | 7 | 39 | 2 | 1.5 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
247 | 4 | 7 | 40 | 2 | 1.5 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
248 | 4 | 7 | 41 | 2 | 1.5 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
249 | 4 | 7 | 42 | 2 | 1.5 | FALSE | Turbine general completion works | OFFSHORE | 4.5 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
250 | 4 | 7 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
251 | 4 | 7 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
252 | 4 | 8 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
253 | 4 | 8 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
254 | 4 | 8 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
255 | 4 | 8 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
256 | 4 | 8 | 25 | 2 | 1.5 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1.5 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
257 | 4 | 8 | 26 | 2 | 1.5 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 3 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
258 | 4 | 8 | 27 | 2 | 1.5 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1.5 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
259 | 4 | 8 | 28 | 2 | 1.5 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 5.25 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
260 | 4 | 8 | 29 | 2 | 1.5 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
261 | 4 | 8 | 30 | 2 | 1.5 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
262 | 4 | 8 | 31 | 2 | 1.5 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 3.375 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
263 | 4 | 8 | 32 | 2 | 1.5 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.75 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
264 | 4 | 8 | 33 | 2 | 1.5 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.75 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
265 | 4 | 8 | 34 | 2 | 1.5 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
266 | 4 | 8 | 35 | 2 | 1.5 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
267 | 4 | 8 | 36 | 2 | 1.5 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
268 | 4 | 8 | 37 | 2 | 1.5 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
269 | 4 | 8 | 38 | 2 | 1.5 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 2.625 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
270 | 4 | 8 | 39 | 2 | 1.5 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 2.25 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
271 | 4 | 8 | 40 | 2 | 1.5 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
272 | 4 | 8 | 41 | 2 | 1.5 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1.5 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
273 | 4 | 8 | 42 | 2 | 1.5 | FALSE | Turbine general completion works | OFFSHORE | 4.5 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
274 | 4 | 8 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
275 | 4 | 8 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
276 | 4 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
277 | 5 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
278 | 5 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
279 | 5 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
280 | 5 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
281 | 5 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
282 | 5 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
283 | 5 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
284 | 5 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
285 | 5 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
286 | 5 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
287 | 5 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
288 | 5 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
289 | 5 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
290 | 5 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
291 | 5 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
292 | 5 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
293 | 5 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
294 | 5 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
295 | 5 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
296 | 5 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
297 | 5 | 9 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
298 | 5 | 9 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
299 | 5 | 9 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
300 | 5 | 9 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
301 | 5 | 9 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
302 | 5 | 9 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
303 | 5 | 9 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
304 | 5 | 9 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
305 | 5 | 9 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
306 | 5 | 9 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
307 | 5 | 9 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
308 | 5 | 9 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
309 | 5 | 9 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
310 | 5 | 9 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
311 | 5 | 9 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
312 | 5 | 9 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
313 | 5 | 9 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
314 | 5 | 9 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
315 | 5 | 9 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
316 | 5 | 9 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
317 | 5 | 9 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
318 | 5 | 9 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
319 | 5 | 9 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
320 | 5 | 9 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
321 | 5 | 10 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
322 | 5 | 10 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
323 | 5 | 10 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
324 | 5 | 10 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
325 | 5 | 10 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
326 | 5 | 10 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
327 | 5 | 10 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
328 | 5 | 10 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
329 | 5 | 10 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
330 | 5 | 10 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
331 | 5 | 10 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
332 | 5 | 10 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
333 | 5 | 10 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
334 | 5 | 10 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
335 | 5 | 10 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
336 | 5 | 10 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
337 | 5 | 10 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
338 | 5 | 10 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
339 | 5 | 10 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
340 | 5 | 10 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
341 | 5 | 10 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
342 | 5 | 10 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
343 | 5 | 10 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
344 | 5 | 10 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
345 | 5 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
346 | 6 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
347 | 6 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
348 | 6 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
349 | 6 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
350 | 6 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
351 | 6 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
352 | 6 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
353 | 6 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
354 | 6 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
355 | 6 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
356 | 6 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
357 | 6 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
358 | 6 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
359 | 6 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
360 | 6 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
361 | 6 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
362 | 6 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
363 | 6 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
364 | 6 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
365 | 6 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
366 | 6 | 11 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
367 | 6 | 11 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
368 | 6 | 11 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
369 | 6 | 11 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
370 | 6 | 11 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
371 | 6 | 11 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
372 | 6 | 11 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
373 | 6 | 11 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
374 | 6 | 11 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
375 | 6 | 11 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
376 | 6 | 11 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
377 | 6 | 11 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
378 | 6 | 11 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
379 | 6 | 11 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
380 | 6 | 11 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
381 | 6 | 11 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
382 | 6 | 11 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
383 | 6 | 11 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
384 | 6 | 11 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
385 | 6 | 11 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
386 | 6 | 11 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
387 | 6 | 11 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
388 | 6 | 11 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
389 | 6 | 11 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
390 | 6 | 12 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
391 | 6 | 12 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
392 | 6 | 12 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
393 | 6 | 12 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
394 | 6 | 12 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
395 | 6 | 12 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
396 | 6 | 12 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
397 | 6 | 12 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
398 | 6 | 12 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
399 | 6 | 12 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
400 | 6 | 12 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
401 | 6 | 12 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
402 | 6 | 12 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
403 | 6 | 12 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
404 | 6 | 12 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
405 | 6 | 12 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
406 | 6 | 12 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
407 | 6 | 12 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
408 | 6 | 12 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
409 | 6 | 12 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
410 | 6 | 12 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
411 | 6 | 12 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
412 | 6 | 12 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
413 | 6 | 12 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
414 | 6 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
415 | 7 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
416 | 7 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
417 | 7 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
418 | 7 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
419 | 7 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
420 | 7 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
421 | 7 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
422 | 7 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
423 | 7 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
424 | 7 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
425 | 7 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
426 | 7 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
427 | 7 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
428 | 7 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
429 | 7 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
430 | 7 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
431 | 7 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
432 | 7 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
433 | 7 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
434 | 7 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
435 | 7 | 13 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
436 | 7 | 13 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
437 | 7 | 13 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
438 | 7 | 13 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
439 | 7 | 13 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
440 | 7 | 13 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
441 | 7 | 13 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
442 | 7 | 13 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
443 | 7 | 13 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
444 | 7 | 13 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
445 | 7 | 13 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
446 | 7 | 13 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
447 | 7 | 13 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
448 | 7 | 13 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
449 | 7 | 13 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
450 | 7 | 13 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
451 | 7 | 13 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
452 | 7 | 13 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
453 | 7 | 13 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
454 | 7 | 13 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
455 | 7 | 13 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
456 | 7 | 13 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
457 | 7 | 13 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
458 | 7 | 13 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
459 | 7 | 14 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
460 | 7 | 14 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
461 | 7 | 14 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
462 | 7 | 14 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
463 | 7 | 14 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
464 | 7 | 14 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
465 | 7 | 14 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
466 | 7 | 14 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
467 | 7 | 14 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
468 | 7 | 14 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
469 | 7 | 14 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
470 | 7 | 14 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
471 | 7 | 14 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
472 | 7 | 14 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
473 | 7 | 14 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
474 | 7 | 14 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
475 | 7 | 14 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
476 | 7 | 14 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
477 | 7 | 14 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
478 | 7 | 14 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
479 | 7 | 14 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
480 | 7 | 14 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
481 | 7 | 14 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
482 | 7 | 14 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
483 | 7 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
484 | 8 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
485 | 8 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
486 | 8 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
487 | 8 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
488 | 8 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
489 | 8 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
490 | 8 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
491 | 8 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
492 | 8 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
493 | 8 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
494 | 8 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
495 | 8 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
496 | 8 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
497 | 8 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
498 | 8 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
499 | 8 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
500 | 8 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
501 | 8 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
502 | 8 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
503 | 8 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
504 | 8 | 15 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
505 | 8 | 15 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
506 | 8 | 15 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
507 | 8 | 15 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
508 | 8 | 15 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
509 | 8 | 15 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
510 | 8 | 15 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
511 | 8 | 15 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
512 | 8 | 15 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
513 | 8 | 15 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
514 | 8 | 15 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
515 | 8 | 15 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
516 | 8 | 15 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
517 | 8 | 15 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
518 | 8 | 15 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
519 | 8 | 15 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
520 | 8 | 15 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
521 | 8 | 15 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
522 | 8 | 15 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
523 | 8 | 15 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
524 | 8 | 15 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
525 | 8 | 15 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
526 | 8 | 15 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
527 | 8 | 15 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
528 | 8 | 16 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
529 | 8 | 16 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
530 | 8 | 16 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
531 | 8 | 16 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
532 | 8 | 16 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
533 | 8 | 16 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
534 | 8 | 16 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
535 | 8 | 16 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
536 | 8 | 16 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
537 | 8 | 16 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
538 | 8 | 16 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
539 | 8 | 16 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
540 | 8 | 16 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
541 | 8 | 16 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
542 | 8 | 16 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
543 | 8 | 16 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
544 | 8 | 16 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
545 | 8 | 16 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
546 | 8 | 16 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
547 | 8 | 16 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
548 | 8 | 16 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
549 | 8 | 16 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
550 | 8 | 16 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
551 | 8 | 16 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
552 | 8 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
553 | 9 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
554 | 9 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
555 | 9 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
556 | 9 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
557 | 9 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
558 | 9 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
559 | 9 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
560 | 9 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
561 | 9 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
562 | 9 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
563 | 9 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
564 | 9 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
565 | 9 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
566 | 9 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
567 | 9 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
568 | 9 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
569 | 9 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
570 | 9 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
571 | 9 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
572 | 9 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
573 | 9 | 17 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
574 | 9 | 17 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
575 | 9 | 17 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
576 | 9 | 17 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
577 | 9 | 17 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
578 | 9 | 17 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
579 | 9 | 17 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
580 | 9 | 17 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
581 | 9 | 17 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
582 | 9 | 17 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
583 | 9 | 17 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
584 | 9 | 17 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
585 | 9 | 17 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
586 | 9 | 17 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
587 | 9 | 17 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
588 | 9 | 17 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
589 | 9 | 17 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
590 | 9 | 17 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
591 | 9 | 17 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
592 | 9 | 17 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
593 | 9 | 17 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
594 | 9 | 17 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
595 | 9 | 17 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
596 | 9 | 17 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
597 | 9 | 18 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
598 | 9 | 18 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
599 | 9 | 18 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
600 | 9 | 18 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
601 | 9 | 18 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
602 | 9 | 18 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
603 | 9 | 18 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
604 | 9 | 18 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
605 | 9 | 18 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
606 | 9 | 18 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
607 | 9 | 18 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
608 | 9 | 18 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
609 | 9 | 18 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
610 | 9 | 18 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
611 | 9 | 18 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
612 | 9 | 18 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
613 | 9 | 18 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
614 | 9 | 18 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
615 | 9 | 18 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
616 | 9 | 18 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
617 | 9 | 18 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
618 | 9 | 18 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
619 | 9 | 18 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
620 | 9 | 18 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
621 | 9 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
622 | 10 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
623 | 10 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
624 | 10 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
625 | 10 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
626 | 10 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
627 | 10 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
628 | 10 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
629 | 10 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
630 | 10 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
631 | 10 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
632 | 10 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
633 | 10 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
634 | 10 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
635 | 10 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
636 | 10 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
637 | 10 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
638 | 10 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
639 | 10 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
640 | 10 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
641 | 10 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
642 | 10 | 19 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
643 | 10 | 19 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
644 | 10 | 19 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
645 | 10 | 19 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
646 | 10 | 19 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
647 | 10 | 19 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
648 | 10 | 19 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
649 | 10 | 19 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
650 | 10 | 19 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
651 | 10 | 19 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
652 | 10 | 19 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
653 | 10 | 19 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
654 | 10 | 19 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
655 | 10 | 19 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
656 | 10 | 19 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
657 | 10 | 19 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
658 | 10 | 19 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
659 | 10 | 19 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
660 | 10 | 19 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
661 | 10 | 19 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
662 | 10 | 19 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
663 | 10 | 19 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
664 | 10 | 19 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
665 | 10 | 19 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
666 | 10 | 20 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
667 | 10 | 20 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
668 | 10 | 20 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
669 | 10 | 20 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
670 | 10 | 20 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
671 | 10 | 20 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
672 | 10 | 20 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
673 | 10 | 20 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
674 | 10 | 20 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
675 | 10 | 20 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
676 | 10 | 20 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
677 | 10 | 20 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
678 | 10 | 20 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
679 | 10 | 20 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
680 | 10 | 20 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
681 | 10 | 20 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
682 | 10 | 20 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
683 | 10 | 20 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
684 | 10 | 20 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
685 | 10 | 20 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
686 | 10 | 20 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
687 | 10 | 20 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
688 | 10 | 20 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
689 | 10 | 20 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
690 | 10 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
691 | 11 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
692 | 11 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
693 | 11 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
694 | 11 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
695 | 11 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
696 | 11 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
697 | 11 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
698 | 11 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
699 | 11 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
700 | 11 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
701 | 11 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
702 | 11 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
703 | 11 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
704 | 11 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
705 | 11 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
706 | 11 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
707 | 11 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
708 | 11 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
709 | 11 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
710 | 11 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
711 | 11 | 21 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
712 | 11 | 21 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
713 | 11 | 21 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
714 | 11 | 21 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
715 | 11 | 21 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
716 | 11 | 21 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
717 | 11 | 21 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
718 | 11 | 21 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
719 | 11 | 21 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
720 | 11 | 21 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
721 | 11 | 21 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
722 | 11 | 21 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
723 | 11 | 21 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
724 | 11 | 21 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
725 | 11 | 21 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
726 | 11 | 21 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
727 | 11 | 21 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
728 | 11 | 21 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
729 | 11 | 21 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
730 | 11 | 21 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
731 | 11 | 21 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
732 | 11 | 21 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
733 | 11 | 21 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
734 | 11 | 21 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
735 | 11 | 22 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
736 | 11 | 22 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
737 | 11 | 22 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
738 | 11 | 22 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
739 | 11 | 22 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
740 | 11 | 22 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
741 | 11 | 22 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
742 | 11 | 22 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
743 | 11 | 22 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
744 | 11 | 22 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
745 | 11 | 22 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
746 | 11 | 22 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
747 | 11 | 22 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
748 | 11 | 22 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
749 | 11 | 22 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
750 | 11 | 22 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
751 | 11 | 22 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
752 | 11 | 22 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
753 | 11 | 22 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
754 | 11 | 22 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
755 | 11 | 22 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
756 | 11 | 22 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
757 | 11 | 22 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
758 | 11 | 22 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
759 | 11 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
760 | 12 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
761 | 12 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
762 | 12 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
763 | 12 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
764 | 12 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
765 | 12 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
766 | 12 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
767 | 12 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
768 | 12 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
769 | 12 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
770 | 12 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
771 | 12 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
772 | 12 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
773 | 12 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
774 | 12 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
775 | 12 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
776 | 12 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
777 | 12 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
778 | 12 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
779 | 12 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
780 | 12 | 23 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
781 | 12 | 23 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
782 | 12 | 23 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
783 | 12 | 23 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
784 | 12 | 23 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
785 | 12 | 23 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
786 | 12 | 23 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
787 | 12 | 23 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
788 | 12 | 23 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
789 | 12 | 23 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
790 | 12 | 23 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
791 | 12 | 23 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
792 | 12 | 23 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
793 | 12 | 23 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
794 | 12 | 23 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
795 | 12 | 23 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
796 | 12 | 23 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
797 | 12 | 23 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
798 | 12 | 23 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
799 | 12 | 23 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
800 | 12 | 23 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
801 | 12 | 23 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
802 | 12 | 23 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
803 | 12 | 23 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
804 | 12 | 24 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
805 | 12 | 24 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
806 | 12 | 24 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
807 | 12 | 24 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
808 | 12 | 24 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
809 | 12 | 24 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
810 | 12 | 24 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
811 | 12 | 24 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
812 | 12 | 24 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
813 | 12 | 24 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
814 | 12 | 24 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
815 | 12 | 24 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
816 | 12 | 24 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
817 | 12 | 24 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
818 | 12 | 24 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
819 | 12 | 24 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
820 | 12 | 24 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
821 | 12 | 24 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
822 | 12 | 24 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
823 | 12 | 24 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
824 | 12 | 24 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
825 | 12 | 24 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
826 | 12 | 24 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
827 | 12 | 24 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
828 | 12 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
829 | 13 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
830 | 13 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
831 | 13 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
832 | 13 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
833 | 13 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
834 | 13 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
835 | 13 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
836 | 13 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
837 | 13 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
838 | 13 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
839 | 13 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
840 | 13 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
841 | 13 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
842 | 13 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
843 | 13 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
844 | 13 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
845 | 13 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
846 | 13 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
847 | 13 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
848 | 13 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
849 | 13 | 25 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
850 | 13 | 25 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
851 | 13 | 25 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
852 | 13 | 25 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
853 | 13 | 25 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
854 | 13 | 25 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
855 | 13 | 25 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
856 | 13 | 25 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
857 | 13 | 25 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
858 | 13 | 25 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
859 | 13 | 25 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
860 | 13 | 25 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
861 | 13 | 25 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
862 | 13 | 25 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
863 | 13 | 25 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
864 | 13 | 25 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
865 | 13 | 25 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
866 | 13 | 25 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
867 | 13 | 25 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
868 | 13 | 25 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
869 | 13 | 25 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
870 | 13 | 25 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
871 | 13 | 25 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
872 | 13 | 25 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
873 | 13 | 26 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
874 | 13 | 26 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
875 | 13 | 26 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
876 | 13 | 26 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
877 | 13 | 26 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
878 | 13 | 26 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
879 | 13 | 26 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
880 | 13 | 26 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
881 | 13 | 26 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
882 | 13 | 26 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
883 | 13 | 26 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
884 | 13 | 26 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
885 | 13 | 26 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
886 | 13 | 26 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
887 | 13 | 26 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
888 | 13 | 26 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
889 | 13 | 26 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
890 | 13 | 26 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
891 | 13 | 26 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
892 | 13 | 26 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
893 | 13 | 26 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
894 | 13 | 26 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
895 | 13 | 26 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
896 | 13 | 26 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
897 | 13 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
898 | 14 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
899 | 14 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
900 | 14 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
901 | 14 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
902 | 14 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
903 | 14 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
904 | 14 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
905 | 14 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
906 | 14 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
907 | 14 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
908 | 14 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
909 | 14 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
910 | 14 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
911 | 14 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
912 | 14 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
913 | 14 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
914 | 14 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
915 | 14 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
916 | 14 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
917 | 14 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
918 | 14 | 27 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
919 | 14 | 27 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
920 | 14 | 27 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
921 | 14 | 27 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
922 | 14 | 27 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
923 | 14 | 27 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
924 | 14 | 27 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
925 | 14 | 27 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
926 | 14 | 27 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
927 | 14 | 27 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
928 | 14 | 27 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
929 | 14 | 27 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
930 | 14 | 27 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
931 | 14 | 27 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
932 | 14 | 27 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
933 | 14 | 27 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
934 | 14 | 27 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
935 | 14 | 27 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
936 | 14 | 27 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
937 | 14 | 27 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
938 | 14 | 27 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
939 | 14 | 27 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
940 | 14 | 27 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
941 | 14 | 27 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
942 | 14 | 28 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
943 | 14 | 28 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
944 | 14 | 28 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
945 | 14 | 28 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
946 | 14 | 28 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
947 | 14 | 28 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
948 | 14 | 28 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
949 | 14 | 28 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
950 | 14 | 28 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
951 | 14 | 28 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
952 | 14 | 28 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
953 | 14 | 28 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
954 | 14 | 28 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
955 | 14 | 28 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
956 | 14 | 28 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
957 | 14 | 28 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
958 | 14 | 28 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
959 | 14 | 28 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
960 | 14 | 28 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
961 | 14 | 28 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
962 | 14 | 28 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
963 | 14 | 28 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
964 | 14 | 28 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
965 | 14 | 28 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
966 | 14 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
967 | 15 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
968 | 15 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
969 | 15 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
970 | 15 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
971 | 15 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
972 | 15 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
973 | 15 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
974 | 15 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
975 | 15 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
976 | 15 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
977 | 15 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
978 | 15 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
979 | 15 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
980 | 15 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
981 | 15 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
982 | 15 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
983 | 15 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
984 | 15 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
985 | 15 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
986 | 15 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
987 | 15 | 29 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
988 | 15 | 29 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
989 | 15 | 29 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
990 | 15 | 29 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
991 | 15 | 29 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
992 | 15 | 29 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
993 | 15 | 29 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
994 | 15 | 29 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
995 | 15 | 29 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
996 | 15 | 29 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
997 | 15 | 29 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
998 | 15 | 29 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
999 | 15 | 29 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1000 | 15 | 29 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1001 | 15 | 29 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1002 | 15 | 29 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1003 | 15 | 29 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1004 | 15 | 29 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1005 | 15 | 29 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1006 | 15 | 29 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1007 | 15 | 29 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1008 | 15 | 29 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1009 | 15 | 29 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1010 | 15 | 29 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1011 | 15 | 30 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1012 | 15 | 30 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1013 | 15 | 30 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1014 | 15 | 30 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1015 | 15 | 30 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1016 | 15 | 30 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1017 | 15 | 30 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1018 | 15 | 30 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1019 | 15 | 30 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1020 | 15 | 30 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1021 | 15 | 30 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1022 | 15 | 30 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1023 | 15 | 30 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1024 | 15 | 30 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1025 | 15 | 30 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1026 | 15 | 30 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1027 | 15 | 30 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1028 | 15 | 30 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1029 | 15 | 30 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1030 | 15 | 30 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1031 | 15 | 30 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1032 | 15 | 30 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1033 | 15 | 30 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1034 | 15 | 30 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1035 | 15 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1036 | 16 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1037 | 16 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1038 | 16 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1039 | 16 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1040 | 16 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1041 | 16 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1042 | 16 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1043 | 16 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1044 | 16 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1045 | 16 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1046 | 16 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1047 | 16 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1048 | 16 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1049 | 16 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1050 | 16 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1051 | 16 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1052 | 16 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1053 | 16 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1054 | 16 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1055 | 16 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1056 | 16 | 31 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1057 | 16 | 31 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1058 | 16 | 31 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1059 | 16 | 31 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1060 | 16 | 31 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1061 | 16 | 31 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1062 | 16 | 31 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1063 | 16 | 31 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1064 | 16 | 31 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1065 | 16 | 31 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1066 | 16 | 31 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1067 | 16 | 31 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1068 | 16 | 31 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1069 | 16 | 31 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1070 | 16 | 31 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1071 | 16 | 31 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1072 | 16 | 31 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1073 | 16 | 31 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1074 | 16 | 31 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1075 | 16 | 31 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1076 | 16 | 31 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1077 | 16 | 31 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1078 | 16 | 31 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1079 | 16 | 31 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1080 | 16 | 32 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1081 | 16 | 32 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1082 | 16 | 32 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1083 | 16 | 32 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1084 | 16 | 32 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1085 | 16 | 32 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1086 | 16 | 32 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1087 | 16 | 32 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1088 | 16 | 32 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1089 | 16 | 32 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1090 | 16 | 32 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1091 | 16 | 32 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1092 | 16 | 32 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1093 | 16 | 32 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1094 | 16 | 32 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1095 | 16 | 32 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1096 | 16 | 32 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1097 | 16 | 32 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1098 | 16 | 32 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1099 | 16 | 32 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1100 | 16 | 32 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1101 | 16 | 32 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1102 | 16 | 32 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1103 | 16 | 32 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1104 | 16 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1105 | 17 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1106 | 17 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1107 | 17 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1108 | 17 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1109 | 17 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1110 | 17 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1111 | 17 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1112 | 17 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1113 | 17 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1114 | 17 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1115 | 17 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1116 | 17 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1117 | 17 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1118 | 17 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1119 | 17 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1120 | 17 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1121 | 17 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1122 | 17 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1123 | 17 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1124 | 17 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1125 | 17 | 33 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1126 | 17 | 33 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1127 | 17 | 33 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1128 | 17 | 33 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1129 | 17 | 33 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1130 | 17 | 33 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1131 | 17 | 33 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1132 | 17 | 33 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1133 | 17 | 33 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1134 | 17 | 33 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1135 | 17 | 33 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1136 | 17 | 33 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1137 | 17 | 33 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1138 | 17 | 33 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1139 | 17 | 33 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1140 | 17 | 33 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1141 | 17 | 33 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1142 | 17 | 33 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1143 | 17 | 33 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1144 | 17 | 33 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1145 | 17 | 33 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1146 | 17 | 33 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1147 | 17 | 33 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1148 | 17 | 33 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1149 | 17 | 34 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1150 | 17 | 34 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1151 | 17 | 34 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1152 | 17 | 34 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1153 | 17 | 34 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1154 | 17 | 34 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1155 | 17 | 34 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1156 | 17 | 34 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1157 | 17 | 34 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1158 | 17 | 34 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1159 | 17 | 34 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1160 | 17 | 34 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1161 | 17 | 34 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1162 | 17 | 34 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1163 | 17 | 34 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1164 | 17 | 34 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1165 | 17 | 34 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1166 | 17 | 34 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1167 | 17 | 34 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1168 | 17 | 34 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1169 | 17 | 34 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1170 | 17 | 34 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1171 | 17 | 34 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1172 | 17 | 34 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1173 | 17 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1174 | 18 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1175 | 18 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1176 | 18 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1177 | 18 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1178 | 18 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1179 | 18 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1180 | 18 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1181 | 18 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1182 | 18 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1183 | 18 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1184 | 18 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1185 | 18 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1186 | 18 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1187 | 18 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1188 | 18 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1189 | 18 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1190 | 18 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1191 | 18 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1192 | 18 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1193 | 18 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1194 | 18 | 35 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1195 | 18 | 35 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1196 | 18 | 35 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1197 | 18 | 35 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1198 | 18 | 35 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1199 | 18 | 35 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1200 | 18 | 35 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1201 | 18 | 35 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1202 | 18 | 35 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1203 | 18 | 35 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1204 | 18 | 35 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1205 | 18 | 35 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1206 | 18 | 35 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1207 | 18 | 35 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1208 | 18 | 35 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1209 | 18 | 35 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1210 | 18 | 35 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1211 | 18 | 35 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1212 | 18 | 35 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1213 | 18 | 35 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1214 | 18 | 35 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1215 | 18 | 35 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1216 | 18 | 35 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1217 | 18 | 35 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1218 | 18 | 36 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1219 | 18 | 36 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1220 | 18 | 36 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1221 | 18 | 36 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1222 | 18 | 36 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1223 | 18 | 36 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1224 | 18 | 36 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1225 | 18 | 36 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1226 | 18 | 36 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1227 | 18 | 36 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1228 | 18 | 36 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1229 | 18 | 36 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1230 | 18 | 36 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1231 | 18 | 36 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1232 | 18 | 36 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1233 | 18 | 36 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1234 | 18 | 36 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1235 | 18 | 36 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1236 | 18 | 36 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1237 | 18 | 36 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1238 | 18 | 36 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1239 | 18 | 36 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1240 | 18 | 36 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1241 | 18 | 36 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1242 | 18 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1243 | 19 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1244 | 19 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1245 | 19 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1246 | 19 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1247 | 19 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1248 | 19 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1249 | 19 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1250 | 19 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1251 | 19 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1252 | 19 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1253 | 19 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1254 | 19 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1255 | 19 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1256 | 19 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1257 | 19 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1258 | 19 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1259 | 19 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1260 | 19 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1261 | 19 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1262 | 19 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1263 | 19 | 37 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1264 | 19 | 37 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1265 | 19 | 37 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1266 | 19 | 37 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1267 | 19 | 37 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1268 | 19 | 37 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1269 | 19 | 37 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1270 | 19 | 37 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1271 | 19 | 37 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1272 | 19 | 37 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1273 | 19 | 37 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1274 | 19 | 37 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1275 | 19 | 37 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1276 | 19 | 37 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1277 | 19 | 37 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1278 | 19 | 37 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1279 | 19 | 37 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1280 | 19 | 37 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1281 | 19 | 37 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1282 | 19 | 37 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1283 | 19 | 37 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1284 | 19 | 37 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1285 | 19 | 37 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1286 | 19 | 37 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1287 | 19 | 38 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1288 | 19 | 38 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1289 | 19 | 38 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1290 | 19 | 38 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1291 | 19 | 38 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1292 | 19 | 38 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1293 | 19 | 38 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1294 | 19 | 38 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1295 | 19 | 38 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1296 | 19 | 38 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1297 | 19 | 38 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1298 | 19 | 38 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1299 | 19 | 38 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1300 | 19 | 38 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1301 | 19 | 38 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1302 | 19 | 38 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1303 | 19 | 38 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1304 | 19 | 38 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1305 | 19 | 38 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1306 | 19 | 38 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1307 | 19 | 38 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1308 | 19 | 38 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1309 | 19 | 38 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1310 | 19 | 38 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1311 | 19 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1312 | 20 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1313 | 20 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1314 | 20 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1315 | 20 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1316 | 20 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1317 | 20 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1318 | 20 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1319 | 20 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1320 | 20 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1321 | 20 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1322 | 20 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1323 | 20 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1324 | 20 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1325 | 20 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1326 | 20 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1327 | 20 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1328 | 20 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1329 | 20 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1330 | 20 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1331 | 20 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1332 | 20 | 39 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1333 | 20 | 39 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1334 | 20 | 39 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1335 | 20 | 39 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1336 | 20 | 39 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1337 | 20 | 39 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1338 | 20 | 39 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1339 | 20 | 39 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1340 | 20 | 39 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1341 | 20 | 39 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1342 | 20 | 39 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1343 | 20 | 39 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1344 | 20 | 39 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1345 | 20 | 39 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1346 | 20 | 39 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1347 | 20 | 39 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1348 | 20 | 39 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1349 | 20 | 39 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1350 | 20 | 39 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1351 | 20 | 39 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1352 | 20 | 39 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1353 | 20 | 39 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1354 | 20 | 39 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1355 | 20 | 39 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1356 | 20 | 40 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1357 | 20 | 40 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1358 | 20 | 40 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1359 | 20 | 40 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1360 | 20 | 40 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1361 | 20 | 40 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1362 | 20 | 40 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1363 | 20 | 40 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1364 | 20 | 40 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1365 | 20 | 40 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1366 | 20 | 40 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1367 | 20 | 40 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1368 | 20 | 40 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1369 | 20 | 40 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1370 | 20 | 40 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1371 | 20 | 40 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1372 | 20 | 40 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1373 | 20 | 40 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1374 | 20 | 40 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1375 | 20 | 40 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1376 | 20 | 40 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1377 | 20 | 40 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1378 | 20 | 40 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1379 | 20 | 40 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1380 | 20 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1381 | 21 |  | 1 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1382 | 21 |  | 2 | 1 | 1 | FALSE | Preload and jacking up at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1383 | 21 |  | 3 | 1 | 1 | FALSE | Release crane, gangway etc and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1384 | 21 |  | 4 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1385 | 21 |  | 5 | 1 | 1 | FALSE | Loadout Nacelle #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1386 | 21 |  | 6 | 1 | 1 | FALSE | Loadout Tower #1 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1387 | 21 |  | 7 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1388 | 21 |  | 8 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1389 | 21 |  | 9 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1390 | 21 |  | 10 | 1 | 1 | FALSE | Load in/out WTG supplier equipment | OFFSHORE | 1 | 1 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1391 | 21 |  | 11 | 1 | 1 | FALSE | Loadout Nacelle #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1392 | 21 |  | 12 | 1 | 1 | FALSE | Loadout Tower #2 | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1393 | 21 |  | 13 | 1 | 1 | FALSE | Loadout Blade 1 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1394 | 21 |  | 14 | 1 | 1 | FALSE | Loadout Blade 2 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1395 | 21 |  | 15 | 1 | 1 | FALSE | Loadout Blade 3 | OFFSHORE | 1.5 | 2.25 | 8.1967 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1396 | 21 |  | 16 | 1 | 1 | FALSE | Secure of crane, gangway (at port)) | OFFSHORE | 3 | 3 | 18 | 100 | 20 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1397 | 21 |  | 17 | 1 | 1 | FALSE | Jacking down at port | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1398 | 21 |  | 18 | 1 | 1 | FALSE | Port maneuvering | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1399 | 21 |  | 19 | 1 | 1 | FALSE | Transit from port to site | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1400 | 21 |  | 20 | 1 | 1 | FALSE | DP field check | OFFSHORE | 0.5 | 0.75 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1401 | 21 | 41 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1402 | 21 | 41 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1403 | 21 | 41 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1404 | 21 | 41 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1405 | 21 | 41 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1406 | 21 | 41 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1407 | 21 | 41 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1408 | 21 | 41 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1409 | 21 | 41 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1410 | 21 | 41 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1411 | 21 | 41 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1412 | 21 | 41 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1413 | 21 | 41 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1414 | 21 | 41 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1415 | 21 | 41 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1416 | 21 | 41 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1417 | 21 | 41 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1418 | 21 | 41 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1419 | 21 | 41 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1420 | 21 | 41 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1421 | 21 | 41 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1422 | 21 | 41 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1423 | 21 | 41 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1424 | 21 | 41 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1425 | 21 | 42 | 21 | 2 | 1 | FALSE | Transit to next foundation | OFFSHORE | 1 | 1.5 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1426 | 21 | 42 | 22 | 2 | 1 | FALSE | Positioning at WTG location | OFFSHORE | 1 | 1.5 | 12.4 | 100 | 2.5 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1427 | 21 | 42 | 23 | 2 | 1 | FALSE | Preload and jacking up at site | OFFSHORE | 4 | 6 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1428 | 21 | 42 | 24 | 2 | 1 | FALSE | Release crane, gangway and prep for lifting | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1429 | 21 | 42 | 25 | 2 | 1 | FALSE | Remove TP cover and Preparation of TP | OFFSHORE | 1 | 1 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1430 | 21 | 42 | 26 | 2 | 1 | FALSE | Tower preparation, removal of seafastening bolts | OFFSHORE | 2 | 2 | 11.6788 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1431 | 21 | 42 | 27 | 2 | 1 | FALSE | Tower rigging-up (attached lifting equipment) | OFFSHORE | 1 | 1.5 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Start | MOST_STRINGENT | OFFSHORE
1432 | 21 | 42 | 28 | 2 | 1 | FALSE | Tower Lifting (safe-to-safe) | OFFSHORE | 3.5 | 5.25 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | Continue | MOST_STRINGENT | OFFSHORE
1433 | 21 | 42 | 29 | 2 | 1 | FALSE | Tower derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G1 | End | MOST_STRINGENT | OFFSHORE
1434 | 21 | 42 | 30 | 2 | 1 | FALSE | Nacelle preparation and rigging | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Start | MOST_STRINGENT | OFFSHORE
1435 | 21 | 42 | 31 | 2 | 1 | FALSE | Nacelle Lifting (safe-to-safe) | OFFSHORE | 2.25 | 3.375 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | Continue | MOST_STRINGENT | OFFSHORE
1436 | 21 | 42 | 32 | 2 | 1 | FALSE | Nacelle derigging (remove lifting equipment) | OFFSHORE | 0.5 | 0.75 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G2 | End | MOST_STRINGENT | OFFSHORE
1437 | 21 | 42 | 33 | 2 | 1 | FALSE | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | 0.5 | 0.75 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Start | MOST_STRINGENT | OFFSHORE
1438 | 21 | 42 | 34 | 2 | 1 | FALSE | Blade #1 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | Continue | MOST_STRINGENT | OFFSHORE
1439 | 21 | 42 | 35 | 2 | 1 | FALSE | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G3 | End | MOST_STRINGENT | OFFSHORE
1440 | 21 | 42 | 36 | 2 | 1 | FALSE | Blade #2 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | Start | MOST_STRINGENT | OFFSHORE
1441 | 21 | 42 | 37 | 2 | 1 | FALSE | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G4 | End | MOST_STRINGENT | OFFSHORE
1442 | 21 | 42 | 38 | 2 | 1 | FALSE | Blade #3 Lifting (safe-to-safe) | OFFSHORE | 1.75 | 2.625 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | Start | MOST_STRINGENT | OFFSHORE
1443 | 21 | 42 | 39 | 2 | 1 | FALSE | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | 1.5 | 2.25 | 8.7591 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  | G5 | End | MOST_STRINGENT | OFFSHORE
1444 | 21 | 42 | 40 | 2 | 1 | FALSE | Handling HSBM and lifting tools | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1445 | 21 | 42 | 41 | 2 | 1 | FALSE | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | 1 | 1 | 10.219 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1446 | 21 | 42 | 42 | 2 | 1 | FALSE | Turbine general completion works | OFFSHORE | 3 | 3 | 13.1387 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1447 | 21 | 42 | 43 | 2 | 1 | FALSE | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | 3 | 3 | 18 | 100 | 3.2 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone
1448 | 21 | 42 | 44 | 2 | 1 | TRUE | Jacking down at site | OFFSHORE | 2 | 3 | 12.4 | 100 | 2 | 7 | 1.03 | 00:00 | 00:00 | None |  |  | Standalone
1449 | 21 |  | 45 | 3 | 1 | FALSE | Transit from site to port | OFFSHORE | 5.2 | 7.8 | 22 | 100 | 3 | 20 | 100 | 00:00 | 00:00 | None |  |  | Standalone

## OUT_years coverage
OUT_years coverage
Hindcast simulations included in or excluded from planning statistics.
Historical start year | Included in planning statistics | Message
1979 | TRUE | Completed
1980 | TRUE | Completed
1981 | TRUE | Completed
1982 | TRUE | Completed
1983 | TRUE | Completed
1984 | TRUE | Completed
1985 | TRUE | Completed
1986 | TRUE | Completed
1987 | TRUE | Completed
1988 | TRUE | Completed
1989 | TRUE | Completed
1990 | TRUE | Completed
1991 | TRUE | Completed
1992 | TRUE | Completed
1993 | TRUE | Completed
1994 | TRUE | Completed
1995 | TRUE | Completed
1996 | TRUE | Completed
1997 | TRUE | Completed
1998 | TRUE | Completed
1999 | TRUE | Completed
2000 | TRUE | Completed
2001 | TRUE | Completed
2002 | TRUE | Completed
2003 | TRUE | Completed
2004 | TRUE | Completed
2005 | TRUE | Completed
2006 | TRUE | Completed
2007 | TRUE | Completed
2008 | TRUE | Completed
2009 | TRUE | Completed
2010 | TRUE | Completed
2011 | TRUE | Completed
2012 | TRUE | Completed
2013 | TRUE | Completed
2014 | TRUE | Completed
2015 | TRUE | Completed
2016 | TRUE | Completed
2017 | TRUE | Completed
2018 | TRUE | Completed
2019 | TRUE | Completed
2020 | TRUE | Completed
2021 | TRUE | Completed
2022 | TRUE | Completed
2023 | FALSE | Unable to assess - End of available weather data

## OUT_P0 run
OUT_P0 run — Exact deterministic no-weather programme
Learning-adjusted productive durations executed continuously. Weather downtime = 0 and simulation-timestep rounding is not applied to P0.
Timestamp | End timestamp | Duration [h] | Activity | Location | Status | Cycle | Position | Activity ID | Learning multiplier | Safe-to-safe group | Group role | Group method | Weather window [h] | Cumulative P0 [h] | Remaining campaign [h] | Downtime type | Main factor | Downtime category
2030-04-01 | 2030-04-01 01:00 | 1 | Port maneuvering | OFFSHORE | Working | 1 |  | 1 | 1 |  | Standalone |  | 1.5 | 1 | 2746.9
2030-04-01 01:00 | 2030-04-01 03:00 | 2 | Preload and jacking up at port | OFFSHORE | Working | 1 |  | 2 | 1 |  | Standalone |  | 3 | 3 | 2744.9
2030-04-01 03:00 | 2030-04-01 06:00 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 1 |  | 3 | 1 |  | Standalone |  | 3 | 6 | 2741.9
2030-04-01 06:00 | 2030-04-01 07:30 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working | 1 |  | 4 | 1.5 |  | Standalone |  | 1 | 7.5 | 2740.4
2030-04-01 07:30 | 2030-04-01 10:52 | 3.375 | Loadout Nacelle #1 | OFFSHORE | Working | 1 |  | 5 | 1.5 |  | Standalone |  | 3.375 | 10.875 | 2737.025
2030-04-01 10:52 | 2030-04-01 14:15 | 3.375 | Loadout Tower #1 | OFFSHORE | Working | 1 |  | 6 | 1.5 |  | Standalone |  | 3.375 | 14.25 | 2733.65
2030-04-01 14:15 | 2030-04-01 16:30 | 2.25 | Loadout Blade 1 | OFFSHORE | Working | 1 |  | 7 | 1.5 |  | Standalone |  | 2.25 | 16.5 | 2731.4
2030-04-01 16:30 | 2030-04-01 18:45 | 2.25 | Loadout Blade 2 | OFFSHORE | Working | 1 |  | 8 | 1.5 |  | Standalone |  | 2.25 | 18.75 | 2729.15
2030-04-01 18:45 | 2030-04-01 21:00 | 2.25 | Loadout Blade 3 | OFFSHORE | Working | 1 |  | 9 | 1.5 |  | Standalone |  | 2.25 | 21 | 2726.9
2030-04-01 21:00 | 2030-04-01 22:30 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working | 1 |  | 10 | 1.5 |  | Standalone |  | 1 | 22.5 | 2725.4
2030-04-01 22:30 | 2030-04-02 01:52 | 3.375 | Loadout Nacelle #2 | OFFSHORE | Working | 1 |  | 11 | 1.5 |  | Standalone |  | 3.375 | 25.875 | 2722.025
2030-04-02 01:52 | 2030-04-02 05:15 | 3.375 | Loadout Tower #2 | OFFSHORE | Working | 1 |  | 12 | 1.5 |  | Standalone |  | 3.375 | 29.25 | 2718.65
2030-04-02 05:15 | 2030-04-02 07:30 | 2.25 | Loadout Blade 1 | OFFSHORE | Working | 1 |  | 13 | 1.5 |  | Standalone |  | 2.25 | 31.5 | 2716.4
2030-04-02 07:30 | 2030-04-02 09:45 | 2.25 | Loadout Blade 2 | OFFSHORE | Working | 1 |  | 14 | 1.5 |  | Standalone |  | 2.25 | 33.75 | 2714.15
2030-04-02 09:45 | 2030-04-02 12:00 | 2.25 | Loadout Blade 3 | OFFSHORE | Working | 1 |  | 15 | 1.5 |  | Standalone |  | 2.25 | 36 | 2711.9
2030-04-02 12:00 | 2030-04-02 15:00 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 1 |  | 16 | 1 |  | Standalone |  | 3 | 39 | 2708.9
2030-04-02 15:00 | 2030-04-02 17:00 | 2 | Jacking down at port | OFFSHORE | Working | 1 |  | 17 | 1 |  | Standalone |  | 3 | 41 | 2706.9
2030-04-02 17:00 | 2030-04-02 18:00 | 1 | Port maneuvering | OFFSHORE | Working | 1 |  | 18 | 1 |  | Standalone |  | 1.5 | 42 | 2705.9
2030-04-02 18:00 | 2030-04-02 23:12 | 5.2 | Transit from port to site | OFFSHORE | Working | 1 |  | 19 | 1 |  | Standalone |  | 7.8 | 47.2 | 2700.7
2030-04-02 23:12 | 2030-04-02 23:42 | 0.5 | DP field check | OFFSHORE | Working | 1 |  | 20 | 1 |  | Standalone |  | 0.75 | 47.7 | 2700.2
2030-04-02 23:42 | 2030-04-03 00:42 | 1 | Transit to next foundation | OFFSHORE | Working | 1 | 1 | 21 | 1 |  | Standalone |  | 1.5 | 48.7 | 2699.2
2030-04-03 00:42 | 2030-04-03 01:42 | 1 | Positioning at WTG location | OFFSHORE | Working | 1 | 1 | 22 | 1 |  | Standalone |  | 1.5 | 49.7 | 2698.2
2030-04-03 01:42 | 2030-04-03 05:42 | 4 | Preload and jacking up at site | OFFSHORE | Working | 1 | 1 | 23 | 1 |  | Standalone |  | 6 | 53.7 | 2694.2
2030-04-03 05:42 | 2030-04-03 08:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 1 | 1 | 24 | 1 |  | Standalone |  | 3 | 56.7 | 2691.2
2030-04-03 08:42 | 2030-04-03 10:12 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 1 | 1 | 25 | 1.5 |  | Standalone |  | 1 | 58.2 | 2689.7
2030-04-03 10:12 | 2030-04-03 13:12 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 1 | 1 | 26 | 1.5 |  | Standalone |  | 2 | 61.2 | 2686.7
2030-04-03 13:12 | 2030-04-03 14:42 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 1 | 1 | 27 | 1.5 | G1 | Start | MOST_STRINGENT | 1.5 | 62.7 | 2685.2
2030-04-03 14:42 | 2030-04-03 19:57 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 1 | 28 | 1.5 | G1 | Continue | MOST_STRINGENT | 5.25 | 67.95 | 2679.95
2030-04-03 19:57 | 2030-04-03 20:42 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 1 | 1 | 29 | 1.5 | G1 | End | MOST_STRINGENT | 0.75 | 68.7 | 2679.2
2030-04-03 20:42 | 2030-04-03 21:27 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working | 1 | 1 | 30 | 1.5 | G2 | Start | MOST_STRINGENT | 0.75 | 69.45 | 2678.45
2030-04-03 21:27 | 2030-04-04 00:50 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 1 | 31 | 1.5 | G2 | Continue | MOST_STRINGENT | 3.375 | 72.825 | 2675.075
2030-04-04 00:50 | 2030-04-04 01:35 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 1 | 1 | 32 | 1.5 | G2 | End | MOST_STRINGENT | 0.75 | 73.575 | 2674.325
2030-04-04 01:35 | 2030-04-04 02:20 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 1 | 1 | 33 | 1.5 | G3 | Start | MOST_STRINGENT | 0.75 | 74.325 | 2673.575
2030-04-04 02:20 | 2030-04-04 04:57 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 1 | 34 | 1.5 | G3 | Continue | MOST_STRINGENT | 2.625 | 76.95 | 2670.95
2030-04-04 04:57 | 2030-04-04 07:12 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 1 | 1 | 35 | 1.5 | G3 | End | MOST_STRINGENT | 2.25 | 79.2 | 2668.7
2030-04-04 07:12 | 2030-04-04 09:50 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 1 | 36 | 1.5 | G4 | Start | MOST_STRINGENT | 2.625 | 81.825 | 2666.075
2030-04-04 09:50 | 2030-04-04 12:05 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 1 | 1 | 37 | 1.5 | G4 | End | MOST_STRINGENT | 2.25 | 84.075 | 2663.825
2030-04-04 12:05 | 2030-04-04 14:42 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 1 | 38 | 1.5 | G5 | Start | MOST_STRINGENT | 2.625 | 86.7 | 2661.2
2030-04-04 14:42 | 2030-04-04 16:57 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 1 | 1 | 39 | 1.5 | G5 | End | MOST_STRINGENT | 2.25 | 88.95 | 2658.95
2030-04-04 16:57 | 2030-04-04 18:27 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working | 1 | 1 | 40 | 1.5 |  | Standalone |  | 1 | 90.45 | 2657.45
2030-04-04 18:27 | 2030-04-04 19:57 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 1 | 1 | 41 | 1.5 |  | Standalone |  | 1 | 91.95 | 2655.95
2030-04-04 19:57 | 2030-04-05 00:27 | 4.5 | Turbine general completion works | OFFSHORE | Working | 1 | 1 | 42 | 1.5 |  | Standalone |  | 3 | 96.45 | 2651.45
2030-04-05 00:27 | 2030-04-05 03:27 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 1 | 1 | 43 | 1 |  | Standalone |  | 3 | 99.45 | 2648.45
2030-04-05 03:27 | 2030-04-05 05:27 | 2 | Jacking down at site | OFFSHORE | Working | 1 | 1 | 44 | 1 |  | Standalone |  | 3 | 101.45 | 2646.45
2030-04-05 05:27 | 2030-04-05 06:27 | 1 | Transit to next foundation | OFFSHORE | Working | 1 | 2 | 21 | 1 |  | Standalone |  | 1.5 | 102.45 | 2645.45
2030-04-05 06:27 | 2030-04-05 07:27 | 1 | Positioning at WTG location | OFFSHORE | Working | 1 | 2 | 22 | 1 |  | Standalone |  | 1.5 | 103.45 | 2644.45
2030-04-05 07:27 | 2030-04-05 11:27 | 4 | Preload and jacking up at site | OFFSHORE | Working | 1 | 2 | 23 | 1 |  | Standalone |  | 6 | 107.45 | 2640.45
2030-04-05 11:27 | 2030-04-05 14:27 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 1 | 2 | 24 | 1 |  | Standalone |  | 3 | 110.45 | 2637.45
2030-04-05 14:27 | 2030-04-05 15:57 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 1 | 2 | 25 | 1.5 |  | Standalone |  | 1 | 111.95 | 2635.95
2030-04-05 15:57 | 2030-04-05 18:57 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 1 | 2 | 26 | 1.5 |  | Standalone |  | 2 | 114.95 | 2632.95
2030-04-05 18:57 | 2030-04-05 20:27 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 1 | 2 | 27 | 1.5 | G1 | Start | MOST_STRINGENT | 1.5 | 116.45 | 2631.45
2030-04-05 20:27 | 2030-04-06 01:42 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 2 | 28 | 1.5 | G1 | Continue | MOST_STRINGENT | 5.25 | 121.7 | 2626.2
2030-04-06 01:42 | 2030-04-06 02:27 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 1 | 2 | 29 | 1.5 | G1 | End | MOST_STRINGENT | 0.75 | 122.45 | 2625.45
2030-04-06 02:27 | 2030-04-06 03:12 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working | 1 | 2 | 30 | 1.5 | G2 | Start | MOST_STRINGENT | 0.75 | 123.2 | 2624.7
2030-04-06 03:12 | 2030-04-06 06:34 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 2 | 31 | 1.5 | G2 | Continue | MOST_STRINGENT | 3.375 | 126.575 | 2621.325
2030-04-06 06:34 | 2030-04-06 07:20 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 1 | 2 | 32 | 1.5 | G2 | End | MOST_STRINGENT | 0.75 | 127.325 | 2620.575
2030-04-06 07:20 | 2030-04-06 08:04 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 1 | 2 | 33 | 1.5 | G3 | Start | MOST_STRINGENT | 0.75 | 128.075 | 2619.825
2030-04-06 08:04 | 2030-04-06 10:42 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 2 | 34 | 1.5 | G3 | Continue | MOST_STRINGENT | 2.625 | 130.7 | 2617.2
2030-04-06 10:42 | 2030-04-06 12:57 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 1 | 2 | 35 | 1.5 | G3 | End | MOST_STRINGENT | 2.25 | 132.95 | 2614.95
2030-04-06 12:57 | 2030-04-06 15:34 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 2 | 36 | 1.5 | G4 | Start | MOST_STRINGENT | 2.625 | 135.575 | 2612.325
2030-04-06 15:34 | 2030-04-06 17:50 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 1 | 2 | 37 | 1.5 | G4 | End | MOST_STRINGENT | 2.25 | 137.825 | 2610.075
2030-04-06 17:50 | 2030-04-06 20:27 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 1 | 2 | 38 | 1.5 | G5 | Start | MOST_STRINGENT | 2.625 | 140.45 | 2607.45
2030-04-06 20:27 | 2030-04-06 22:42 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 1 | 2 | 39 | 1.5 | G5 | End | MOST_STRINGENT | 2.25 | 142.7 | 2605.2
2030-04-06 22:42 | 2030-04-07 00:12 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working | 1 | 2 | 40 | 1.5 |  | Standalone |  | 1 | 144.2 | 2603.7
2030-04-07 00:12 | 2030-04-07 01:42 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 1 | 2 | 41 | 1.5 |  | Standalone |  | 1 | 145.7 | 2602.2
2030-04-07 01:42 | 2030-04-07 06:12 | 4.5 | Turbine general completion works | OFFSHORE | Working | 1 | 2 | 42 | 1.5 |  | Standalone |  | 3 | 150.2 | 2597.7
2030-04-07 06:12 | 2030-04-07 09:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 1 | 2 | 43 | 1 |  | Standalone |  | 3 | 153.2 | 2594.7
2030-04-07 09:12 | 2030-04-07 11:12 | 2 | Jacking down at site | OFFSHORE | Working | 1 | 2 | 44 | 1 |  | Standalone |  | 3 | 155.2 | 2592.7
2030-04-07 11:12 | 2030-04-07 16:24 | 5.2 | Transit from site to port | OFFSHORE | Working | 1 |  | 45 | 1 |  | Standalone |  | 7.8 | 160.4 | 2587.5
2030-04-07 16:24 | 2030-04-07 17:24 | 1 | Port maneuvering | OFFSHORE | Working | 2 |  | 1 | 1 |  | Standalone |  | 1.5 | 161.4 | 2586.5
2030-04-07 17:24 | 2030-04-07 19:24 | 2 | Preload and jacking up at port | OFFSHORE | Working | 2 |  | 2 | 1 |  | Standalone |  | 3 | 163.4 | 2584.5
2030-04-07 19:24 | 2030-04-07 22:24 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 2 |  | 3 | 1 |  | Standalone |  | 3 | 166.4 | 2581.5
2030-04-07 22:24 | 2030-04-07 23:54 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working | 2 |  | 4 | 1.5 |  | Standalone |  | 1 | 167.9 | 2580
2030-04-07 23:54 | 2030-04-08 03:16 | 3.375 | Loadout Nacelle #1 | OFFSHORE | Working | 2 |  | 5 | 1.5 |  | Standalone |  | 3.375 | 171.275 | 2576.625
2030-04-08 03:16 | 2030-04-08 06:39 | 3.375 | Loadout Tower #1 | OFFSHORE | Working | 2 |  | 6 | 1.5 |  | Standalone |  | 3.375 | 174.65 | 2573.25
2030-04-08 06:39 | 2030-04-08 08:54 | 2.25 | Loadout Blade 1 | OFFSHORE | Working | 2 |  | 7 | 1.5 |  | Standalone |  | 2.25 | 176.9 | 2571
2030-04-08 08:54 | 2030-04-08 11:09 | 2.25 | Loadout Blade 2 | OFFSHORE | Working | 2 |  | 8 | 1.5 |  | Standalone |  | 2.25 | 179.15 | 2568.75
2030-04-08 11:09 | 2030-04-08 13:24 | 2.25 | Loadout Blade 3 | OFFSHORE | Working | 2 |  | 9 | 1.5 |  | Standalone |  | 2.25 | 181.4 | 2566.5
2030-04-08 13:24 | 2030-04-08 14:54 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working | 2 |  | 10 | 1.5 |  | Standalone |  | 1 | 182.9 | 2565
2030-04-08 14:54 | 2030-04-08 18:16 | 3.375 | Loadout Nacelle #2 | OFFSHORE | Working | 2 |  | 11 | 1.5 |  | Standalone |  | 3.375 | 186.275 | 2561.625
2030-04-08 18:16 | 2030-04-08 21:39 | 3.375 | Loadout Tower #2 | OFFSHORE | Working | 2 |  | 12 | 1.5 |  | Standalone |  | 3.375 | 189.65 | 2558.25
2030-04-08 21:39 | 2030-04-08 23:54 | 2.25 | Loadout Blade 1 | OFFSHORE | Working | 2 |  | 13 | 1.5 |  | Standalone |  | 2.25 | 191.9 | 2556
2030-04-08 23:54 | 2030-04-09 02:09 | 2.25 | Loadout Blade 2 | OFFSHORE | Working | 2 |  | 14 | 1.5 |  | Standalone |  | 2.25 | 194.15 | 2553.75
2030-04-09 02:09 | 2030-04-09 04:24 | 2.25 | Loadout Blade 3 | OFFSHORE | Working | 2 |  | 15 | 1.5 |  | Standalone |  | 2.25 | 196.4 | 2551.5
2030-04-09 04:24 | 2030-04-09 07:24 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 2 |  | 16 | 1 |  | Standalone |  | 3 | 199.4 | 2548.5
2030-04-09 07:24 | 2030-04-09 09:24 | 2 | Jacking down at port | OFFSHORE | Working | 2 |  | 17 | 1 |  | Standalone |  | 3 | 201.4 | 2546.5
2030-04-09 09:24 | 2030-04-09 10:24 | 1 | Port maneuvering | OFFSHORE | Working | 2 |  | 18 | 1 |  | Standalone |  | 1.5 | 202.4 | 2545.5
2030-04-09 10:24 | 2030-04-09 15:36 | 5.2 | Transit from port to site | OFFSHORE | Working | 2 |  | 19 | 1 |  | Standalone |  | 7.8 | 207.6 | 2540.3
2030-04-09 15:36 | 2030-04-09 16:06 | 0.5 | DP field check | OFFSHORE | Working | 2 |  | 20 | 1 |  | Standalone |  | 0.75 | 208.1 | 2539.8
2030-04-09 16:06 | 2030-04-09 17:06 | 1 | Transit to next foundation | OFFSHORE | Working | 2 | 3 | 21 | 1 |  | Standalone |  | 1.5 | 209.1 | 2538.8
2030-04-09 17:06 | 2030-04-09 18:06 | 1 | Positioning at WTG location | OFFSHORE | Working | 2 | 3 | 22 | 1 |  | Standalone |  | 1.5 | 210.1 | 2537.8
2030-04-09 18:06 | 2030-04-09 22:06 | 4 | Preload and jacking up at site | OFFSHORE | Working | 2 | 3 | 23 | 1 |  | Standalone |  | 6 | 214.1 | 2533.8
2030-04-09 22:06 | 2030-04-10 01:06 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 2 | 3 | 24 | 1 |  | Standalone |  | 3 | 217.1 | 2530.8
2030-04-10 01:06 | 2030-04-10 02:36 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 2 | 3 | 25 | 1.5 |  | Standalone |  | 1 | 218.6 | 2529.3
2030-04-10 02:36 | 2030-04-10 05:36 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 2 | 3 | 26 | 1.5 |  | Standalone |  | 2 | 221.6 | 2526.3
2030-04-10 05:36 | 2030-04-10 07:06 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 2 | 3 | 27 | 1.5 | G1 | Start | MOST_STRINGENT | 1.5 | 223.1 | 2524.8
2030-04-10 07:06 | 2030-04-10 12:21 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 3 | 28 | 1.5 | G1 | Continue | MOST_STRINGENT | 5.25 | 228.35 | 2519.55
2030-04-10 12:21 | 2030-04-10 13:06 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 2 | 3 | 29 | 1.5 | G1 | End | MOST_STRINGENT | 0.75 | 229.1 | 2518.8
2030-04-10 13:06 | 2030-04-10 13:51 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working | 2 | 3 | 30 | 1.5 | G2 | Start | MOST_STRINGENT | 0.75 | 229.85 | 2518.05
2030-04-10 13:51 | 2030-04-10 17:13 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 3 | 31 | 1.5 | G2 | Continue | MOST_STRINGENT | 3.375 | 233.225 | 2514.675
2030-04-10 17:13 | 2030-04-10 17:58 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 2 | 3 | 32 | 1.5 | G2 | End | MOST_STRINGENT | 0.75 | 233.975 | 2513.925
2030-04-10 17:58 | 2030-04-10 18:43 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 2 | 3 | 33 | 1.5 | G3 | Start | MOST_STRINGENT | 0.75 | 234.725 | 2513.175
2030-04-10 18:43 | 2030-04-10 21:21 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 3 | 34 | 1.5 | G3 | Continue | MOST_STRINGENT | 2.625 | 237.35 | 2510.55
2030-04-10 21:21 | 2030-04-10 23:36 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 2 | 3 | 35 | 1.5 | G3 | End | MOST_STRINGENT | 2.25 | 239.6 | 2508.3
2030-04-10 23:36 | 2030-04-11 02:13 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 3 | 36 | 1.5 | G4 | Start | MOST_STRINGENT | 2.625 | 242.225 | 2505.675
2030-04-11 02:13 | 2030-04-11 04:28 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 2 | 3 | 37 | 1.5 | G4 | End | MOST_STRINGENT | 2.25 | 244.475 | 2503.425
2030-04-11 04:28 | 2030-04-11 07:06 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 3 | 38 | 1.5 | G5 | Start | MOST_STRINGENT | 2.625 | 247.1 | 2500.8
2030-04-11 07:06 | 2030-04-11 09:21 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 2 | 3 | 39 | 1.5 | G5 | End | MOST_STRINGENT | 2.25 | 249.35 | 2498.55
2030-04-11 09:21 | 2030-04-11 10:51 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working | 2 | 3 | 40 | 1.5 |  | Standalone |  | 1 | 250.85 | 2497.05
2030-04-11 10:51 | 2030-04-11 12:21 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 2 | 3 | 41 | 1.5 |  | Standalone |  | 1 | 252.35 | 2495.55
2030-04-11 12:21 | 2030-04-11 16:51 | 4.5 | Turbine general completion works | OFFSHORE | Working | 2 | 3 | 42 | 1.5 |  | Standalone |  | 3 | 256.85 | 2491.05
2030-04-11 16:51 | 2030-04-11 19:51 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 2 | 3 | 43 | 1 |  | Standalone |  | 3 | 259.85 | 2488.05
2030-04-11 19:51 | 2030-04-11 21:51 | 2 | Jacking down at site | OFFSHORE | Working | 2 | 3 | 44 | 1 |  | Standalone |  | 3 | 261.85 | 2486.05
2030-04-11 21:51 | 2030-04-11 22:51 | 1 | Transit to next foundation | OFFSHORE | Working | 2 | 4 | 21 | 1 |  | Standalone |  | 1.5 | 262.85 | 2485.05
2030-04-11 22:51 | 2030-04-11 23:51 | 1 | Positioning at WTG location | OFFSHORE | Working | 2 | 4 | 22 | 1 |  | Standalone |  | 1.5 | 263.85 | 2484.05
2030-04-11 23:51 | 2030-04-12 03:51 | 4 | Preload and jacking up at site | OFFSHORE | Working | 2 | 4 | 23 | 1 |  | Standalone |  | 6 | 267.85 | 2480.05
2030-04-12 03:51 | 2030-04-12 06:51 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 2 | 4 | 24 | 1 |  | Standalone |  | 3 | 270.85 | 2477.05
2030-04-12 06:51 | 2030-04-12 08:21 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 2 | 4 | 25 | 1.5 |  | Standalone |  | 1 | 272.35 | 2475.55
2030-04-12 08:21 | 2030-04-12 11:21 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 2 | 4 | 26 | 1.5 |  | Standalone |  | 2 | 275.35 | 2472.55
2030-04-12 11:21 | 2030-04-12 12:51 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 2 | 4 | 27 | 1.5 | G1 | Start | MOST_STRINGENT | 1.5 | 276.85 | 2471.05
2030-04-12 12:51 | 2030-04-12 18:06 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 4 | 28 | 1.5 | G1 | Continue | MOST_STRINGENT | 5.25 | 282.1 | 2465.8
2030-04-12 18:06 | 2030-04-12 18:51 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 2 | 4 | 29 | 1.5 | G1 | End | MOST_STRINGENT | 0.75 | 282.85 | 2465.05
2030-04-12 18:51 | 2030-04-12 19:36 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working | 2 | 4 | 30 | 1.5 | G2 | Start | MOST_STRINGENT | 0.75 | 283.6 | 2464.3
2030-04-12 19:36 | 2030-04-12 22:59 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 4 | 31 | 1.5 | G2 | Continue | MOST_STRINGENT | 3.375 | 286.975 | 2460.925
2030-04-12 22:59 | 2030-04-12 23:44 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 2 | 4 | 32 | 1.5 | G2 | End | MOST_STRINGENT | 0.75 | 287.725 | 2460.175
2030-04-12 23:44 | 2030-04-13 00:29 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 2 | 4 | 33 | 1.5 | G3 | Start | MOST_STRINGENT | 0.75 | 288.475 | 2459.425
2030-04-13 00:29 | 2030-04-13 03:06 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 4 | 34 | 1.5 | G3 | Continue | MOST_STRINGENT | 2.625 | 291.1 | 2456.8
2030-04-13 03:06 | 2030-04-13 05:21 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 2 | 4 | 35 | 1.5 | G3 | End | MOST_STRINGENT | 2.25 | 293.35 | 2454.55
2030-04-13 05:21 | 2030-04-13 07:59 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 4 | 36 | 1.5 | G4 | Start | MOST_STRINGENT | 2.625 | 295.975 | 2451.925
2030-04-13 07:59 | 2030-04-13 10:14 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 2 | 4 | 37 | 1.5 | G4 | End | MOST_STRINGENT | 2.25 | 298.225 | 2449.675
2030-04-13 10:14 | 2030-04-13 12:51 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 2 | 4 | 38 | 1.5 | G5 | Start | MOST_STRINGENT | 2.625 | 300.85 | 2447.05
2030-04-13 12:51 | 2030-04-13 15:06 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 2 | 4 | 39 | 1.5 | G5 | End | MOST_STRINGENT | 2.25 | 303.1 | 2444.8
2030-04-13 15:06 | 2030-04-13 16:36 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working | 2 | 4 | 40 | 1.5 |  | Standalone |  | 1 | 304.6 | 2443.3
2030-04-13 16:36 | 2030-04-13 18:06 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 2 | 4 | 41 | 1.5 |  | Standalone |  | 1 | 306.1 | 2441.8
2030-04-13 18:06 | 2030-04-13 22:36 | 4.5 | Turbine general completion works | OFFSHORE | Working | 2 | 4 | 42 | 1.5 |  | Standalone |  | 3 | 310.6 | 2437.3
2030-04-13 22:36 | 2030-04-14 01:36 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 2 | 4 | 43 | 1 |  | Standalone |  | 3 | 313.6 | 2434.3
2030-04-14 01:36 | 2030-04-14 03:36 | 2 | Jacking down at site | OFFSHORE | Working | 2 | 4 | 44 | 1 |  | Standalone |  | 3 | 315.6 | 2432.3
2030-04-14 03:36 | 2030-04-14 08:48 | 5.2 | Transit from site to port | OFFSHORE | Working | 2 |  | 45 | 1 |  | Standalone |  | 7.8 | 320.8 | 2427.1
2030-04-14 08:48 | 2030-04-14 09:48 | 1 | Port maneuvering | OFFSHORE | Working | 3 |  | 1 | 1 |  | Standalone |  | 1.5 | 321.8 | 2426.1
2030-04-14 09:48 | 2030-04-14 11:48 | 2 | Preload and jacking up at port | OFFSHORE | Working | 3 |  | 2 | 1 |  | Standalone |  | 3 | 323.8 | 2424.1
2030-04-14 11:48 | 2030-04-14 14:48 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 3 |  | 3 | 1 |  | Standalone |  | 3 | 326.8 | 2421.1
2030-04-14 14:48 | 2030-04-14 16:18 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working | 3 |  | 4 | 1.5 |  | Standalone |  | 1 | 328.3 | 2419.6
2030-04-14 16:18 | 2030-04-14 19:40 | 3.375 | Loadout Nacelle #1 | OFFSHORE | Working | 3 |  | 5 | 1.5 |  | Standalone |  | 3.375 | 331.675 | 2416.225
2030-04-14 19:40 | 2030-04-14 23:03 | 3.375 | Loadout Tower #1 | OFFSHORE | Working | 3 |  | 6 | 1.5 |  | Standalone |  | 3.375 | 335.05 | 2412.85
2030-04-14 23:03 | 2030-04-15 01:18 | 2.25 | Loadout Blade 1 | OFFSHORE | Working | 3 |  | 7 | 1.5 |  | Standalone |  | 2.25 | 337.3 | 2410.6
2030-04-15 01:18 | 2030-04-15 03:33 | 2.25 | Loadout Blade 2 | OFFSHORE | Working | 3 |  | 8 | 1.5 |  | Standalone |  | 2.25 | 339.55 | 2408.35
2030-04-15 03:33 | 2030-04-15 05:48 | 2.25 | Loadout Blade 3 | OFFSHORE | Working | 3 |  | 9 | 1.5 |  | Standalone |  | 2.25 | 341.8 | 2406.1
2030-04-15 05:48 | 2030-04-15 07:18 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working | 3 |  | 10 | 1.5 |  | Standalone |  | 1 | 343.3 | 2404.6
2030-04-15 07:18 | 2030-04-15 10:40 | 3.375 | Loadout Nacelle #2 | OFFSHORE | Working | 3 |  | 11 | 1.5 |  | Standalone |  | 3.375 | 346.675 | 2401.225
2030-04-15 10:40 | 2030-04-15 14:03 | 3.375 | Loadout Tower #2 | OFFSHORE | Working | 3 |  | 12 | 1.5 |  | Standalone |  | 3.375 | 350.05 | 2397.85
2030-04-15 14:03 | 2030-04-15 16:18 | 2.25 | Loadout Blade 1 | OFFSHORE | Working | 3 |  | 13 | 1.5 |  | Standalone |  | 2.25 | 352.3 | 2395.6
2030-04-15 16:18 | 2030-04-15 18:33 | 2.25 | Loadout Blade 2 | OFFSHORE | Working | 3 |  | 14 | 1.5 |  | Standalone |  | 2.25 | 354.55 | 2393.35
2030-04-15 18:33 | 2030-04-15 20:48 | 2.25 | Loadout Blade 3 | OFFSHORE | Working | 3 |  | 15 | 1.5 |  | Standalone |  | 2.25 | 356.8 | 2391.1
2030-04-15 20:48 | 2030-04-15 23:48 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 3 |  | 16 | 1 |  | Standalone |  | 3 | 359.8 | 2388.1
2030-04-15 23:48 | 2030-04-16 01:48 | 2 | Jacking down at port | OFFSHORE | Working | 3 |  | 17 | 1 |  | Standalone |  | 3 | 361.8 | 2386.1
2030-04-16 01:48 | 2030-04-16 02:48 | 1 | Port maneuvering | OFFSHORE | Working | 3 |  | 18 | 1 |  | Standalone |  | 1.5 | 362.8 | 2385.1
2030-04-16 02:48 | 2030-04-16 08:00 | 5.2 | Transit from port to site | OFFSHORE | Working | 3 |  | 19 | 1 |  | Standalone |  | 7.8 | 368 | 2379.9
2030-04-16 08:00 | 2030-04-16 08:30 | 0.5 | DP field check | OFFSHORE | Working | 3 |  | 20 | 1 |  | Standalone |  | 0.75 | 368.5 | 2379.4
2030-04-16 08:30 | 2030-04-16 09:30 | 1 | Transit to next foundation | OFFSHORE | Working | 3 | 5 | 21 | 1 |  | Standalone |  | 1.5 | 369.5 | 2378.4
2030-04-16 09:30 | 2030-04-16 10:30 | 1 | Positioning at WTG location | OFFSHORE | Working | 3 | 5 | 22 | 1 |  | Standalone |  | 1.5 | 370.5 | 2377.4
2030-04-16 10:30 | 2030-04-16 14:30 | 4 | Preload and jacking up at site | OFFSHORE | Working | 3 | 5 | 23 | 1 |  | Standalone |  | 6 | 374.5 | 2373.4
2030-04-16 14:30 | 2030-04-16 17:30 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 3 | 5 | 24 | 1 |  | Standalone |  | 3 | 377.5 | 2370.4
2030-04-16 17:30 | 2030-04-16 19:00 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 3 | 5 | 25 | 1.5 |  | Standalone |  | 1 | 379 | 2368.9
2030-04-16 19:00 | 2030-04-16 22:00 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 3 | 5 | 26 | 1.5 |  | Standalone |  | 2 | 382 | 2365.9
2030-04-16 22:00 | 2030-04-16 23:30 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 3 | 5 | 27 | 1.5 | G1 | Start | MOST_STRINGENT | 1.5 | 383.5 | 2364.4
2030-04-16 23:30 | 2030-04-17 04:45 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 5 | 28 | 1.5 | G1 | Continue | MOST_STRINGENT | 5.25 | 388.75 | 2359.15
2030-04-17 04:45 | 2030-04-17 05:30 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 3 | 5 | 29 | 1.5 | G1 | End | MOST_STRINGENT | 0.75 | 389.5 | 2358.4
2030-04-17 05:30 | 2030-04-17 06:15 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working | 3 | 5 | 30 | 1.5 | G2 | Start | MOST_STRINGENT | 0.75 | 390.25 | 2357.65
2030-04-17 06:15 | 2030-04-17 09:37 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 5 | 31 | 1.5 | G2 | Continue | MOST_STRINGENT | 3.375 | 393.625 | 2354.275
2030-04-17 09:37 | 2030-04-17 10:22 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 3 | 5 | 32 | 1.5 | G2 | End | MOST_STRINGENT | 0.75 | 394.375 | 2353.525
2030-04-17 10:22 | 2030-04-17 11:07 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 3 | 5 | 33 | 1.5 | G3 | Start | MOST_STRINGENT | 0.75 | 395.125 | 2352.775
2030-04-17 11:07 | 2030-04-17 13:45 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 5 | 34 | 1.5 | G3 | Continue | MOST_STRINGENT | 2.625 | 397.75 | 2350.15
2030-04-17 13:45 | 2030-04-17 16:00 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 3 | 5 | 35 | 1.5 | G3 | End | MOST_STRINGENT | 2.25 | 400 | 2347.9
2030-04-17 16:00 | 2030-04-17 18:37 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 5 | 36 | 1.5 | G4 | Start | MOST_STRINGENT | 2.625 | 402.625 | 2345.275
2030-04-17 18:37 | 2030-04-17 20:52 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 3 | 5 | 37 | 1.5 | G4 | End | MOST_STRINGENT | 2.25 | 404.875 | 2343.025
2030-04-17 20:52 | 2030-04-17 23:30 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 5 | 38 | 1.5 | G5 | Start | MOST_STRINGENT | 2.625 | 407.5 | 2340.4
2030-04-17 23:30 | 2030-04-18 01:45 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 3 | 5 | 39 | 1.5 | G5 | End | MOST_STRINGENT | 2.25 | 409.75 | 2338.15
2030-04-18 01:45 | 2030-04-18 03:15 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working | 3 | 5 | 40 | 1.5 |  | Standalone |  | 1 | 411.25 | 2336.65
2030-04-18 03:15 | 2030-04-18 04:45 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 3 | 5 | 41 | 1.5 |  | Standalone |  | 1 | 412.75 | 2335.15
2030-04-18 04:45 | 2030-04-18 09:15 | 4.5 | Turbine general completion works | OFFSHORE | Working | 3 | 5 | 42 | 1.5 |  | Standalone |  | 3 | 417.25 | 2330.65
2030-04-18 09:15 | 2030-04-18 12:15 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 3 | 5 | 43 | 1 |  | Standalone |  | 3 | 420.25 | 2327.65
2030-04-18 12:15 | 2030-04-18 14:15 | 2 | Jacking down at site | OFFSHORE | Working | 3 | 5 | 44 | 1 |  | Standalone |  | 3 | 422.25 | 2325.65
2030-04-18 14:15 | 2030-04-18 15:15 | 1 | Transit to next foundation | OFFSHORE | Working | 3 | 6 | 21 | 1 |  | Standalone |  | 1.5 | 423.25 | 2324.65
2030-04-18 15:15 | 2030-04-18 16:15 | 1 | Positioning at WTG location | OFFSHORE | Working | 3 | 6 | 22 | 1 |  | Standalone |  | 1.5 | 424.25 | 2323.65
2030-04-18 16:15 | 2030-04-18 20:15 | 4 | Preload and jacking up at site | OFFSHORE | Working | 3 | 6 | 23 | 1 |  | Standalone |  | 6 | 428.25 | 2319.65
2030-04-18 20:15 | 2030-04-18 23:15 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 3 | 6 | 24 | 1 |  | Standalone |  | 3 | 431.25 | 2316.65
2030-04-18 23:15 | 2030-04-19 00:45 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 3 | 6 | 25 | 1.5 |  | Standalone |  | 1 | 432.75 | 2315.15
2030-04-19 00:45 | 2030-04-19 03:45 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 3 | 6 | 26 | 1.5 |  | Standalone |  | 2 | 435.75 | 2312.15
2030-04-19 03:45 | 2030-04-19 05:15 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 3 | 6 | 27 | 1.5 | G1 | Start | MOST_STRINGENT | 1.5 | 437.25 | 2310.65
2030-04-19 05:15 | 2030-04-19 10:30 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 6 | 28 | 1.5 | G1 | Continue | MOST_STRINGENT | 5.25 | 442.5 | 2305.4
2030-04-19 10:30 | 2030-04-19 11:15 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 3 | 6 | 29 | 1.5 | G1 | End | MOST_STRINGENT | 0.75 | 443.25 | 2304.65
2030-04-19 11:15 | 2030-04-19 12:00 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working | 3 | 6 | 30 | 1.5 | G2 | Start | MOST_STRINGENT | 0.75 | 444 | 2303.9
2030-04-19 12:00 | 2030-04-19 15:22 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 6 | 31 | 1.5 | G2 | Continue | MOST_STRINGENT | 3.375 | 447.375 | 2300.525
2030-04-19 15:22 | 2030-04-19 16:08 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 3 | 6 | 32 | 1.5 | G2 | End | MOST_STRINGENT | 0.75 | 448.125 | 2299.775
2030-04-19 16:08 | 2030-04-19 16:52 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 3 | 6 | 33 | 1.5 | G3 | Start | MOST_STRINGENT | 0.75 | 448.875 | 2299.025
2030-04-19 16:52 | 2030-04-19 19:30 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 6 | 34 | 1.5 | G3 | Continue | MOST_STRINGENT | 2.625 | 451.5 | 2296.4
2030-04-19 19:30 | 2030-04-19 21:45 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 3 | 6 | 35 | 1.5 | G3 | End | MOST_STRINGENT | 2.25 | 453.75 | 2294.15
2030-04-19 21:45 | 2030-04-20 00:22 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 6 | 36 | 1.5 | G4 | Start | MOST_STRINGENT | 2.625 | 456.375 | 2291.525
2030-04-20 00:22 | 2030-04-20 02:38 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 3 | 6 | 37 | 1.5 | G4 | End | MOST_STRINGENT | 2.25 | 458.625 | 2289.275
2030-04-20 02:38 | 2030-04-20 05:15 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 3 | 6 | 38 | 1.5 | G5 | Start | MOST_STRINGENT | 2.625 | 461.25 | 2286.65
2030-04-20 05:15 | 2030-04-20 07:30 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 3 | 6 | 39 | 1.5 | G5 | End | MOST_STRINGENT | 2.25 | 463.5 | 2284.4
2030-04-20 07:30 | 2030-04-20 09:00 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working | 3 | 6 | 40 | 1.5 |  | Standalone |  | 1 | 465 | 2282.9
2030-04-20 09:00 | 2030-04-20 10:30 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 3 | 6 | 41 | 1.5 |  | Standalone |  | 1 | 466.5 | 2281.4
2030-04-20 10:30 | 2030-04-20 15:00 | 4.5 | Turbine general completion works | OFFSHORE | Working | 3 | 6 | 42 | 1.5 |  | Standalone |  | 3 | 471 | 2276.9
2030-04-20 15:00 | 2030-04-20 18:00 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 3 | 6 | 43 | 1 |  | Standalone |  | 3 | 474 | 2273.9
2030-04-20 18:00 | 2030-04-20 20:00 | 2 | Jacking down at site | OFFSHORE | Working | 3 | 6 | 44 | 1 |  | Standalone |  | 3 | 476 | 2271.9
2030-04-20 20:00 | 2030-04-21 01:12 | 5.2 | Transit from site to port | OFFSHORE | Working | 3 |  | 45 | 1 |  | Standalone |  | 7.8 | 481.2 | 2266.7
2030-04-21 01:12 | 2030-04-21 02:12 | 1 | Port maneuvering | OFFSHORE | Working | 4 |  | 1 | 1 |  | Standalone |  | 1.5 | 482.2 | 2265.7
2030-04-21 02:12 | 2030-04-21 04:12 | 2 | Preload and jacking up at port | OFFSHORE | Working | 4 |  | 2 | 1 |  | Standalone |  | 3 | 484.2 | 2263.7
2030-04-21 04:12 | 2030-04-21 07:12 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 4 |  | 3 | 1 |  | Standalone |  | 3 | 487.2 | 2260.7
2030-04-21 07:12 | 2030-04-21 08:42 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working | 4 |  | 4 | 1.5 |  | Standalone |  | 1 | 488.7 | 2259.2
2030-04-21 08:42 | 2030-04-21 12:05 | 3.375 | Loadout Nacelle #1 | OFFSHORE | Working | 4 |  | 5 | 1.5 |  | Standalone |  | 3.375 | 492.075 | 2255.825
2030-04-21 12:05 | 2030-04-21 15:27 | 3.375 | Loadout Tower #1 | OFFSHORE | Working | 4 |  | 6 | 1.5 |  | Standalone |  | 3.375 | 495.45 | 2252.45
2030-04-21 15:27 | 2030-04-21 17:42 | 2.25 | Loadout Blade 1 | OFFSHORE | Working | 4 |  | 7 | 1.5 |  | Standalone |  | 2.25 | 497.7 | 2250.2
2030-04-21 17:42 | 2030-04-21 19:57 | 2.25 | Loadout Blade 2 | OFFSHORE | Working | 4 |  | 8 | 1.5 |  | Standalone |  | 2.25 | 499.95 | 2247.95
2030-04-21 19:57 | 2030-04-21 22:12 | 2.25 | Loadout Blade 3 | OFFSHORE | Working | 4 |  | 9 | 1.5 |  | Standalone |  | 2.25 | 502.2 | 2245.7
2030-04-21 22:12 | 2030-04-21 23:42 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working | 4 |  | 10 | 1.5 |  | Standalone |  | 1 | 503.7 | 2244.2
2030-04-21 23:42 | 2030-04-22 03:05 | 3.375 | Loadout Nacelle #2 | OFFSHORE | Working | 4 |  | 11 | 1.5 |  | Standalone |  | 3.375 | 507.075 | 2240.825
2030-04-22 03:05 | 2030-04-22 06:27 | 3.375 | Loadout Tower #2 | OFFSHORE | Working | 4 |  | 12 | 1.5 |  | Standalone |  | 3.375 | 510.45 | 2237.45
2030-04-22 06:27 | 2030-04-22 08:42 | 2.25 | Loadout Blade 1 | OFFSHORE | Working | 4 |  | 13 | 1.5 |  | Standalone |  | 2.25 | 512.7 | 2235.2
2030-04-22 08:42 | 2030-04-22 10:57 | 2.25 | Loadout Blade 2 | OFFSHORE | Working | 4 |  | 14 | 1.5 |  | Standalone |  | 2.25 | 514.95 | 2232.95
2030-04-22 10:57 | 2030-04-22 13:12 | 2.25 | Loadout Blade 3 | OFFSHORE | Working | 4 |  | 15 | 1.5 |  | Standalone |  | 2.25 | 517.2 | 2230.7
2030-04-22 13:12 | 2030-04-22 16:12 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 4 |  | 16 | 1 |  | Standalone |  | 3 | 520.2 | 2227.7
2030-04-22 16:12 | 2030-04-22 18:12 | 2 | Jacking down at port | OFFSHORE | Working | 4 |  | 17 | 1 |  | Standalone |  | 3 | 522.2 | 2225.7
2030-04-22 18:12 | 2030-04-22 19:12 | 1 | Port maneuvering | OFFSHORE | Working | 4 |  | 18 | 1 |  | Standalone |  | 1.5 | 523.2 | 2224.7
2030-04-22 19:12 | 2030-04-23 00:24 | 5.2 | Transit from port to site | OFFSHORE | Working | 4 |  | 19 | 1 |  | Standalone |  | 7.8 | 528.4 | 2219.5
2030-04-23 00:24 | 2030-04-23 00:54 | 0.5 | DP field check | OFFSHORE | Working | 4 |  | 20 | 1 |  | Standalone |  | 0.75 | 528.9 | 2219
2030-04-23 00:54 | 2030-04-23 01:54 | 1 | Transit to next foundation | OFFSHORE | Working | 4 | 7 | 21 | 1 |  | Standalone |  | 1.5 | 529.9 | 2218
2030-04-23 01:54 | 2030-04-23 02:54 | 1 | Positioning at WTG location | OFFSHORE | Working | 4 | 7 | 22 | 1 |  | Standalone |  | 1.5 | 530.9 | 2217
2030-04-23 02:54 | 2030-04-23 06:54 | 4 | Preload and jacking up at site | OFFSHORE | Working | 4 | 7 | 23 | 1 |  | Standalone |  | 6 | 534.9 | 2213
2030-04-23 06:54 | 2030-04-23 09:54 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 4 | 7 | 24 | 1 |  | Standalone |  | 3 | 537.9 | 2210
2030-04-23 09:54 | 2030-04-23 11:24 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 4 | 7 | 25 | 1.5 |  | Standalone |  | 1 | 539.4 | 2208.5
2030-04-23 11:24 | 2030-04-23 14:24 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 4 | 7 | 26 | 1.5 |  | Standalone |  | 2 | 542.4 | 2205.5
2030-04-23 14:24 | 2030-04-23 15:54 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 4 | 7 | 27 | 1.5 | G1 | Start | MOST_STRINGENT | 1.5 | 543.9 | 2204
2030-04-23 15:54 | 2030-04-23 21:09 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 7 | 28 | 1.5 | G1 | Continue | MOST_STRINGENT | 5.25 | 549.15 | 2198.75
2030-04-23 21:09 | 2030-04-23 21:54 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 4 | 7 | 29 | 1.5 | G1 | End | MOST_STRINGENT | 0.75 | 549.9 | 2198
2030-04-23 21:54 | 2030-04-23 22:39 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working | 4 | 7 | 30 | 1.5 | G2 | Start | MOST_STRINGENT | 0.75 | 550.65 | 2197.25
2030-04-23 22:39 | 2030-04-24 02:02 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 7 | 31 | 1.5 | G2 | Continue | MOST_STRINGENT | 3.375 | 554.025 | 2193.875
2030-04-24 02:02 | 2030-04-24 02:46 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 4 | 7 | 32 | 1.5 | G2 | End | MOST_STRINGENT | 0.75 | 554.775 | 2193.125
2030-04-24 02:46 | 2030-04-24 03:32 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 4 | 7 | 33 | 1.5 | G3 | Start | MOST_STRINGENT | 0.75 | 555.525 | 2192.375
2030-04-24 03:32 | 2030-04-24 06:09 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 7 | 34 | 1.5 | G3 | Continue | MOST_STRINGENT | 2.625 | 558.15 | 2189.75
2030-04-24 06:09 | 2030-04-24 08:24 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 4 | 7 | 35 | 1.5 | G3 | End | MOST_STRINGENT | 2.25 | 560.4 | 2187.5
2030-04-24 08:24 | 2030-04-24 11:02 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 7 | 36 | 1.5 | G4 | Start | MOST_STRINGENT | 2.625 | 563.025 | 2184.875
2030-04-24 11:02 | 2030-04-24 13:16 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 4 | 7 | 37 | 1.5 | G4 | End | MOST_STRINGENT | 2.25 | 565.275 | 2182.625
2030-04-24 13:16 | 2030-04-24 15:54 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 7 | 38 | 1.5 | G5 | Start | MOST_STRINGENT | 2.625 | 567.9 | 2180
2030-04-24 15:54 | 2030-04-24 18:09 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 4 | 7 | 39 | 1.5 | G5 | End | MOST_STRINGENT | 2.25 | 570.15 | 2177.75
2030-04-24 18:09 | 2030-04-24 19:39 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working | 4 | 7 | 40 | 1.5 |  | Standalone |  | 1 | 571.65 | 2176.25
2030-04-24 19:39 | 2030-04-24 21:09 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 4 | 7 | 41 | 1.5 |  | Standalone |  | 1 | 573.15 | 2174.75
2030-04-24 21:09 | 2030-04-25 01:39 | 4.5 | Turbine general completion works | OFFSHORE | Working | 4 | 7 | 42 | 1.5 |  | Standalone |  | 3 | 577.65 | 2170.25
2030-04-25 01:39 | 2030-04-25 04:39 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 4 | 7 | 43 | 1 |  | Standalone |  | 3 | 580.65 | 2167.25
2030-04-25 04:39 | 2030-04-25 06:39 | 2 | Jacking down at site | OFFSHORE | Working | 4 | 7 | 44 | 1 |  | Standalone |  | 3 | 582.65 | 2165.25
2030-04-25 06:39 | 2030-04-25 07:39 | 1 | Transit to next foundation | OFFSHORE | Working | 4 | 8 | 21 | 1 |  | Standalone |  | 1.5 | 583.65 | 2164.25
2030-04-25 07:39 | 2030-04-25 08:39 | 1 | Positioning at WTG location | OFFSHORE | Working | 4 | 8 | 22 | 1 |  | Standalone |  | 1.5 | 584.65 | 2163.25
2030-04-25 08:39 | 2030-04-25 12:39 | 4 | Preload and jacking up at site | OFFSHORE | Working | 4 | 8 | 23 | 1 |  | Standalone |  | 6 | 588.65 | 2159.25
2030-04-25 12:39 | 2030-04-25 15:39 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 4 | 8 | 24 | 1 |  | Standalone |  | 3 | 591.65 | 2156.25
2030-04-25 15:39 | 2030-04-25 17:09 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 4 | 8 | 25 | 1.5 |  | Standalone |  | 1 | 593.15 | 2154.75
2030-04-25 17:09 | 2030-04-25 20:09 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 4 | 8 | 26 | 1.5 |  | Standalone |  | 2 | 596.15 | 2151.75
2030-04-25 20:09 | 2030-04-25 21:39 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 4 | 8 | 27 | 1.5 | G1 | Start | MOST_STRINGENT | 1.5 | 597.65 | 2150.25
2030-04-25 21:39 | 2030-04-26 02:54 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 8 | 28 | 1.5 | G1 | Continue | MOST_STRINGENT | 5.25 | 602.9 | 2145
2030-04-26 02:54 | 2030-04-26 03:39 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 4 | 8 | 29 | 1.5 | G1 | End | MOST_STRINGENT | 0.75 | 603.65 | 2144.25
2030-04-26 03:39 | 2030-04-26 04:24 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working | 4 | 8 | 30 | 1.5 | G2 | Start | MOST_STRINGENT | 0.75 | 604.4 | 2143.5
2030-04-26 04:24 | 2030-04-26 07:46 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 8 | 31 | 1.5 | G2 | Continue | MOST_STRINGENT | 3.375 | 607.775 | 2140.125
2030-04-26 07:46 | 2030-04-26 08:31 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 4 | 8 | 32 | 1.5 | G2 | End | MOST_STRINGENT | 0.75 | 608.525 | 2139.375
2030-04-26 08:31 | 2030-04-26 09:16 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 4 | 8 | 33 | 1.5 | G3 | Start | MOST_STRINGENT | 0.75 | 609.275 | 2138.625
2030-04-26 09:16 | 2030-04-26 11:54 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 8 | 34 | 1.5 | G3 | Continue | MOST_STRINGENT | 2.625 | 611.9 | 2136
2030-04-26 11:54 | 2030-04-26 14:09 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 4 | 8 | 35 | 1.5 | G3 | End | MOST_STRINGENT | 2.25 | 614.15 | 2133.75
2030-04-26 14:09 | 2030-04-26 16:46 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 8 | 36 | 1.5 | G4 | Start | MOST_STRINGENT | 2.625 | 616.775 | 2131.125
2030-04-26 16:46 | 2030-04-26 19:01 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 4 | 8 | 37 | 1.5 | G4 | End | MOST_STRINGENT | 2.25 | 619.025 | 2128.875
2030-04-26 19:01 | 2030-04-26 21:39 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 4 | 8 | 38 | 1.5 | G5 | Start | MOST_STRINGENT | 2.625 | 621.65 | 2126.25
2030-04-26 21:39 | 2030-04-26 23:54 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 4 | 8 | 39 | 1.5 | G5 | End | MOST_STRINGENT | 2.25 | 623.9 | 2124
2030-04-26 23:54 | 2030-04-27 01:24 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working | 4 | 8 | 40 | 1.5 |  | Standalone |  | 1 | 625.4 | 2122.5
2030-04-27 01:24 | 2030-04-27 02:54 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 4 | 8 | 41 | 1.5 |  | Standalone |  | 1 | 626.9 | 2121
2030-04-27 02:54 | 2030-04-27 07:24 | 4.5 | Turbine general completion works | OFFSHORE | Working | 4 | 8 | 42 | 1.5 |  | Standalone |  | 3 | 631.4 | 2116.5
2030-04-27 07:24 | 2030-04-27 10:24 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 4 | 8 | 43 | 1 |  | Standalone |  | 3 | 634.4 | 2113.5
2030-04-27 10:24 | 2030-04-27 12:24 | 2 | Jacking down at site | OFFSHORE | Working | 4 | 8 | 44 | 1 |  | Standalone |  | 3 | 636.4 | 2111.5
2030-04-27 12:24 | 2030-04-27 17:36 | 5.2 | Transit from site to port | OFFSHORE | Working | 4 |  | 45 | 1 |  | Standalone |  | 7.8 | 641.6 | 2106.3
2030-04-27 17:36 | 2030-04-27 18:36 | 1 | Port maneuvering | OFFSHORE | Working | 5 |  | 1 | 1 |  | Standalone |  | 1.5 | 642.6 | 2105.3
2030-04-27 18:36 | 2030-04-27 20:36 | 2 | Preload and jacking up at port | OFFSHORE | Working | 5 |  | 2 | 1 |  | Standalone |  | 3 | 644.6 | 2103.3
2030-04-27 20:36 | 2030-04-27 23:36 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 5 |  | 3 | 1 |  | Standalone |  | 3 | 647.6 | 2100.3
2030-04-27 23:36 | 2030-04-28 00:36 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 5 |  | 4 | 1 |  | Standalone |  | 1 | 648.6 | 2099.3
2030-04-28 00:36 | 2030-04-28 02:51 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 5 |  | 5 | 1 |  | Standalone |  | 3.375 | 650.85 | 2097.05
2030-04-28 02:51 | 2030-04-28 05:06 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 5 |  | 6 | 1 |  | Standalone |  | 3.375 | 653.1 | 2094.8
2030-04-28 05:06 | 2030-04-28 06:36 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 5 |  | 7 | 1 |  | Standalone |  | 2.25 | 654.6 | 2093.3
2030-04-28 06:36 | 2030-04-28 08:06 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 5 |  | 8 | 1 |  | Standalone |  | 2.25 | 656.1 | 2091.8
2030-04-28 08:06 | 2030-04-28 09:36 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 5 |  | 9 | 1 |  | Standalone |  | 2.25 | 657.6 | 2090.3
2030-04-28 09:36 | 2030-04-28 10:36 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 5 |  | 10 | 1 |  | Standalone |  | 1 | 658.6 | 2089.3
2030-04-28 10:36 | 2030-04-28 12:51 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 5 |  | 11 | 1 |  | Standalone |  | 3.375 | 660.85 | 2087.05
2030-04-28 12:51 | 2030-04-28 15:06 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 5 |  | 12 | 1 |  | Standalone |  | 3.375 | 663.1 | 2084.8
2030-04-28 15:06 | 2030-04-28 16:36 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 5 |  | 13 | 1 |  | Standalone |  | 2.25 | 664.6 | 2083.3
2030-04-28 16:36 | 2030-04-28 18:06 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 5 |  | 14 | 1 |  | Standalone |  | 2.25 | 666.1 | 2081.8
2030-04-28 18:06 | 2030-04-28 19:36 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 5 |  | 15 | 1 |  | Standalone |  | 2.25 | 667.6 | 2080.3
2030-04-28 19:36 | 2030-04-28 22:36 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 5 |  | 16 | 1 |  | Standalone |  | 3 | 670.6 | 2077.3
2030-04-28 22:36 | 2030-04-29 00:36 | 2 | Jacking down at port | OFFSHORE | Working | 5 |  | 17 | 1 |  | Standalone |  | 3 | 672.6 | 2075.3
2030-04-29 00:36 | 2030-04-29 01:36 | 1 | Port maneuvering | OFFSHORE | Working | 5 |  | 18 | 1 |  | Standalone |  | 1.5 | 673.6 | 2074.3
2030-04-29 01:36 | 2030-04-29 06:48 | 5.2 | Transit from port to site | OFFSHORE | Working | 5 |  | 19 | 1 |  | Standalone |  | 7.8 | 678.8 | 2069.1
2030-04-29 06:48 | 2030-04-29 07:18 | 0.5 | DP field check | OFFSHORE | Working | 5 |  | 20 | 1 |  | Standalone |  | 0.75 | 679.3 | 2068.6
2030-04-29 07:18 | 2030-04-29 08:18 | 1 | Transit to next foundation | OFFSHORE | Working | 5 | 9 | 21 | 1 |  | Standalone |  | 1.5 | 680.3 | 2067.6
2030-04-29 08:18 | 2030-04-29 09:18 | 1 | Positioning at WTG location | OFFSHORE | Working | 5 | 9 | 22 | 1 |  | Standalone |  | 1.5 | 681.3 | 2066.6
2030-04-29 09:18 | 2030-04-29 13:18 | 4 | Preload and jacking up at site | OFFSHORE | Working | 5 | 9 | 23 | 1 |  | Standalone |  | 6 | 685.3 | 2062.6
2030-04-29 13:18 | 2030-04-29 16:18 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 5 | 9 | 24 | 1 |  | Standalone |  | 3 | 688.3 | 2059.6
2030-04-29 16:18 | 2030-04-29 17:18 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 5 | 9 | 25 | 1 |  | Standalone |  | 1 | 689.3 | 2058.6
2030-04-29 17:18 | 2030-04-29 19:18 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 5 | 9 | 26 | 1 |  | Standalone |  | 2 | 691.3 | 2056.6
2030-04-29 19:18 | 2030-04-29 20:18 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 5 | 9 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 692.3 | 2055.6
2030-04-29 20:18 | 2030-04-29 23:48 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 9 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 695.8 | 2052.1
2030-04-29 23:48 | 2030-04-30 00:18 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 5 | 9 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 696.3 | 2051.6
2030-04-30 00:18 | 2030-04-30 00:48 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 5 | 9 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 696.8 | 2051.1
2030-04-30 00:48 | 2030-04-30 03:03 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 9 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 699.05 | 2048.85
2030-04-30 03:03 | 2030-04-30 03:33 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 5 | 9 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 699.55 | 2048.35
2030-04-30 03:33 | 2030-04-30 04:03 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 5 | 9 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 700.05 | 2047.85
2030-04-30 04:03 | 2030-04-30 05:48 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 9 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 701.8 | 2046.1
2030-04-30 05:48 | 2030-04-30 07:18 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 5 | 9 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 703.3 | 2044.6
2030-04-30 07:18 | 2030-04-30 09:03 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 9 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 705.05 | 2042.85
2030-04-30 09:03 | 2030-04-30 10:33 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 5 | 9 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 706.55 | 2041.35
2030-04-30 10:33 | 2030-04-30 12:18 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 9 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 708.3 | 2039.6
2030-04-30 12:18 | 2030-04-30 13:48 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 5 | 9 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 709.8 | 2038.1
2030-04-30 13:48 | 2030-04-30 14:48 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 5 | 9 | 40 | 1 |  | Standalone |  | 1 | 710.8 | 2037.1
2030-04-30 14:48 | 2030-04-30 15:48 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 5 | 9 | 41 | 1 |  | Standalone |  | 1 | 711.8 | 2036.1
2030-04-30 15:48 | 2030-04-30 18:48 | 3 | Turbine general completion works | OFFSHORE | Working | 5 | 9 | 42 | 1 |  | Standalone |  | 3 | 714.8 | 2033.1
2030-04-30 18:48 | 2030-04-30 21:48 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 5 | 9 | 43 | 1 |  | Standalone |  | 3 | 717.8 | 2030.1
2030-04-30 21:48 | 2030-04-30 23:48 | 2 | Jacking down at site | OFFSHORE | Working | 5 | 9 | 44 | 1 |  | Standalone |  | 3 | 719.8 | 2028.1
2030-04-30 23:48 | 2030-05-01 00:48 | 1 | Transit to next foundation | OFFSHORE | Working | 5 | 10 | 21 | 1 |  | Standalone |  | 1.5 | 720.8 | 2027.1
2030-05-01 00:48 | 2030-05-01 01:48 | 1 | Positioning at WTG location | OFFSHORE | Working | 5 | 10 | 22 | 1 |  | Standalone |  | 1.5 | 721.8 | 2026.1
2030-05-01 01:48 | 2030-05-01 05:48 | 4 | Preload and jacking up at site | OFFSHORE | Working | 5 | 10 | 23 | 1 |  | Standalone |  | 6 | 725.8 | 2022.1
2030-05-01 05:48 | 2030-05-01 08:48 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 5 | 10 | 24 | 1 |  | Standalone |  | 3 | 728.8 | 2019.1
2030-05-01 08:48 | 2030-05-01 09:48 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 5 | 10 | 25 | 1 |  | Standalone |  | 1 | 729.8 | 2018.1
2030-05-01 09:48 | 2030-05-01 11:48 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 5 | 10 | 26 | 1 |  | Standalone |  | 2 | 731.8 | 2016.1
2030-05-01 11:48 | 2030-05-01 12:48 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 5 | 10 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 732.8 | 2015.1
2030-05-01 12:48 | 2030-05-01 16:18 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 10 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 736.3 | 2011.6
2030-05-01 16:18 | 2030-05-01 16:48 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 5 | 10 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 736.8 | 2011.1
2030-05-01 16:48 | 2030-05-01 17:18 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 5 | 10 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 737.3 | 2010.6
2030-05-01 17:18 | 2030-05-01 19:33 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 10 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 739.55 | 2008.35
2030-05-01 19:33 | 2030-05-01 20:03 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 5 | 10 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 740.05 | 2007.85
2030-05-01 20:03 | 2030-05-01 20:33 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 5 | 10 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 740.55 | 2007.35
2030-05-01 20:33 | 2030-05-01 22:18 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 10 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 742.3 | 2005.6
2030-05-01 22:18 | 2030-05-01 23:48 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 5 | 10 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 743.8 | 2004.1
2030-05-01 23:48 | 2030-05-02 01:33 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 10 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 745.55 | 2002.35
2030-05-02 01:33 | 2030-05-02 03:03 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 5 | 10 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 747.05 | 2000.85
2030-05-02 03:03 | 2030-05-02 04:48 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 5 | 10 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 748.8 | 1999.1
2030-05-02 04:48 | 2030-05-02 06:18 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 5 | 10 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 750.3 | 1997.6
2030-05-02 06:18 | 2030-05-02 07:18 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 5 | 10 | 40 | 1 |  | Standalone |  | 1 | 751.3 | 1996.6
2030-05-02 07:18 | 2030-05-02 08:18 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 5 | 10 | 41 | 1 |  | Standalone |  | 1 | 752.3 | 1995.6
2030-05-02 08:18 | 2030-05-02 11:18 | 3 | Turbine general completion works | OFFSHORE | Working | 5 | 10 | 42 | 1 |  | Standalone |  | 3 | 755.3 | 1992.6
2030-05-02 11:18 | 2030-05-02 14:18 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 5 | 10 | 43 | 1 |  | Standalone |  | 3 | 758.3 | 1989.6
2030-05-02 14:18 | 2030-05-02 16:18 | 2 | Jacking down at site | OFFSHORE | Working | 5 | 10 | 44 | 1 |  | Standalone |  | 3 | 760.3 | 1987.6
2030-05-02 16:18 | 2030-05-02 21:30 | 5.2 | Transit from site to port | OFFSHORE | Working | 5 |  | 45 | 1 |  | Standalone |  | 7.8 | 765.5 | 1982.4
2030-05-02 21:30 | 2030-05-02 22:30 | 1 | Port maneuvering | OFFSHORE | Working | 6 |  | 1 | 1 |  | Standalone |  | 1.5 | 766.5 | 1981.4
2030-05-02 22:30 | 2030-05-03 00:30 | 2 | Preload and jacking up at port | OFFSHORE | Working | 6 |  | 2 | 1 |  | Standalone |  | 3 | 768.5 | 1979.4
2030-05-03 00:30 | 2030-05-03 03:30 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 6 |  | 3 | 1 |  | Standalone |  | 3 | 771.5 | 1976.4
2030-05-03 03:30 | 2030-05-03 04:30 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 6 |  | 4 | 1 |  | Standalone |  | 1 | 772.5 | 1975.4
2030-05-03 04:30 | 2030-05-03 06:45 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 6 |  | 5 | 1 |  | Standalone |  | 3.375 | 774.75 | 1973.15
2030-05-03 06:45 | 2030-05-03 09:00 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 6 |  | 6 | 1 |  | Standalone |  | 3.375 | 777 | 1970.9
2030-05-03 09:00 | 2030-05-03 10:30 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 6 |  | 7 | 1 |  | Standalone |  | 2.25 | 778.5 | 1969.4
2030-05-03 10:30 | 2030-05-03 12:00 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 6 |  | 8 | 1 |  | Standalone |  | 2.25 | 780 | 1967.9
2030-05-03 12:00 | 2030-05-03 13:30 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 6 |  | 9 | 1 |  | Standalone |  | 2.25 | 781.5 | 1966.4
2030-05-03 13:30 | 2030-05-03 14:30 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 6 |  | 10 | 1 |  | Standalone |  | 1 | 782.5 | 1965.4
2030-05-03 14:30 | 2030-05-03 16:45 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 6 |  | 11 | 1 |  | Standalone |  | 3.375 | 784.75 | 1963.15
2030-05-03 16:45 | 2030-05-03 19:00 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 6 |  | 12 | 1 |  | Standalone |  | 3.375 | 787 | 1960.9
2030-05-03 19:00 | 2030-05-03 20:30 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 6 |  | 13 | 1 |  | Standalone |  | 2.25 | 788.5 | 1959.4
2030-05-03 20:30 | 2030-05-03 22:00 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 6 |  | 14 | 1 |  | Standalone |  | 2.25 | 790 | 1957.9
2030-05-03 22:00 | 2030-05-03 23:30 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 6 |  | 15 | 1 |  | Standalone |  | 2.25 | 791.5 | 1956.4
2030-05-03 23:30 | 2030-05-04 02:30 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 6 |  | 16 | 1 |  | Standalone |  | 3 | 794.5 | 1953.4
2030-05-04 02:30 | 2030-05-04 04:30 | 2 | Jacking down at port | OFFSHORE | Working | 6 |  | 17 | 1 |  | Standalone |  | 3 | 796.5 | 1951.4
2030-05-04 04:30 | 2030-05-04 05:30 | 1 | Port maneuvering | OFFSHORE | Working | 6 |  | 18 | 1 |  | Standalone |  | 1.5 | 797.5 | 1950.4
2030-05-04 05:30 | 2030-05-04 10:42 | 5.2 | Transit from port to site | OFFSHORE | Working | 6 |  | 19 | 1 |  | Standalone |  | 7.8 | 802.7 | 1945.2
2030-05-04 10:42 | 2030-05-04 11:12 | 0.5 | DP field check | OFFSHORE | Working | 6 |  | 20 | 1 |  | Standalone |  | 0.75 | 803.2 | 1944.7
2030-05-04 11:12 | 2030-05-04 12:12 | 1 | Transit to next foundation | OFFSHORE | Working | 6 | 11 | 21 | 1 |  | Standalone |  | 1.5 | 804.2 | 1943.7
2030-05-04 12:12 | 2030-05-04 13:12 | 1 | Positioning at WTG location | OFFSHORE | Working | 6 | 11 | 22 | 1 |  | Standalone |  | 1.5 | 805.2 | 1942.7
2030-05-04 13:12 | 2030-05-04 17:12 | 4 | Preload and jacking up at site | OFFSHORE | Working | 6 | 11 | 23 | 1 |  | Standalone |  | 6 | 809.2 | 1938.7
2030-05-04 17:12 | 2030-05-04 20:12 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 6 | 11 | 24 | 1 |  | Standalone |  | 3 | 812.2 | 1935.7
2030-05-04 20:12 | 2030-05-04 21:12 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 6 | 11 | 25 | 1 |  | Standalone |  | 1 | 813.2 | 1934.7
2030-05-04 21:12 | 2030-05-04 23:12 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 6 | 11 | 26 | 1 |  | Standalone |  | 2 | 815.2 | 1932.7
2030-05-04 23:12 | 2030-05-05 00:12 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 6 | 11 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 816.2 | 1931.7
2030-05-05 00:12 | 2030-05-05 03:42 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 11 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 819.7 | 1928.2
2030-05-05 03:42 | 2030-05-05 04:12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 6 | 11 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 820.2 | 1927.7
2030-05-05 04:12 | 2030-05-05 04:42 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 6 | 11 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 820.7 | 1927.2
2030-05-05 04:42 | 2030-05-05 06:57 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 11 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 822.95 | 1924.95
2030-05-05 06:57 | 2030-05-05 07:27 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 6 | 11 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 823.45 | 1924.45
2030-05-05 07:27 | 2030-05-05 07:57 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 6 | 11 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 823.95 | 1923.95
2030-05-05 07:57 | 2030-05-05 09:42 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 11 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 825.7 | 1922.2
2030-05-05 09:42 | 2030-05-05 11:12 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 6 | 11 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 827.2 | 1920.7
2030-05-05 11:12 | 2030-05-05 12:57 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 11 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 828.95 | 1918.95
2030-05-05 12:57 | 2030-05-05 14:27 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 6 | 11 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 830.45 | 1917.45
2030-05-05 14:27 | 2030-05-05 16:12 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 11 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 832.2 | 1915.7
2030-05-05 16:12 | 2030-05-05 17:42 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 6 | 11 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 833.7 | 1914.2
2030-05-05 17:42 | 2030-05-05 18:42 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 6 | 11 | 40 | 1 |  | Standalone |  | 1 | 834.7 | 1913.2
2030-05-05 18:42 | 2030-05-05 19:42 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 6 | 11 | 41 | 1 |  | Standalone |  | 1 | 835.7 | 1912.2
2030-05-05 19:42 | 2030-05-05 22:42 | 3 | Turbine general completion works | OFFSHORE | Working | 6 | 11 | 42 | 1 |  | Standalone |  | 3 | 838.7 | 1909.2
2030-05-05 22:42 | 2030-05-06 01:42 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 6 | 11 | 43 | 1 |  | Standalone |  | 3 | 841.7 | 1906.2
2030-05-06 01:42 | 2030-05-06 03:42 | 2 | Jacking down at site | OFFSHORE | Working | 6 | 11 | 44 | 1 |  | Standalone |  | 3 | 843.7 | 1904.2
2030-05-06 03:42 | 2030-05-06 04:42 | 1 | Transit to next foundation | OFFSHORE | Working | 6 | 12 | 21 | 1 |  | Standalone |  | 1.5 | 844.7 | 1903.2
2030-05-06 04:42 | 2030-05-06 05:42 | 1 | Positioning at WTG location | OFFSHORE | Working | 6 | 12 | 22 | 1 |  | Standalone |  | 1.5 | 845.7 | 1902.2
2030-05-06 05:42 | 2030-05-06 09:42 | 4 | Preload and jacking up at site | OFFSHORE | Working | 6 | 12 | 23 | 1 |  | Standalone |  | 6 | 849.7 | 1898.2
2030-05-06 09:42 | 2030-05-06 12:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 6 | 12 | 24 | 1 |  | Standalone |  | 3 | 852.7 | 1895.2
2030-05-06 12:42 | 2030-05-06 13:42 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 6 | 12 | 25 | 1 |  | Standalone |  | 1 | 853.7 | 1894.2
2030-05-06 13:42 | 2030-05-06 15:42 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 6 | 12 | 26 | 1 |  | Standalone |  | 2 | 855.7 | 1892.2
2030-05-06 15:42 | 2030-05-06 16:42 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 6 | 12 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 856.7 | 1891.2
2030-05-06 16:42 | 2030-05-06 20:12 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 12 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 860.2 | 1887.7
2030-05-06 20:12 | 2030-05-06 20:42 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 6 | 12 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 860.7 | 1887.2
2030-05-06 20:42 | 2030-05-06 21:12 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 6 | 12 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 861.2 | 1886.7
2030-05-06 21:12 | 2030-05-06 23:27 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 12 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 863.45 | 1884.45
2030-05-06 23:27 | 2030-05-06 23:57 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 6 | 12 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 863.95 | 1883.95
2030-05-06 23:57 | 2030-05-07 00:27 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 6 | 12 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 864.45 | 1883.45
2030-05-07 00:27 | 2030-05-07 02:12 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 12 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 866.2 | 1881.7
2030-05-07 02:12 | 2030-05-07 03:42 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 6 | 12 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 867.7 | 1880.2
2030-05-07 03:42 | 2030-05-07 05:27 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 12 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 869.45 | 1878.45
2030-05-07 05:27 | 2030-05-07 06:57 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 6 | 12 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 870.95 | 1876.95
2030-05-07 06:57 | 2030-05-07 08:42 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 6 | 12 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 872.7 | 1875.2
2030-05-07 08:42 | 2030-05-07 10:12 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 6 | 12 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 874.2 | 1873.7
2030-05-07 10:12 | 2030-05-07 11:12 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 6 | 12 | 40 | 1 |  | Standalone |  | 1 | 875.2 | 1872.7
2030-05-07 11:12 | 2030-05-07 12:12 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 6 | 12 | 41 | 1 |  | Standalone |  | 1 | 876.2 | 1871.7
2030-05-07 12:12 | 2030-05-07 15:12 | 3 | Turbine general completion works | OFFSHORE | Working | 6 | 12 | 42 | 1 |  | Standalone |  | 3 | 879.2 | 1868.7
2030-05-07 15:12 | 2030-05-07 18:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 6 | 12 | 43 | 1 |  | Standalone |  | 3 | 882.2 | 1865.7
2030-05-07 18:12 | 2030-05-07 20:12 | 2 | Jacking down at site | OFFSHORE | Working | 6 | 12 | 44 | 1 |  | Standalone |  | 3 | 884.2 | 1863.7
2030-05-07 20:12 | 2030-05-08 01:24 | 5.2 | Transit from site to port | OFFSHORE | Working | 6 |  | 45 | 1 |  | Standalone |  | 7.8 | 889.4 | 1858.5
2030-05-08 01:24 | 2030-05-08 02:24 | 1 | Port maneuvering | OFFSHORE | Working | 7 |  | 1 | 1 |  | Standalone |  | 1.5 | 890.4 | 1857.5
2030-05-08 02:24 | 2030-05-08 04:24 | 2 | Preload and jacking up at port | OFFSHORE | Working | 7 |  | 2 | 1 |  | Standalone |  | 3 | 892.4 | 1855.5
2030-05-08 04:24 | 2030-05-08 07:24 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 7 |  | 3 | 1 |  | Standalone |  | 3 | 895.4 | 1852.5
2030-05-08 07:24 | 2030-05-08 08:24 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 7 |  | 4 | 1 |  | Standalone |  | 1 | 896.4 | 1851.5
2030-05-08 08:24 | 2030-05-08 10:39 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 7 |  | 5 | 1 |  | Standalone |  | 3.375 | 898.65 | 1849.25
2030-05-08 10:39 | 2030-05-08 12:54 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 7 |  | 6 | 1 |  | Standalone |  | 3.375 | 900.9 | 1847
2030-05-08 12:54 | 2030-05-08 14:24 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 7 |  | 7 | 1 |  | Standalone |  | 2.25 | 902.4 | 1845.5
2030-05-08 14:24 | 2030-05-08 15:54 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 7 |  | 8 | 1 |  | Standalone |  | 2.25 | 903.9 | 1844
2030-05-08 15:54 | 2030-05-08 17:24 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 7 |  | 9 | 1 |  | Standalone |  | 2.25 | 905.4 | 1842.5
2030-05-08 17:24 | 2030-05-08 18:24 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 7 |  | 10 | 1 |  | Standalone |  | 1 | 906.4 | 1841.5
2030-05-08 18:24 | 2030-05-08 20:39 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 7 |  | 11 | 1 |  | Standalone |  | 3.375 | 908.65 | 1839.25
2030-05-08 20:39 | 2030-05-08 22:54 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 7 |  | 12 | 1 |  | Standalone |  | 3.375 | 910.9 | 1837
2030-05-08 22:54 | 2030-05-09 00:24 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 7 |  | 13 | 1 |  | Standalone |  | 2.25 | 912.4 | 1835.5
2030-05-09 00:24 | 2030-05-09 01:54 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 7 |  | 14 | 1 |  | Standalone |  | 2.25 | 913.9 | 1834
2030-05-09 01:54 | 2030-05-09 03:24 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 7 |  | 15 | 1 |  | Standalone |  | 2.25 | 915.4 | 1832.5
2030-05-09 03:24 | 2030-05-09 06:24 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 7 |  | 16 | 1 |  | Standalone |  | 3 | 918.4 | 1829.5
2030-05-09 06:24 | 2030-05-09 08:24 | 2 | Jacking down at port | OFFSHORE | Working | 7 |  | 17 | 1 |  | Standalone |  | 3 | 920.4 | 1827.5
2030-05-09 08:24 | 2030-05-09 09:24 | 1 | Port maneuvering | OFFSHORE | Working | 7 |  | 18 | 1 |  | Standalone |  | 1.5 | 921.4 | 1826.5
2030-05-09 09:24 | 2030-05-09 14:36 | 5.2 | Transit from port to site | OFFSHORE | Working | 7 |  | 19 | 1 |  | Standalone |  | 7.8 | 926.6 | 1821.3
2030-05-09 14:36 | 2030-05-09 15:06 | 0.5 | DP field check | OFFSHORE | Working | 7 |  | 20 | 1 |  | Standalone |  | 0.75 | 927.1 | 1820.8
2030-05-09 15:06 | 2030-05-09 16:06 | 1 | Transit to next foundation | OFFSHORE | Working | 7 | 13 | 21 | 1 |  | Standalone |  | 1.5 | 928.1 | 1819.8
2030-05-09 16:06 | 2030-05-09 17:06 | 1 | Positioning at WTG location | OFFSHORE | Working | 7 | 13 | 22 | 1 |  | Standalone |  | 1.5 | 929.1 | 1818.8
2030-05-09 17:06 | 2030-05-09 21:06 | 4 | Preload and jacking up at site | OFFSHORE | Working | 7 | 13 | 23 | 1 |  | Standalone |  | 6 | 933.1 | 1814.8
2030-05-09 21:06 | 2030-05-10 00:06 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 7 | 13 | 24 | 1 |  | Standalone |  | 3 | 936.1 | 1811.8
2030-05-10 00:06 | 2030-05-10 01:06 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 7 | 13 | 25 | 1 |  | Standalone |  | 1 | 937.1 | 1810.8
2030-05-10 01:06 | 2030-05-10 03:06 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 7 | 13 | 26 | 1 |  | Standalone |  | 2 | 939.1 | 1808.8
2030-05-10 03:06 | 2030-05-10 04:06 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 7 | 13 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 940.1 | 1807.8
2030-05-10 04:06 | 2030-05-10 07:36 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 13 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 943.6 | 1804.3
2030-05-10 07:36 | 2030-05-10 08:06 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 7 | 13 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 944.1 | 1803.8
2030-05-10 08:06 | 2030-05-10 08:36 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 7 | 13 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 944.6 | 1803.3
2030-05-10 08:36 | 2030-05-10 10:51 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 13 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 946.85 | 1801.05
2030-05-10 10:51 | 2030-05-10 11:21 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 7 | 13 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 947.35 | 1800.55
2030-05-10 11:21 | 2030-05-10 11:51 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 7 | 13 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 947.85 | 1800.05
2030-05-10 11:51 | 2030-05-10 13:36 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 13 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 949.6 | 1798.3
2030-05-10 13:36 | 2030-05-10 15:06 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 7 | 13 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 951.1 | 1796.8
2030-05-10 15:06 | 2030-05-10 16:51 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 13 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 952.85 | 1795.05
2030-05-10 16:51 | 2030-05-10 18:21 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 7 | 13 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 954.35 | 1793.55
2030-05-10 18:21 | 2030-05-10 20:06 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 13 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 956.1 | 1791.8
2030-05-10 20:06 | 2030-05-10 21:36 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 7 | 13 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 957.6 | 1790.3
2030-05-10 21:36 | 2030-05-10 22:36 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 7 | 13 | 40 | 1 |  | Standalone |  | 1 | 958.6 | 1789.3
2030-05-10 22:36 | 2030-05-10 23:36 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 7 | 13 | 41 | 1 |  | Standalone |  | 1 | 959.6 | 1788.3
2030-05-10 23:36 | 2030-05-11 02:36 | 3 | Turbine general completion works | OFFSHORE | Working | 7 | 13 | 42 | 1 |  | Standalone |  | 3 | 962.6 | 1785.3
2030-05-11 02:36 | 2030-05-11 05:36 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 7 | 13 | 43 | 1 |  | Standalone |  | 3 | 965.6 | 1782.3
2030-05-11 05:36 | 2030-05-11 07:36 | 2 | Jacking down at site | OFFSHORE | Working | 7 | 13 | 44 | 1 |  | Standalone |  | 3 | 967.6 | 1780.3
2030-05-11 07:36 | 2030-05-11 08:36 | 1 | Transit to next foundation | OFFSHORE | Working | 7 | 14 | 21 | 1 |  | Standalone |  | 1.5 | 968.6 | 1779.3
2030-05-11 08:36 | 2030-05-11 09:36 | 1 | Positioning at WTG location | OFFSHORE | Working | 7 | 14 | 22 | 1 |  | Standalone |  | 1.5 | 969.6 | 1778.3
2030-05-11 09:36 | 2030-05-11 13:36 | 4 | Preload and jacking up at site | OFFSHORE | Working | 7 | 14 | 23 | 1 |  | Standalone |  | 6 | 973.6 | 1774.3
2030-05-11 13:36 | 2030-05-11 16:36 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 7 | 14 | 24 | 1 |  | Standalone |  | 3 | 976.6 | 1771.3
2030-05-11 16:36 | 2030-05-11 17:36 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 7 | 14 | 25 | 1 |  | Standalone |  | 1 | 977.6 | 1770.3
2030-05-11 17:36 | 2030-05-11 19:36 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 7 | 14 | 26 | 1 |  | Standalone |  | 2 | 979.6 | 1768.3
2030-05-11 19:36 | 2030-05-11 20:36 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 7 | 14 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 980.6 | 1767.3
2030-05-11 20:36 | 2030-05-12 00:06 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 14 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 984.1 | 1763.8
2030-05-12 00:06 | 2030-05-12 00:36 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 7 | 14 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 984.6 | 1763.3
2030-05-12 00:36 | 2030-05-12 01:06 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 7 | 14 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 985.1 | 1762.8
2030-05-12 01:06 | 2030-05-12 03:21 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 14 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 987.35 | 1760.55
2030-05-12 03:21 | 2030-05-12 03:51 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 7 | 14 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 987.85 | 1760.05
2030-05-12 03:51 | 2030-05-12 04:21 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 7 | 14 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 988.35 | 1759.55
2030-05-12 04:21 | 2030-05-12 06:06 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 14 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 990.1 | 1757.8
2030-05-12 06:06 | 2030-05-12 07:36 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 7 | 14 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 991.6 | 1756.3
2030-05-12 07:36 | 2030-05-12 09:21 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 14 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 993.35 | 1754.55
2030-05-12 09:21 | 2030-05-12 10:51 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 7 | 14 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 994.85 | 1753.05
2030-05-12 10:51 | 2030-05-12 12:36 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 7 | 14 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 996.6 | 1751.3
2030-05-12 12:36 | 2030-05-12 14:06 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 7 | 14 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 998.1 | 1749.8
2030-05-12 14:06 | 2030-05-12 15:06 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 7 | 14 | 40 | 1 |  | Standalone |  | 1 | 999.1 | 1748.8
2030-05-12 15:06 | 2030-05-12 16:06 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 7 | 14 | 41 | 1 |  | Standalone |  | 1 | 1000.1 | 1747.8
2030-05-12 16:06 | 2030-05-12 19:06 | 3 | Turbine general completion works | OFFSHORE | Working | 7 | 14 | 42 | 1 |  | Standalone |  | 3 | 1003.1 | 1744.8
2030-05-12 19:06 | 2030-05-12 22:06 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 7 | 14 | 43 | 1 |  | Standalone |  | 3 | 1006.1 | 1741.8
2030-05-12 22:06 | 2030-05-13 00:06 | 2 | Jacking down at site | OFFSHORE | Working | 7 | 14 | 44 | 1 |  | Standalone |  | 3 | 1008.1 | 1739.8
2030-05-13 00:06 | 2030-05-13 05:18 | 5.2 | Transit from site to port | OFFSHORE | Working | 7 |  | 45 | 1 |  | Standalone |  | 7.8 | 1013.3 | 1734.6
2030-05-13 05:18 | 2030-05-13 06:18 | 1 | Port maneuvering | OFFSHORE | Working | 8 |  | 1 | 1 |  | Standalone |  | 1.5 | 1014.3 | 1733.6
2030-05-13 06:18 | 2030-05-13 08:18 | 2 | Preload and jacking up at port | OFFSHORE | Working | 8 |  | 2 | 1 |  | Standalone |  | 3 | 1016.3 | 1731.6
2030-05-13 08:18 | 2030-05-13 11:18 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 8 |  | 3 | 1 |  | Standalone |  | 3 | 1019.3 | 1728.6
2030-05-13 11:18 | 2030-05-13 12:18 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 8 |  | 4 | 1 |  | Standalone |  | 1 | 1020.3 | 1727.6
2030-05-13 12:18 | 2030-05-13 14:33 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 8 |  | 5 | 1 |  | Standalone |  | 3.375 | 1022.55 | 1725.35
2030-05-13 14:33 | 2030-05-13 16:48 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 8 |  | 6 | 1 |  | Standalone |  | 3.375 | 1024.8 | 1723.1
2030-05-13 16:48 | 2030-05-13 18:18 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 8 |  | 7 | 1 |  | Standalone |  | 2.25 | 1026.3 | 1721.6
2030-05-13 18:18 | 2030-05-13 19:48 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 8 |  | 8 | 1 |  | Standalone |  | 2.25 | 1027.8 | 1720.1
2030-05-13 19:48 | 2030-05-13 21:18 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 8 |  | 9 | 1 |  | Standalone |  | 2.25 | 1029.3 | 1718.6
2030-05-13 21:18 | 2030-05-13 22:18 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 8 |  | 10 | 1 |  | Standalone |  | 1 | 1030.3 | 1717.6
2030-05-13 22:18 | 2030-05-14 00:33 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 8 |  | 11 | 1 |  | Standalone |  | 3.375 | 1032.55 | 1715.35
2030-05-14 00:33 | 2030-05-14 02:48 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 8 |  | 12 | 1 |  | Standalone |  | 3.375 | 1034.8 | 1713.1
2030-05-14 02:48 | 2030-05-14 04:18 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 8 |  | 13 | 1 |  | Standalone |  | 2.25 | 1036.3 | 1711.6
2030-05-14 04:18 | 2030-05-14 05:48 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 8 |  | 14 | 1 |  | Standalone |  | 2.25 | 1037.8 | 1710.1
2030-05-14 05:48 | 2030-05-14 07:18 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 8 |  | 15 | 1 |  | Standalone |  | 2.25 | 1039.3 | 1708.6
2030-05-14 07:18 | 2030-05-14 10:18 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 8 |  | 16 | 1 |  | Standalone |  | 3 | 1042.3 | 1705.6
2030-05-14 10:18 | 2030-05-14 12:18 | 2 | Jacking down at port | OFFSHORE | Working | 8 |  | 17 | 1 |  | Standalone |  | 3 | 1044.3 | 1703.6
2030-05-14 12:18 | 2030-05-14 13:18 | 1 | Port maneuvering | OFFSHORE | Working | 8 |  | 18 | 1 |  | Standalone |  | 1.5 | 1045.3 | 1702.6
2030-05-14 13:18 | 2030-05-14 18:30 | 5.2 | Transit from port to site | OFFSHORE | Working | 8 |  | 19 | 1 |  | Standalone |  | 7.8 | 1050.5 | 1697.4
2030-05-14 18:30 | 2030-05-14 19:00 | 0.5 | DP field check | OFFSHORE | Working | 8 |  | 20 | 1 |  | Standalone |  | 0.75 | 1051 | 1696.9
2030-05-14 19:00 | 2030-05-14 20:00 | 1 | Transit to next foundation | OFFSHORE | Working | 8 | 15 | 21 | 1 |  | Standalone |  | 1.5 | 1052 | 1695.9
2030-05-14 20:00 | 2030-05-14 21:00 | 1 | Positioning at WTG location | OFFSHORE | Working | 8 | 15 | 22 | 1 |  | Standalone |  | 1.5 | 1053 | 1694.9
2030-05-14 21:00 | 2030-05-15 01:00 | 4 | Preload and jacking up at site | OFFSHORE | Working | 8 | 15 | 23 | 1 |  | Standalone |  | 6 | 1057 | 1690.9
2030-05-15 01:00 | 2030-05-15 04:00 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 8 | 15 | 24 | 1 |  | Standalone |  | 3 | 1060 | 1687.9
2030-05-15 04:00 | 2030-05-15 05:00 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 8 | 15 | 25 | 1 |  | Standalone |  | 1 | 1061 | 1686.9
2030-05-15 05:00 | 2030-05-15 07:00 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 8 | 15 | 26 | 1 |  | Standalone |  | 2 | 1063 | 1684.9
2030-05-15 07:00 | 2030-05-15 08:00 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 8 | 15 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1064 | 1683.9
2030-05-15 08:00 | 2030-05-15 11:30 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 15 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1067.5 | 1680.4
2030-05-15 11:30 | 2030-05-15 12:00 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 8 | 15 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1068 | 1679.9
2030-05-15 12:00 | 2030-05-15 12:30 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 8 | 15 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1068.5 | 1679.4
2030-05-15 12:30 | 2030-05-15 14:45 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 15 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1070.75 | 1677.15
2030-05-15 14:45 | 2030-05-15 15:15 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 8 | 15 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1071.25 | 1676.65
2030-05-15 15:15 | 2030-05-15 15:45 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 8 | 15 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1071.75 | 1676.15
2030-05-15 15:45 | 2030-05-15 17:30 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 15 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1073.5 | 1674.4
2030-05-15 17:30 | 2030-05-15 19:00 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 8 | 15 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1075 | 1672.9
2030-05-15 19:00 | 2030-05-15 20:45 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 15 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1076.75 | 1671.15
2030-05-15 20:45 | 2030-05-15 22:15 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 8 | 15 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1078.25 | 1669.65
2030-05-15 22:15 | 2030-05-16 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 15 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1080 | 1667.9
2030-05-16 | 2030-05-16 01:30 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 8 | 15 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1081.5 | 1666.4
2030-05-16 01:30 | 2030-05-16 02:30 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 8 | 15 | 40 | 1 |  | Standalone |  | 1 | 1082.5 | 1665.4
2030-05-16 02:30 | 2030-05-16 03:30 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 8 | 15 | 41 | 1 |  | Standalone |  | 1 | 1083.5 | 1664.4
2030-05-16 03:30 | 2030-05-16 06:30 | 3 | Turbine general completion works | OFFSHORE | Working | 8 | 15 | 42 | 1 |  | Standalone |  | 3 | 1086.5 | 1661.4
2030-05-16 06:30 | 2030-05-16 09:30 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 8 | 15 | 43 | 1 |  | Standalone |  | 3 | 1089.5 | 1658.4
2030-05-16 09:30 | 2030-05-16 11:30 | 2 | Jacking down at site | OFFSHORE | Working | 8 | 15 | 44 | 1 |  | Standalone |  | 3 | 1091.5 | 1656.4
2030-05-16 11:30 | 2030-05-16 12:30 | 1 | Transit to next foundation | OFFSHORE | Working | 8 | 16 | 21 | 1 |  | Standalone |  | 1.5 | 1092.5 | 1655.4
2030-05-16 12:30 | 2030-05-16 13:30 | 1 | Positioning at WTG location | OFFSHORE | Working | 8 | 16 | 22 | 1 |  | Standalone |  | 1.5 | 1093.5 | 1654.4
2030-05-16 13:30 | 2030-05-16 17:30 | 4 | Preload and jacking up at site | OFFSHORE | Working | 8 | 16 | 23 | 1 |  | Standalone |  | 6 | 1097.5 | 1650.4
2030-05-16 17:30 | 2030-05-16 20:30 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 8 | 16 | 24 | 1 |  | Standalone |  | 3 | 1100.5 | 1647.4
2030-05-16 20:30 | 2030-05-16 21:30 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 8 | 16 | 25 | 1 |  | Standalone |  | 1 | 1101.5 | 1646.4
2030-05-16 21:30 | 2030-05-16 23:30 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 8 | 16 | 26 | 1 |  | Standalone |  | 2 | 1103.5 | 1644.4
2030-05-16 23:30 | 2030-05-17 00:30 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 8 | 16 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1104.5 | 1643.4
2030-05-17 00:30 | 2030-05-17 04:00 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 16 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1108 | 1639.9
2030-05-17 04:00 | 2030-05-17 04:30 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 8 | 16 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1108.5 | 1639.4
2030-05-17 04:30 | 2030-05-17 05:00 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 8 | 16 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1109 | 1638.9
2030-05-17 05:00 | 2030-05-17 07:15 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 16 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1111.25 | 1636.65
2030-05-17 07:15 | 2030-05-17 07:45 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 8 | 16 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1111.75 | 1636.15
2030-05-17 07:45 | 2030-05-17 08:15 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 8 | 16 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1112.25 | 1635.65
2030-05-17 08:15 | 2030-05-17 10:00 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 16 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1114 | 1633.9
2030-05-17 10:00 | 2030-05-17 11:30 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 8 | 16 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1115.5 | 1632.4
2030-05-17 11:30 | 2030-05-17 13:15 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 16 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1117.25 | 1630.65
2030-05-17 13:15 | 2030-05-17 14:45 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 8 | 16 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1118.75 | 1629.15
2030-05-17 14:45 | 2030-05-17 16:30 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 8 | 16 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1120.5 | 1627.4
2030-05-17 16:30 | 2030-05-17 18:00 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 8 | 16 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1122 | 1625.9
2030-05-17 18:00 | 2030-05-17 19:00 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 8 | 16 | 40 | 1 |  | Standalone |  | 1 | 1123 | 1624.9
2030-05-17 19:00 | 2030-05-17 20:00 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 8 | 16 | 41 | 1 |  | Standalone |  | 1 | 1124 | 1623.9
2030-05-17 20:00 | 2030-05-17 23:00 | 3 | Turbine general completion works | OFFSHORE | Working | 8 | 16 | 42 | 1 |  | Standalone |  | 3 | 1127 | 1620.9
2030-05-17 23:00 | 2030-05-18 02:00 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 8 | 16 | 43 | 1 |  | Standalone |  | 3 | 1130 | 1617.9
2030-05-18 02:00 | 2030-05-18 04:00 | 2 | Jacking down at site | OFFSHORE | Working | 8 | 16 | 44 | 1 |  | Standalone |  | 3 | 1132 | 1615.9
2030-05-18 04:00 | 2030-05-18 09:12 | 5.2 | Transit from site to port | OFFSHORE | Working | 8 |  | 45 | 1 |  | Standalone |  | 7.8 | 1137.2 | 1610.7
2030-05-18 09:12 | 2030-05-18 10:12 | 1 | Port maneuvering | OFFSHORE | Working | 9 |  | 1 | 1 |  | Standalone |  | 1.5 | 1138.2 | 1609.7
2030-05-18 10:12 | 2030-05-18 12:12 | 2 | Preload and jacking up at port | OFFSHORE | Working | 9 |  | 2 | 1 |  | Standalone |  | 3 | 1140.2 | 1607.7
2030-05-18 12:12 | 2030-05-18 15:12 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 9 |  | 3 | 1 |  | Standalone |  | 3 | 1143.2 | 1604.7
2030-05-18 15:12 | 2030-05-18 16:12 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 9 |  | 4 | 1 |  | Standalone |  | 1 | 1144.2 | 1603.7
2030-05-18 16:12 | 2030-05-18 18:27 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 9 |  | 5 | 1 |  | Standalone |  | 3.375 | 1146.45 | 1601.45
2030-05-18 18:27 | 2030-05-18 20:42 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 9 |  | 6 | 1 |  | Standalone |  | 3.375 | 1148.7 | 1599.2
2030-05-18 20:42 | 2030-05-18 22:12 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 9 |  | 7 | 1 |  | Standalone |  | 2.25 | 1150.2 | 1597.7
2030-05-18 22:12 | 2030-05-18 23:42 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 9 |  | 8 | 1 |  | Standalone |  | 2.25 | 1151.7 | 1596.2
2030-05-18 23:42 | 2030-05-19 01:12 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 9 |  | 9 | 1 |  | Standalone |  | 2.25 | 1153.2 | 1594.7
2030-05-19 01:12 | 2030-05-19 02:12 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 9 |  | 10 | 1 |  | Standalone |  | 1 | 1154.2 | 1593.7
2030-05-19 02:12 | 2030-05-19 04:27 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 9 |  | 11 | 1 |  | Standalone |  | 3.375 | 1156.45 | 1591.45
2030-05-19 04:27 | 2030-05-19 06:42 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 9 |  | 12 | 1 |  | Standalone |  | 3.375 | 1158.7 | 1589.2
2030-05-19 06:42 | 2030-05-19 08:12 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 9 |  | 13 | 1 |  | Standalone |  | 2.25 | 1160.2 | 1587.7
2030-05-19 08:12 | 2030-05-19 09:42 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 9 |  | 14 | 1 |  | Standalone |  | 2.25 | 1161.7 | 1586.2
2030-05-19 09:42 | 2030-05-19 11:12 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 9 |  | 15 | 1 |  | Standalone |  | 2.25 | 1163.2 | 1584.7
2030-05-19 11:12 | 2030-05-19 14:12 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 9 |  | 16 | 1 |  | Standalone |  | 3 | 1166.2 | 1581.7
2030-05-19 14:12 | 2030-05-19 16:12 | 2 | Jacking down at port | OFFSHORE | Working | 9 |  | 17 | 1 |  | Standalone |  | 3 | 1168.2 | 1579.7
2030-05-19 16:12 | 2030-05-19 17:12 | 1 | Port maneuvering | OFFSHORE | Working | 9 |  | 18 | 1 |  | Standalone |  | 1.5 | 1169.2 | 1578.7
2030-05-19 17:12 | 2030-05-19 22:24 | 5.2 | Transit from port to site | OFFSHORE | Working | 9 |  | 19 | 1 |  | Standalone |  | 7.8 | 1174.4 | 1573.5
2030-05-19 22:24 | 2030-05-19 22:54 | 0.5 | DP field check | OFFSHORE | Working | 9 |  | 20 | 1 |  | Standalone |  | 0.75 | 1174.9 | 1573
2030-05-19 22:54 | 2030-05-19 23:54 | 1 | Transit to next foundation | OFFSHORE | Working | 9 | 17 | 21 | 1 |  | Standalone |  | 1.5 | 1175.9 | 1572
2030-05-19 23:54 | 2030-05-20 00:54 | 1 | Positioning at WTG location | OFFSHORE | Working | 9 | 17 | 22 | 1 |  | Standalone |  | 1.5 | 1176.9 | 1571
2030-05-20 00:54 | 2030-05-20 04:54 | 4 | Preload and jacking up at site | OFFSHORE | Working | 9 | 17 | 23 | 1 |  | Standalone |  | 6 | 1180.9 | 1567
2030-05-20 04:54 | 2030-05-20 07:54 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 9 | 17 | 24 | 1 |  | Standalone |  | 3 | 1183.9 | 1564
2030-05-20 07:54 | 2030-05-20 08:54 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 9 | 17 | 25 | 1 |  | Standalone |  | 1 | 1184.9 | 1563
2030-05-20 08:54 | 2030-05-20 10:54 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 9 | 17 | 26 | 1 |  | Standalone |  | 2 | 1186.9 | 1561
2030-05-20 10:54 | 2030-05-20 11:54 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 9 | 17 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1187.9 | 1560
2030-05-20 11:54 | 2030-05-20 15:24 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 17 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1191.4 | 1556.5
2030-05-20 15:24 | 2030-05-20 15:54 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 9 | 17 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1191.9 | 1556
2030-05-20 15:54 | 2030-05-20 16:24 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 9 | 17 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1192.4 | 1555.5
2030-05-20 16:24 | 2030-05-20 18:39 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 17 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1194.65 | 1553.25
2030-05-20 18:39 | 2030-05-20 19:09 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 9 | 17 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1195.15 | 1552.75
2030-05-20 19:09 | 2030-05-20 19:39 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 9 | 17 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1195.65 | 1552.25
2030-05-20 19:39 | 2030-05-20 21:24 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 17 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1197.4 | 1550.5
2030-05-20 21:24 | 2030-05-20 22:54 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 9 | 17 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1198.9 | 1549
2030-05-20 22:54 | 2030-05-21 00:39 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 17 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1200.65 | 1547.25
2030-05-21 00:39 | 2030-05-21 02:09 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 9 | 17 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1202.15 | 1545.75
2030-05-21 02:09 | 2030-05-21 03:54 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 17 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1203.9 | 1544
2030-05-21 03:54 | 2030-05-21 05:24 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 9 | 17 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1205.4 | 1542.5
2030-05-21 05:24 | 2030-05-21 06:24 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 9 | 17 | 40 | 1 |  | Standalone |  | 1 | 1206.4 | 1541.5
2030-05-21 06:24 | 2030-05-21 07:24 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 9 | 17 | 41 | 1 |  | Standalone |  | 1 | 1207.4 | 1540.5
2030-05-21 07:24 | 2030-05-21 10:24 | 3 | Turbine general completion works | OFFSHORE | Working | 9 | 17 | 42 | 1 |  | Standalone |  | 3 | 1210.4 | 1537.5
2030-05-21 10:24 | 2030-05-21 13:24 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 9 | 17 | 43 | 1 |  | Standalone |  | 3 | 1213.4 | 1534.5
2030-05-21 13:24 | 2030-05-21 15:24 | 2 | Jacking down at site | OFFSHORE | Working | 9 | 17 | 44 | 1 |  | Standalone |  | 3 | 1215.4 | 1532.5
2030-05-21 15:24 | 2030-05-21 16:24 | 1 | Transit to next foundation | OFFSHORE | Working | 9 | 18 | 21 | 1 |  | Standalone |  | 1.5 | 1216.4 | 1531.5
2030-05-21 16:24 | 2030-05-21 17:24 | 1 | Positioning at WTG location | OFFSHORE | Working | 9 | 18 | 22 | 1 |  | Standalone |  | 1.5 | 1217.4 | 1530.5
2030-05-21 17:24 | 2030-05-21 21:24 | 4 | Preload and jacking up at site | OFFSHORE | Working | 9 | 18 | 23 | 1 |  | Standalone |  | 6 | 1221.4 | 1526.5
2030-05-21 21:24 | 2030-05-22 00:24 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 9 | 18 | 24 | 1 |  | Standalone |  | 3 | 1224.4 | 1523.5
2030-05-22 00:24 | 2030-05-22 01:24 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 9 | 18 | 25 | 1 |  | Standalone |  | 1 | 1225.4 | 1522.5
2030-05-22 01:24 | 2030-05-22 03:24 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 9 | 18 | 26 | 1 |  | Standalone |  | 2 | 1227.4 | 1520.5
2030-05-22 03:24 | 2030-05-22 04:24 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 9 | 18 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1228.4 | 1519.5
2030-05-22 04:24 | 2030-05-22 07:54 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 18 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1231.9 | 1516
2030-05-22 07:54 | 2030-05-22 08:24 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 9 | 18 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1232.4 | 1515.5
2030-05-22 08:24 | 2030-05-22 08:54 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 9 | 18 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1232.9 | 1515
2030-05-22 08:54 | 2030-05-22 11:09 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 18 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1235.15 | 1512.75
2030-05-22 11:09 | 2030-05-22 11:39 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 9 | 18 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1235.65 | 1512.25
2030-05-22 11:39 | 2030-05-22 12:09 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 9 | 18 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1236.15 | 1511.75
2030-05-22 12:09 | 2030-05-22 13:54 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 18 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1237.9 | 1510
2030-05-22 13:54 | 2030-05-22 15:24 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 9 | 18 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1239.4 | 1508.5
2030-05-22 15:24 | 2030-05-22 17:09 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 18 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1241.15 | 1506.75
2030-05-22 17:09 | 2030-05-22 18:39 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 9 | 18 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1242.65 | 1505.25
2030-05-22 18:39 | 2030-05-22 20:24 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 9 | 18 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1244.4 | 1503.5
2030-05-22 20:24 | 2030-05-22 21:54 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 9 | 18 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1245.9 | 1502
2030-05-22 21:54 | 2030-05-22 22:54 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 9 | 18 | 40 | 1 |  | Standalone |  | 1 | 1246.9 | 1501
2030-05-22 22:54 | 2030-05-22 23:54 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 9 | 18 | 41 | 1 |  | Standalone |  | 1 | 1247.9 | 1500
2030-05-22 23:54 | 2030-05-23 02:54 | 3 | Turbine general completion works | OFFSHORE | Working | 9 | 18 | 42 | 1 |  | Standalone |  | 3 | 1250.9 | 1497
2030-05-23 02:54 | 2030-05-23 05:54 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 9 | 18 | 43 | 1 |  | Standalone |  | 3 | 1253.9 | 1494
2030-05-23 05:54 | 2030-05-23 07:54 | 2 | Jacking down at site | OFFSHORE | Working | 9 | 18 | 44 | 1 |  | Standalone |  | 3 | 1255.9 | 1492
2030-05-23 07:54 | 2030-05-23 13:06 | 5.2 | Transit from site to port | OFFSHORE | Working | 9 |  | 45 | 1 |  | Standalone |  | 7.8 | 1261.1 | 1486.8
2030-05-23 13:06 | 2030-05-23 14:06 | 1 | Port maneuvering | OFFSHORE | Working | 10 |  | 1 | 1 |  | Standalone |  | 1.5 | 1262.1 | 1485.8
2030-05-23 14:06 | 2030-05-23 16:06 | 2 | Preload and jacking up at port | OFFSHORE | Working | 10 |  | 2 | 1 |  | Standalone |  | 3 | 1264.1 | 1483.8
2030-05-23 16:06 | 2030-05-23 19:06 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 10 |  | 3 | 1 |  | Standalone |  | 3 | 1267.1 | 1480.8
2030-05-23 19:06 | 2030-05-23 20:06 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 10 |  | 4 | 1 |  | Standalone |  | 1 | 1268.1 | 1479.8
2030-05-23 20:06 | 2030-05-23 22:21 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 10 |  | 5 | 1 |  | Standalone |  | 3.375 | 1270.35 | 1477.55
2030-05-23 22:21 | 2030-05-24 00:36 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 10 |  | 6 | 1 |  | Standalone |  | 3.375 | 1272.6 | 1475.3
2030-05-24 00:36 | 2030-05-24 02:06 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 10 |  | 7 | 1 |  | Standalone |  | 2.25 | 1274.1 | 1473.8
2030-05-24 02:06 | 2030-05-24 03:36 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 10 |  | 8 | 1 |  | Standalone |  | 2.25 | 1275.6 | 1472.3
2030-05-24 03:36 | 2030-05-24 05:06 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 10 |  | 9 | 1 |  | Standalone |  | 2.25 | 1277.1 | 1470.8
2030-05-24 05:06 | 2030-05-24 06:06 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 10 |  | 10 | 1 |  | Standalone |  | 1 | 1278.1 | 1469.8
2030-05-24 06:06 | 2030-05-24 08:21 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 10 |  | 11 | 1 |  | Standalone |  | 3.375 | 1280.35 | 1467.55
2030-05-24 08:21 | 2030-05-24 10:36 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 10 |  | 12 | 1 |  | Standalone |  | 3.375 | 1282.6 | 1465.3
2030-05-24 10:36 | 2030-05-24 12:06 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 10 |  | 13 | 1 |  | Standalone |  | 2.25 | 1284.1 | 1463.8
2030-05-24 12:06 | 2030-05-24 13:36 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 10 |  | 14 | 1 |  | Standalone |  | 2.25 | 1285.6 | 1462.3
2030-05-24 13:36 | 2030-05-24 15:06 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 10 |  | 15 | 1 |  | Standalone |  | 2.25 | 1287.1 | 1460.8
2030-05-24 15:06 | 2030-05-24 18:06 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 10 |  | 16 | 1 |  | Standalone |  | 3 | 1290.1 | 1457.8
2030-05-24 18:06 | 2030-05-24 20:06 | 2 | Jacking down at port | OFFSHORE | Working | 10 |  | 17 | 1 |  | Standalone |  | 3 | 1292.1 | 1455.8
2030-05-24 20:06 | 2030-05-24 21:06 | 1 | Port maneuvering | OFFSHORE | Working | 10 |  | 18 | 1 |  | Standalone |  | 1.5 | 1293.1 | 1454.8
2030-05-24 21:06 | 2030-05-25 02:18 | 5.2 | Transit from port to site | OFFSHORE | Working | 10 |  | 19 | 1 |  | Standalone |  | 7.8 | 1298.3 | 1449.6
2030-05-25 02:18 | 2030-05-25 02:48 | 0.5 | DP field check | OFFSHORE | Working | 10 |  | 20 | 1 |  | Standalone |  | 0.75 | 1298.8 | 1449.1
2030-05-25 02:48 | 2030-05-25 03:48 | 1 | Transit to next foundation | OFFSHORE | Working | 10 | 19 | 21 | 1 |  | Standalone |  | 1.5 | 1299.8 | 1448.1
2030-05-25 03:48 | 2030-05-25 04:48 | 1 | Positioning at WTG location | OFFSHORE | Working | 10 | 19 | 22 | 1 |  | Standalone |  | 1.5 | 1300.8 | 1447.1
2030-05-25 04:48 | 2030-05-25 08:48 | 4 | Preload and jacking up at site | OFFSHORE | Working | 10 | 19 | 23 | 1 |  | Standalone |  | 6 | 1304.8 | 1443.1
2030-05-25 08:48 | 2030-05-25 11:48 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 10 | 19 | 24 | 1 |  | Standalone |  | 3 | 1307.8 | 1440.1
2030-05-25 11:48 | 2030-05-25 12:48 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 10 | 19 | 25 | 1 |  | Standalone |  | 1 | 1308.8 | 1439.1
2030-05-25 12:48 | 2030-05-25 14:48 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 10 | 19 | 26 | 1 |  | Standalone |  | 2 | 1310.8 | 1437.1
2030-05-25 14:48 | 2030-05-25 15:48 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 10 | 19 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1311.8 | 1436.1
2030-05-25 15:48 | 2030-05-25 19:18 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 19 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1315.3 | 1432.6
2030-05-25 19:18 | 2030-05-25 19:48 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 10 | 19 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1315.8 | 1432.1
2030-05-25 19:48 | 2030-05-25 20:18 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 10 | 19 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1316.3 | 1431.6
2030-05-25 20:18 | 2030-05-25 22:33 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 19 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1318.55 | 1429.35
2030-05-25 22:33 | 2030-05-25 23:03 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 10 | 19 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1319.05 | 1428.85
2030-05-25 23:03 | 2030-05-25 23:33 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 10 | 19 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1319.55 | 1428.35
2030-05-25 23:33 | 2030-05-26 01:18 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 19 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1321.3 | 1426.6
2030-05-26 01:18 | 2030-05-26 02:48 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 10 | 19 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1322.8 | 1425.1
2030-05-26 02:48 | 2030-05-26 04:33 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 19 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1324.55 | 1423.35
2030-05-26 04:33 | 2030-05-26 06:03 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 10 | 19 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1326.05 | 1421.85
2030-05-26 06:03 | 2030-05-26 07:48 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 19 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1327.8 | 1420.1
2030-05-26 07:48 | 2030-05-26 09:18 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 10 | 19 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1329.3 | 1418.6
2030-05-26 09:18 | 2030-05-26 10:18 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 10 | 19 | 40 | 1 |  | Standalone |  | 1 | 1330.3 | 1417.6
2030-05-26 10:18 | 2030-05-26 11:18 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 10 | 19 | 41 | 1 |  | Standalone |  | 1 | 1331.3 | 1416.6
2030-05-26 11:18 | 2030-05-26 14:18 | 3 | Turbine general completion works | OFFSHORE | Working | 10 | 19 | 42 | 1 |  | Standalone |  | 3 | 1334.3 | 1413.6
2030-05-26 14:18 | 2030-05-26 17:18 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 10 | 19 | 43 | 1 |  | Standalone |  | 3 | 1337.3 | 1410.6
2030-05-26 17:18 | 2030-05-26 19:18 | 2 | Jacking down at site | OFFSHORE | Working | 10 | 19 | 44 | 1 |  | Standalone |  | 3 | 1339.3 | 1408.6
2030-05-26 19:18 | 2030-05-26 20:18 | 1 | Transit to next foundation | OFFSHORE | Working | 10 | 20 | 21 | 1 |  | Standalone |  | 1.5 | 1340.3 | 1407.6
2030-05-26 20:18 | 2030-05-26 21:18 | 1 | Positioning at WTG location | OFFSHORE | Working | 10 | 20 | 22 | 1 |  | Standalone |  | 1.5 | 1341.3 | 1406.6
2030-05-26 21:18 | 2030-05-27 01:18 | 4 | Preload and jacking up at site | OFFSHORE | Working | 10 | 20 | 23 | 1 |  | Standalone |  | 6 | 1345.3 | 1402.6
2030-05-27 01:18 | 2030-05-27 04:18 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 10 | 20 | 24 | 1 |  | Standalone |  | 3 | 1348.3 | 1399.6
2030-05-27 04:18 | 2030-05-27 05:18 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 10 | 20 | 25 | 1 |  | Standalone |  | 1 | 1349.3 | 1398.6
2030-05-27 05:18 | 2030-05-27 07:18 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 10 | 20 | 26 | 1 |  | Standalone |  | 2 | 1351.3 | 1396.6
2030-05-27 07:18 | 2030-05-27 08:18 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 10 | 20 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1352.3 | 1395.6
2030-05-27 08:18 | 2030-05-27 11:48 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 20 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1355.8 | 1392.1
2030-05-27 11:48 | 2030-05-27 12:18 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 10 | 20 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1356.3 | 1391.6
2030-05-27 12:18 | 2030-05-27 12:48 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 10 | 20 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1356.8 | 1391.1
2030-05-27 12:48 | 2030-05-27 15:03 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 20 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1359.05 | 1388.85
2030-05-27 15:03 | 2030-05-27 15:33 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 10 | 20 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1359.55 | 1388.35
2030-05-27 15:33 | 2030-05-27 16:03 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 10 | 20 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1360.05 | 1387.85
2030-05-27 16:03 | 2030-05-27 17:48 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 20 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1361.8 | 1386.1
2030-05-27 17:48 | 2030-05-27 19:18 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 10 | 20 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1363.3 | 1384.6
2030-05-27 19:18 | 2030-05-27 21:03 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 20 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1365.05 | 1382.85
2030-05-27 21:03 | 2030-05-27 22:33 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 10 | 20 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1366.55 | 1381.35
2030-05-27 22:33 | 2030-05-28 00:18 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 10 | 20 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1368.3 | 1379.6
2030-05-28 00:18 | 2030-05-28 01:48 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 10 | 20 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1369.8 | 1378.1
2030-05-28 01:48 | 2030-05-28 02:48 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 10 | 20 | 40 | 1 |  | Standalone |  | 1 | 1370.8 | 1377.1
2030-05-28 02:48 | 2030-05-28 03:48 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 10 | 20 | 41 | 1 |  | Standalone |  | 1 | 1371.8 | 1376.1
2030-05-28 03:48 | 2030-05-28 06:48 | 3 | Turbine general completion works | OFFSHORE | Working | 10 | 20 | 42 | 1 |  | Standalone |  | 3 | 1374.8 | 1373.1
2030-05-28 06:48 | 2030-05-28 09:48 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 10 | 20 | 43 | 1 |  | Standalone |  | 3 | 1377.8 | 1370.1
2030-05-28 09:48 | 2030-05-28 11:48 | 2 | Jacking down at site | OFFSHORE | Working | 10 | 20 | 44 | 1 |  | Standalone |  | 3 | 1379.8 | 1368.1
2030-05-28 11:48 | 2030-05-28 17:00 | 5.2 | Transit from site to port | OFFSHORE | Working | 10 |  | 45 | 1 |  | Standalone |  | 7.8 | 1385 | 1362.9
2030-05-28 17:00 | 2030-05-28 18:00 | 1 | Port maneuvering | OFFSHORE | Working | 11 |  | 1 | 1 |  | Standalone |  | 1.5 | 1386 | 1361.9
2030-05-28 18:00 | 2030-05-28 20:00 | 2 | Preload and jacking up at port | OFFSHORE | Working | 11 |  | 2 | 1 |  | Standalone |  | 3 | 1388 | 1359.9
2030-05-28 20:00 | 2030-05-28 23:00 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 11 |  | 3 | 1 |  | Standalone |  | 3 | 1391 | 1356.9
2030-05-28 23:00 | 2030-05-29 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 11 |  | 4 | 1 |  | Standalone |  | 1 | 1392 | 1355.9
2030-05-29 | 2030-05-29 02:15 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 11 |  | 5 | 1 |  | Standalone |  | 3.375 | 1394.25 | 1353.65
2030-05-29 02:15 | 2030-05-29 04:30 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 11 |  | 6 | 1 |  | Standalone |  | 3.375 | 1396.5 | 1351.4
2030-05-29 04:30 | 2030-05-29 06:00 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 11 |  | 7 | 1 |  | Standalone |  | 2.25 | 1398 | 1349.9
2030-05-29 06:00 | 2030-05-29 07:30 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 11 |  | 8 | 1 |  | Standalone |  | 2.25 | 1399.5 | 1348.4
2030-05-29 07:30 | 2030-05-29 09:00 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 11 |  | 9 | 1 |  | Standalone |  | 2.25 | 1401 | 1346.9
2030-05-29 09:00 | 2030-05-29 10:00 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 11 |  | 10 | 1 |  | Standalone |  | 1 | 1402 | 1345.9
2030-05-29 10:00 | 2030-05-29 12:15 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 11 |  | 11 | 1 |  | Standalone |  | 3.375 | 1404.25 | 1343.65
2030-05-29 12:15 | 2030-05-29 14:30 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 11 |  | 12 | 1 |  | Standalone |  | 3.375 | 1406.5 | 1341.4
2030-05-29 14:30 | 2030-05-29 16:00 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 11 |  | 13 | 1 |  | Standalone |  | 2.25 | 1408 | 1339.9
2030-05-29 16:00 | 2030-05-29 17:30 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 11 |  | 14 | 1 |  | Standalone |  | 2.25 | 1409.5 | 1338.4
2030-05-29 17:30 | 2030-05-29 19:00 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 11 |  | 15 | 1 |  | Standalone |  | 2.25 | 1411 | 1336.9
2030-05-29 19:00 | 2030-05-29 22:00 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 11 |  | 16 | 1 |  | Standalone |  | 3 | 1414 | 1333.9
2030-05-29 22:00 | 2030-05-30 | 2 | Jacking down at port | OFFSHORE | Working | 11 |  | 17 | 1 |  | Standalone |  | 3 | 1416 | 1331.9
2030-05-30 | 2030-05-30 01:00 | 1 | Port maneuvering | OFFSHORE | Working | 11 |  | 18 | 1 |  | Standalone |  | 1.5 | 1417 | 1330.9
2030-05-30 01:00 | 2030-05-30 06:12 | 5.2 | Transit from port to site | OFFSHORE | Working | 11 |  | 19 | 1 |  | Standalone |  | 7.8 | 1422.2 | 1325.7
2030-05-30 06:12 | 2030-05-30 06:42 | 0.5 | DP field check | OFFSHORE | Working | 11 |  | 20 | 1 |  | Standalone |  | 0.75 | 1422.7 | 1325.2
2030-05-30 06:42 | 2030-05-30 07:42 | 1 | Transit to next foundation | OFFSHORE | Working | 11 | 21 | 21 | 1 |  | Standalone |  | 1.5 | 1423.7 | 1324.2
2030-05-30 07:42 | 2030-05-30 08:42 | 1 | Positioning at WTG location | OFFSHORE | Working | 11 | 21 | 22 | 1 |  | Standalone |  | 1.5 | 1424.7 | 1323.2
2030-05-30 08:42 | 2030-05-30 12:42 | 4 | Preload and jacking up at site | OFFSHORE | Working | 11 | 21 | 23 | 1 |  | Standalone |  | 6 | 1428.7 | 1319.2
2030-05-30 12:42 | 2030-05-30 15:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 11 | 21 | 24 | 1 |  | Standalone |  | 3 | 1431.7 | 1316.2
2030-05-30 15:42 | 2030-05-30 16:42 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 11 | 21 | 25 | 1 |  | Standalone |  | 1 | 1432.7 | 1315.2
2030-05-30 16:42 | 2030-05-30 18:42 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 11 | 21 | 26 | 1 |  | Standalone |  | 2 | 1434.7 | 1313.2
2030-05-30 18:42 | 2030-05-30 19:42 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 11 | 21 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1435.7 | 1312.2
2030-05-30 19:42 | 2030-05-30 23:12 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 21 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1439.2 | 1308.7
2030-05-30 23:12 | 2030-05-30 23:42 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 11 | 21 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1439.7 | 1308.2
2030-05-30 23:42 | 2030-05-31 00:12 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 11 | 21 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1440.2 | 1307.7
2030-05-31 00:12 | 2030-05-31 02:27 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 21 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1442.45 | 1305.45
2030-05-31 02:27 | 2030-05-31 02:57 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 11 | 21 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1442.95 | 1304.95
2030-05-31 02:57 | 2030-05-31 03:27 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 11 | 21 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1443.45 | 1304.45
2030-05-31 03:27 | 2030-05-31 05:12 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 21 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1445.2 | 1302.7
2030-05-31 05:12 | 2030-05-31 06:42 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 11 | 21 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1446.7 | 1301.2
2030-05-31 06:42 | 2030-05-31 08:27 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 21 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1448.45 | 1299.45
2030-05-31 08:27 | 2030-05-31 09:57 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 11 | 21 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1449.95 | 1297.95
2030-05-31 09:57 | 2030-05-31 11:42 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 21 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1451.7 | 1296.2
2030-05-31 11:42 | 2030-05-31 13:12 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 11 | 21 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1453.2 | 1294.7
2030-05-31 13:12 | 2030-05-31 14:12 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 11 | 21 | 40 | 1 |  | Standalone |  | 1 | 1454.2 | 1293.7
2030-05-31 14:12 | 2030-05-31 15:12 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 11 | 21 | 41 | 1 |  | Standalone |  | 1 | 1455.2 | 1292.7
2030-05-31 15:12 | 2030-05-31 18:12 | 3 | Turbine general completion works | OFFSHORE | Working | 11 | 21 | 42 | 1 |  | Standalone |  | 3 | 1458.2 | 1289.7
2030-05-31 18:12 | 2030-05-31 21:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 11 | 21 | 43 | 1 |  | Standalone |  | 3 | 1461.2 | 1286.7
2030-05-31 21:12 | 2030-05-31 23:12 | 2 | Jacking down at site | OFFSHORE | Working | 11 | 21 | 44 | 1 |  | Standalone |  | 3 | 1463.2 | 1284.7
2030-05-31 23:12 | 2030-06-01 00:12 | 1 | Transit to next foundation | OFFSHORE | Working | 11 | 22 | 21 | 1 |  | Standalone |  | 1.5 | 1464.2 | 1283.7
2030-06-01 00:12 | 2030-06-01 01:12 | 1 | Positioning at WTG location | OFFSHORE | Working | 11 | 22 | 22 | 1 |  | Standalone |  | 1.5 | 1465.2 | 1282.7
2030-06-01 01:12 | 2030-06-01 05:12 | 4 | Preload and jacking up at site | OFFSHORE | Working | 11 | 22 | 23 | 1 |  | Standalone |  | 6 | 1469.2 | 1278.7
2030-06-01 05:12 | 2030-06-01 08:12 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 11 | 22 | 24 | 1 |  | Standalone |  | 3 | 1472.2 | 1275.7
2030-06-01 08:12 | 2030-06-01 09:12 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 11 | 22 | 25 | 1 |  | Standalone |  | 1 | 1473.2 | 1274.7
2030-06-01 09:12 | 2030-06-01 11:12 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 11 | 22 | 26 | 1 |  | Standalone |  | 2 | 1475.2 | 1272.7
2030-06-01 11:12 | 2030-06-01 12:12 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 11 | 22 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1476.2 | 1271.7
2030-06-01 12:12 | 2030-06-01 15:42 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 22 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1479.7 | 1268.2
2030-06-01 15:42 | 2030-06-01 16:12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 11 | 22 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1480.2 | 1267.7
2030-06-01 16:12 | 2030-06-01 16:42 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 11 | 22 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1480.7 | 1267.2
2030-06-01 16:42 | 2030-06-01 18:57 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 22 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1482.95 | 1264.95
2030-06-01 18:57 | 2030-06-01 19:27 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 11 | 22 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1483.45 | 1264.45
2030-06-01 19:27 | 2030-06-01 19:57 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 11 | 22 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1483.95 | 1263.95
2030-06-01 19:57 | 2030-06-01 21:42 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 22 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1485.7 | 1262.2
2030-06-01 21:42 | 2030-06-01 23:12 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 11 | 22 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1487.2 | 1260.7
2030-06-01 23:12 | 2030-06-02 00:57 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 22 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1488.95 | 1258.95
2030-06-02 00:57 | 2030-06-02 02:27 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 11 | 22 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1490.45 | 1257.45
2030-06-02 02:27 | 2030-06-02 04:12 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 11 | 22 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1492.2 | 1255.7
2030-06-02 04:12 | 2030-06-02 05:42 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 11 | 22 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1493.7 | 1254.2
2030-06-02 05:42 | 2030-06-02 06:42 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 11 | 22 | 40 | 1 |  | Standalone |  | 1 | 1494.7 | 1253.2
2030-06-02 06:42 | 2030-06-02 07:42 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 11 | 22 | 41 | 1 |  | Standalone |  | 1 | 1495.7 | 1252.2
2030-06-02 07:42 | 2030-06-02 10:42 | 3 | Turbine general completion works | OFFSHORE | Working | 11 | 22 | 42 | 1 |  | Standalone |  | 3 | 1498.7 | 1249.2
2030-06-02 10:42 | 2030-06-02 13:42 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 11 | 22 | 43 | 1 |  | Standalone |  | 3 | 1501.7 | 1246.2
2030-06-02 13:42 | 2030-06-02 15:42 | 2 | Jacking down at site | OFFSHORE | Working | 11 | 22 | 44 | 1 |  | Standalone |  | 3 | 1503.7 | 1244.2
2030-06-02 15:42 | 2030-06-02 20:54 | 5.2 | Transit from site to port | OFFSHORE | Working | 11 |  | 45 | 1 |  | Standalone |  | 7.8 | 1508.9 | 1239
2030-06-02 20:54 | 2030-06-02 21:54 | 1 | Port maneuvering | OFFSHORE | Working | 12 |  | 1 | 1 |  | Standalone |  | 1.5 | 1509.9 | 1238
2030-06-02 21:54 | 2030-06-02 23:54 | 2 | Preload and jacking up at port | OFFSHORE | Working | 12 |  | 2 | 1 |  | Standalone |  | 3 | 1511.9 | 1236
2030-06-02 23:54 | 2030-06-03 02:54 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 12 |  | 3 | 1 |  | Standalone |  | 3 | 1514.9 | 1233
2030-06-03 02:54 | 2030-06-03 03:54 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 12 |  | 4 | 1 |  | Standalone |  | 1 | 1515.9 | 1232
2030-06-03 03:54 | 2030-06-03 06:09 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 12 |  | 5 | 1 |  | Standalone |  | 3.375 | 1518.15 | 1229.75
2030-06-03 06:09 | 2030-06-03 08:24 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 12 |  | 6 | 1 |  | Standalone |  | 3.375 | 1520.4 | 1227.5
2030-06-03 08:24 | 2030-06-03 09:54 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 12 |  | 7 | 1 |  | Standalone |  | 2.25 | 1521.9 | 1226
2030-06-03 09:54 | 2030-06-03 11:24 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 12 |  | 8 | 1 |  | Standalone |  | 2.25 | 1523.4 | 1224.5
2030-06-03 11:24 | 2030-06-03 12:54 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 12 |  | 9 | 1 |  | Standalone |  | 2.25 | 1524.9 | 1223
2030-06-03 12:54 | 2030-06-03 13:54 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 12 |  | 10 | 1 |  | Standalone |  | 1 | 1525.9 | 1222
2030-06-03 13:54 | 2030-06-03 16:09 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 12 |  | 11 | 1 |  | Standalone |  | 3.375 | 1528.15 | 1219.75
2030-06-03 16:09 | 2030-06-03 18:24 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 12 |  | 12 | 1 |  | Standalone |  | 3.375 | 1530.4 | 1217.5
2030-06-03 18:24 | 2030-06-03 19:54 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 12 |  | 13 | 1 |  | Standalone |  | 2.25 | 1531.9 | 1216
2030-06-03 19:54 | 2030-06-03 21:24 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 12 |  | 14 | 1 |  | Standalone |  | 2.25 | 1533.4 | 1214.5
2030-06-03 21:24 | 2030-06-03 22:54 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 12 |  | 15 | 1 |  | Standalone |  | 2.25 | 1534.9 | 1213
2030-06-03 22:54 | 2030-06-04 01:54 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 12 |  | 16 | 1 |  | Standalone |  | 3 | 1537.9 | 1210
2030-06-04 01:54 | 2030-06-04 03:54 | 2 | Jacking down at port | OFFSHORE | Working | 12 |  | 17 | 1 |  | Standalone |  | 3 | 1539.9 | 1208
2030-06-04 03:54 | 2030-06-04 04:54 | 1 | Port maneuvering | OFFSHORE | Working | 12 |  | 18 | 1 |  | Standalone |  | 1.5 | 1540.9 | 1207
2030-06-04 04:54 | 2030-06-04 10:06 | 5.2 | Transit from port to site | OFFSHORE | Working | 12 |  | 19 | 1 |  | Standalone |  | 7.8 | 1546.1 | 1201.8
2030-06-04 10:06 | 2030-06-04 10:36 | 0.5 | DP field check | OFFSHORE | Working | 12 |  | 20 | 1 |  | Standalone |  | 0.75 | 1546.6 | 1201.3
2030-06-04 10:36 | 2030-06-04 11:36 | 1 | Transit to next foundation | OFFSHORE | Working | 12 | 23 | 21 | 1 |  | Standalone |  | 1.5 | 1547.6 | 1200.3
2030-06-04 11:36 | 2030-06-04 12:36 | 1 | Positioning at WTG location | OFFSHORE | Working | 12 | 23 | 22 | 1 |  | Standalone |  | 1.5 | 1548.6 | 1199.3
2030-06-04 12:36 | 2030-06-04 16:36 | 4 | Preload and jacking up at site | OFFSHORE | Working | 12 | 23 | 23 | 1 |  | Standalone |  | 6 | 1552.6 | 1195.3
2030-06-04 16:36 | 2030-06-04 19:36 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 12 | 23 | 24 | 1 |  | Standalone |  | 3 | 1555.6 | 1192.3
2030-06-04 19:36 | 2030-06-04 20:36 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 12 | 23 | 25 | 1 |  | Standalone |  | 1 | 1556.6 | 1191.3
2030-06-04 20:36 | 2030-06-04 22:36 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 12 | 23 | 26 | 1 |  | Standalone |  | 2 | 1558.6 | 1189.3
2030-06-04 22:36 | 2030-06-04 23:36 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 12 | 23 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1559.6 | 1188.3
2030-06-04 23:36 | 2030-06-05 03:06 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 23 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1563.1 | 1184.8
2030-06-05 03:06 | 2030-06-05 03:36 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 12 | 23 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1563.6 | 1184.3
2030-06-05 03:36 | 2030-06-05 04:06 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 12 | 23 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1564.1 | 1183.8
2030-06-05 04:06 | 2030-06-05 06:21 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 23 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1566.35 | 1181.55
2030-06-05 06:21 | 2030-06-05 06:51 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 12 | 23 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1566.85 | 1181.05
2030-06-05 06:51 | 2030-06-05 07:21 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 12 | 23 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1567.35 | 1180.55
2030-06-05 07:21 | 2030-06-05 09:06 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 23 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1569.1 | 1178.8
2030-06-05 09:06 | 2030-06-05 10:36 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 12 | 23 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1570.6 | 1177.3
2030-06-05 10:36 | 2030-06-05 12:21 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 23 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1572.35 | 1175.55
2030-06-05 12:21 | 2030-06-05 13:51 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 12 | 23 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1573.85 | 1174.05
2030-06-05 13:51 | 2030-06-05 15:36 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 23 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1575.6 | 1172.3
2030-06-05 15:36 | 2030-06-05 17:06 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 12 | 23 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1577.1 | 1170.8
2030-06-05 17:06 | 2030-06-05 18:06 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 12 | 23 | 40 | 1 |  | Standalone |  | 1 | 1578.1 | 1169.8
2030-06-05 18:06 | 2030-06-05 19:06 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 12 | 23 | 41 | 1 |  | Standalone |  | 1 | 1579.1 | 1168.8
2030-06-05 19:06 | 2030-06-05 22:06 | 3 | Turbine general completion works | OFFSHORE | Working | 12 | 23 | 42 | 1 |  | Standalone |  | 3 | 1582.1 | 1165.8
2030-06-05 22:06 | 2030-06-06 01:06 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 12 | 23 | 43 | 1 |  | Standalone |  | 3 | 1585.1 | 1162.8
2030-06-06 01:06 | 2030-06-06 03:06 | 2 | Jacking down at site | OFFSHORE | Working | 12 | 23 | 44 | 1 |  | Standalone |  | 3 | 1587.1 | 1160.8
2030-06-06 03:06 | 2030-06-06 04:06 | 1 | Transit to next foundation | OFFSHORE | Working | 12 | 24 | 21 | 1 |  | Standalone |  | 1.5 | 1588.1 | 1159.8
2030-06-06 04:06 | 2030-06-06 05:06 | 1 | Positioning at WTG location | OFFSHORE | Working | 12 | 24 | 22 | 1 |  | Standalone |  | 1.5 | 1589.1 | 1158.8
2030-06-06 05:06 | 2030-06-06 09:06 | 4 | Preload and jacking up at site | OFFSHORE | Working | 12 | 24 | 23 | 1 |  | Standalone |  | 6 | 1593.1 | 1154.8
2030-06-06 09:06 | 2030-06-06 12:06 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 12 | 24 | 24 | 1 |  | Standalone |  | 3 | 1596.1 | 1151.8
2030-06-06 12:06 | 2030-06-06 13:06 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 12 | 24 | 25 | 1 |  | Standalone |  | 1 | 1597.1 | 1150.8
2030-06-06 13:06 | 2030-06-06 15:06 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 12 | 24 | 26 | 1 |  | Standalone |  | 2 | 1599.1 | 1148.8
2030-06-06 15:06 | 2030-06-06 16:06 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 12 | 24 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1600.1 | 1147.8
2030-06-06 16:06 | 2030-06-06 19:36 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 24 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1603.6 | 1144.3
2030-06-06 19:36 | 2030-06-06 20:06 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 12 | 24 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1604.1 | 1143.8
2030-06-06 20:06 | 2030-06-06 20:36 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 12 | 24 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1604.6 | 1143.3
2030-06-06 20:36 | 2030-06-06 22:51 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 24 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1606.85 | 1141.05
2030-06-06 22:51 | 2030-06-06 23:21 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 12 | 24 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1607.35 | 1140.55
2030-06-06 23:21 | 2030-06-06 23:51 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 12 | 24 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1607.85 | 1140.05
2030-06-06 23:51 | 2030-06-07 01:36 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 24 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1609.6 | 1138.3
2030-06-07 01:36 | 2030-06-07 03:06 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 12 | 24 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1611.1 | 1136.8
2030-06-07 03:06 | 2030-06-07 04:51 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 24 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1612.85 | 1135.05
2030-06-07 04:51 | 2030-06-07 06:21 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 12 | 24 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1614.35 | 1133.55
2030-06-07 06:21 | 2030-06-07 08:06 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 12 | 24 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1616.1 | 1131.8
2030-06-07 08:06 | 2030-06-07 09:36 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 12 | 24 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1617.6 | 1130.3
2030-06-07 09:36 | 2030-06-07 10:36 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 12 | 24 | 40 | 1 |  | Standalone |  | 1 | 1618.6 | 1129.3
2030-06-07 10:36 | 2030-06-07 11:36 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 12 | 24 | 41 | 1 |  | Standalone |  | 1 | 1619.6 | 1128.3
2030-06-07 11:36 | 2030-06-07 14:36 | 3 | Turbine general completion works | OFFSHORE | Working | 12 | 24 | 42 | 1 |  | Standalone |  | 3 | 1622.6 | 1125.3
2030-06-07 14:36 | 2030-06-07 17:36 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 12 | 24 | 43 | 1 |  | Standalone |  | 3 | 1625.6 | 1122.3
2030-06-07 17:36 | 2030-06-07 19:36 | 2 | Jacking down at site | OFFSHORE | Working | 12 | 24 | 44 | 1 |  | Standalone |  | 3 | 1627.6 | 1120.3
2030-06-07 19:36 | 2030-06-08 00:48 | 5.2 | Transit from site to port | OFFSHORE | Working | 12 |  | 45 | 1 |  | Standalone |  | 7.8 | 1632.8 | 1115.1
2030-06-08 00:48 | 2030-06-08 01:48 | 1 | Port maneuvering | OFFSHORE | Working | 13 |  | 1 | 1 |  | Standalone |  | 1.5 | 1633.8 | 1114.1
2030-06-08 01:48 | 2030-06-08 03:48 | 2 | Preload and jacking up at port | OFFSHORE | Working | 13 |  | 2 | 1 |  | Standalone |  | 3 | 1635.8 | 1112.1
2030-06-08 03:48 | 2030-06-08 06:48 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 13 |  | 3 | 1 |  | Standalone |  | 3 | 1638.8 | 1109.1
2030-06-08 06:48 | 2030-06-08 07:48 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 13 |  | 4 | 1 |  | Standalone |  | 1 | 1639.8 | 1108.1
2030-06-08 07:48 | 2030-06-08 10:03 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 13 |  | 5 | 1 |  | Standalone |  | 3.375 | 1642.05 | 1105.85
2030-06-08 10:03 | 2030-06-08 12:18 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 13 |  | 6 | 1 |  | Standalone |  | 3.375 | 1644.3 | 1103.6
2030-06-08 12:18 | 2030-06-08 13:48 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 13 |  | 7 | 1 |  | Standalone |  | 2.25 | 1645.8 | 1102.1
2030-06-08 13:48 | 2030-06-08 15:18 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 13 |  | 8 | 1 |  | Standalone |  | 2.25 | 1647.3 | 1100.6
2030-06-08 15:18 | 2030-06-08 16:48 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 13 |  | 9 | 1 |  | Standalone |  | 2.25 | 1648.8 | 1099.1
2030-06-08 16:48 | 2030-06-08 17:48 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 13 |  | 10 | 1 |  | Standalone |  | 1 | 1649.8 | 1098.1
2030-06-08 17:48 | 2030-06-08 20:03 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 13 |  | 11 | 1 |  | Standalone |  | 3.375 | 1652.05 | 1095.85
2030-06-08 20:03 | 2030-06-08 22:18 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 13 |  | 12 | 1 |  | Standalone |  | 3.375 | 1654.3 | 1093.6
2030-06-08 22:18 | 2030-06-08 23:48 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 13 |  | 13 | 1 |  | Standalone |  | 2.25 | 1655.8 | 1092.1
2030-06-08 23:48 | 2030-06-09 01:18 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 13 |  | 14 | 1 |  | Standalone |  | 2.25 | 1657.3 | 1090.6
2030-06-09 01:18 | 2030-06-09 02:48 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 13 |  | 15 | 1 |  | Standalone |  | 2.25 | 1658.8 | 1089.1
2030-06-09 02:48 | 2030-06-09 05:48 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 13 |  | 16 | 1 |  | Standalone |  | 3 | 1661.8 | 1086.1
2030-06-09 05:48 | 2030-06-09 07:48 | 2 | Jacking down at port | OFFSHORE | Working | 13 |  | 17 | 1 |  | Standalone |  | 3 | 1663.8 | 1084.1
2030-06-09 07:48 | 2030-06-09 08:48 | 1 | Port maneuvering | OFFSHORE | Working | 13 |  | 18 | 1 |  | Standalone |  | 1.5 | 1664.8 | 1083.1
2030-06-09 08:48 | 2030-06-09 14:00 | 5.2 | Transit from port to site | OFFSHORE | Working | 13 |  | 19 | 1 |  | Standalone |  | 7.8 | 1670 | 1077.9
2030-06-09 14:00 | 2030-06-09 14:30 | 0.5 | DP field check | OFFSHORE | Working | 13 |  | 20 | 1 |  | Standalone |  | 0.75 | 1670.5 | 1077.4
2030-06-09 14:30 | 2030-06-09 15:30 | 1 | Transit to next foundation | OFFSHORE | Working | 13 | 25 | 21 | 1 |  | Standalone |  | 1.5 | 1671.5 | 1076.4
2030-06-09 15:30 | 2030-06-09 16:30 | 1 | Positioning at WTG location | OFFSHORE | Working | 13 | 25 | 22 | 1 |  | Standalone |  | 1.5 | 1672.5 | 1075.4
2030-06-09 16:30 | 2030-06-09 20:30 | 4 | Preload and jacking up at site | OFFSHORE | Working | 13 | 25 | 23 | 1 |  | Standalone |  | 6 | 1676.5 | 1071.4
2030-06-09 20:30 | 2030-06-09 23:30 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 13 | 25 | 24 | 1 |  | Standalone |  | 3 | 1679.5 | 1068.4
2030-06-09 23:30 | 2030-06-10 00:30 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 13 | 25 | 25 | 1 |  | Standalone |  | 1 | 1680.5 | 1067.4
2030-06-10 00:30 | 2030-06-10 02:30 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 13 | 25 | 26 | 1 |  | Standalone |  | 2 | 1682.5 | 1065.4
2030-06-10 02:30 | 2030-06-10 03:30 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 13 | 25 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1683.5 | 1064.4
2030-06-10 03:30 | 2030-06-10 07:00 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 25 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1687 | 1060.9
2030-06-10 07:00 | 2030-06-10 07:30 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 13 | 25 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1687.5 | 1060.4
2030-06-10 07:30 | 2030-06-10 08:00 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 13 | 25 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1688 | 1059.9
2030-06-10 08:00 | 2030-06-10 10:15 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 25 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1690.25 | 1057.65
2030-06-10 10:15 | 2030-06-10 10:45 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 13 | 25 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1690.75 | 1057.15
2030-06-10 10:45 | 2030-06-10 11:15 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 13 | 25 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1691.25 | 1056.65
2030-06-10 11:15 | 2030-06-10 13:00 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 25 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1693 | 1054.9
2030-06-10 13:00 | 2030-06-10 14:30 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 13 | 25 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1694.5 | 1053.4
2030-06-10 14:30 | 2030-06-10 16:15 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 25 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1696.25 | 1051.65
2030-06-10 16:15 | 2030-06-10 17:45 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 13 | 25 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1697.75 | 1050.15
2030-06-10 17:45 | 2030-06-10 19:30 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 25 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1699.5 | 1048.4
2030-06-10 19:30 | 2030-06-10 21:00 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 13 | 25 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1701 | 1046.9
2030-06-10 21:00 | 2030-06-10 22:00 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 13 | 25 | 40 | 1 |  | Standalone |  | 1 | 1702 | 1045.9
2030-06-10 22:00 | 2030-06-10 23:00 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 13 | 25 | 41 | 1 |  | Standalone |  | 1 | 1703 | 1044.9
2030-06-10 23:00 | 2030-06-11 02:00 | 3 | Turbine general completion works | OFFSHORE | Working | 13 | 25 | 42 | 1 |  | Standalone |  | 3 | 1706 | 1041.9
2030-06-11 02:00 | 2030-06-11 05:00 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 13 | 25 | 43 | 1 |  | Standalone |  | 3 | 1709 | 1038.9
2030-06-11 05:00 | 2030-06-11 07:00 | 2 | Jacking down at site | OFFSHORE | Working | 13 | 25 | 44 | 1 |  | Standalone |  | 3 | 1711 | 1036.9
2030-06-11 07:00 | 2030-06-11 08:00 | 1 | Transit to next foundation | OFFSHORE | Working | 13 | 26 | 21 | 1 |  | Standalone |  | 1.5 | 1712 | 1035.9
2030-06-11 08:00 | 2030-06-11 09:00 | 1 | Positioning at WTG location | OFFSHORE | Working | 13 | 26 | 22 | 1 |  | Standalone |  | 1.5 | 1713 | 1034.9
2030-06-11 09:00 | 2030-06-11 13:00 | 4 | Preload and jacking up at site | OFFSHORE | Working | 13 | 26 | 23 | 1 |  | Standalone |  | 6 | 1717 | 1030.9
2030-06-11 13:00 | 2030-06-11 16:00 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 13 | 26 | 24 | 1 |  | Standalone |  | 3 | 1720 | 1027.9
2030-06-11 16:00 | 2030-06-11 17:00 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 13 | 26 | 25 | 1 |  | Standalone |  | 1 | 1721 | 1026.9
2030-06-11 17:00 | 2030-06-11 19:00 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 13 | 26 | 26 | 1 |  | Standalone |  | 2 | 1723 | 1024.9
2030-06-11 19:00 | 2030-06-11 20:00 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 13 | 26 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1724 | 1023.9
2030-06-11 20:00 | 2030-06-11 23:30 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 26 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1727.5 | 1020.4
2030-06-11 23:30 | 2030-06-12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 13 | 26 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1728 | 1019.9
2030-06-12 | 2030-06-12 00:30 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 13 | 26 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1728.5 | 1019.4
2030-06-12 00:30 | 2030-06-12 02:45 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 26 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1730.75 | 1017.15
2030-06-12 02:45 | 2030-06-12 03:15 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 13 | 26 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1731.25 | 1016.65
2030-06-12 03:15 | 2030-06-12 03:45 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 13 | 26 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1731.75 | 1016.15
2030-06-12 03:45 | 2030-06-12 05:30 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 26 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1733.5 | 1014.4
2030-06-12 05:30 | 2030-06-12 07:00 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 13 | 26 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1735 | 1012.9
2030-06-12 07:00 | 2030-06-12 08:45 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 26 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1736.75 | 1011.15
2030-06-12 08:45 | 2030-06-12 10:15 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 13 | 26 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1738.25 | 1009.65
2030-06-12 10:15 | 2030-06-12 12:00 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 13 | 26 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1740 | 1007.9
2030-06-12 12:00 | 2030-06-12 13:30 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 13 | 26 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1741.5 | 1006.4
2030-06-12 13:30 | 2030-06-12 14:30 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 13 | 26 | 40 | 1 |  | Standalone |  | 1 | 1742.5 | 1005.4
2030-06-12 14:30 | 2030-06-12 15:30 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 13 | 26 | 41 | 1 |  | Standalone |  | 1 | 1743.5 | 1004.4
2030-06-12 15:30 | 2030-06-12 18:30 | 3 | Turbine general completion works | OFFSHORE | Working | 13 | 26 | 42 | 1 |  | Standalone |  | 3 | 1746.5 | 1001.4
2030-06-12 18:30 | 2030-06-12 21:30 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 13 | 26 | 43 | 1 |  | Standalone |  | 3 | 1749.5 | 998.4
2030-06-12 21:30 | 2030-06-12 23:30 | 2 | Jacking down at site | OFFSHORE | Working | 13 | 26 | 44 | 1 |  | Standalone |  | 3 | 1751.5 | 996.4
2030-06-12 23:30 | 2030-06-13 04:42 | 5.2 | Transit from site to port | OFFSHORE | Working | 13 |  | 45 | 1 |  | Standalone |  | 7.8 | 1756.7 | 991.2
2030-06-13 04:42 | 2030-06-13 05:42 | 1 | Port maneuvering | OFFSHORE | Working | 14 |  | 1 | 1 |  | Standalone |  | 1.5 | 1757.7 | 990.2
2030-06-13 05:42 | 2030-06-13 07:42 | 2 | Preload and jacking up at port | OFFSHORE | Working | 14 |  | 2 | 1 |  | Standalone |  | 3 | 1759.7 | 988.2
2030-06-13 07:42 | 2030-06-13 10:42 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 14 |  | 3 | 1 |  | Standalone |  | 3 | 1762.7 | 985.2
2030-06-13 10:42 | 2030-06-13 11:42 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 14 |  | 4 | 1 |  | Standalone |  | 1 | 1763.7 | 984.2
2030-06-13 11:42 | 2030-06-13 13:57 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 14 |  | 5 | 1 |  | Standalone |  | 3.375 | 1765.95 | 981.95
2030-06-13 13:57 | 2030-06-13 16:12 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 14 |  | 6 | 1 |  | Standalone |  | 3.375 | 1768.2 | 979.7
2030-06-13 16:12 | 2030-06-13 17:42 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 14 |  | 7 | 1 |  | Standalone |  | 2.25 | 1769.7 | 978.2
2030-06-13 17:42 | 2030-06-13 19:12 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 14 |  | 8 | 1 |  | Standalone |  | 2.25 | 1771.2 | 976.7
2030-06-13 19:12 | 2030-06-13 20:42 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 14 |  | 9 | 1 |  | Standalone |  | 2.25 | 1772.7 | 975.2
2030-06-13 20:42 | 2030-06-13 21:42 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 14 |  | 10 | 1 |  | Standalone |  | 1 | 1773.7 | 974.2
2030-06-13 21:42 | 2030-06-13 23:57 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 14 |  | 11 | 1 |  | Standalone |  | 3.375 | 1775.95 | 971.95
2030-06-13 23:57 | 2030-06-14 02:12 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 14 |  | 12 | 1 |  | Standalone |  | 3.375 | 1778.2 | 969.7
2030-06-14 02:12 | 2030-06-14 03:42 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 14 |  | 13 | 1 |  | Standalone |  | 2.25 | 1779.7 | 968.2
2030-06-14 03:42 | 2030-06-14 05:12 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 14 |  | 14 | 1 |  | Standalone |  | 2.25 | 1781.2 | 966.7
2030-06-14 05:12 | 2030-06-14 06:42 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 14 |  | 15 | 1 |  | Standalone |  | 2.25 | 1782.7 | 965.2
2030-06-14 06:42 | 2030-06-14 09:42 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 14 |  | 16 | 1 |  | Standalone |  | 3 | 1785.7 | 962.2
2030-06-14 09:42 | 2030-06-14 11:42 | 2 | Jacking down at port | OFFSHORE | Working | 14 |  | 17 | 1 |  | Standalone |  | 3 | 1787.7 | 960.2
2030-06-14 11:42 | 2030-06-14 12:42 | 1 | Port maneuvering | OFFSHORE | Working | 14 |  | 18 | 1 |  | Standalone |  | 1.5 | 1788.7 | 959.2
2030-06-14 12:42 | 2030-06-14 17:54 | 5.2 | Transit from port to site | OFFSHORE | Working | 14 |  | 19 | 1 |  | Standalone |  | 7.8 | 1793.9 | 954
2030-06-14 17:54 | 2030-06-14 18:24 | 0.5 | DP field check | OFFSHORE | Working | 14 |  | 20 | 1 |  | Standalone |  | 0.75 | 1794.4 | 953.5
2030-06-14 18:24 | 2030-06-14 19:24 | 1 | Transit to next foundation | OFFSHORE | Working | 14 | 27 | 21 | 1 |  | Standalone |  | 1.5 | 1795.4 | 952.5
2030-06-14 19:24 | 2030-06-14 20:24 | 1 | Positioning at WTG location | OFFSHORE | Working | 14 | 27 | 22 | 1 |  | Standalone |  | 1.5 | 1796.4 | 951.5
2030-06-14 20:24 | 2030-06-15 00:24 | 4 | Preload and jacking up at site | OFFSHORE | Working | 14 | 27 | 23 | 1 |  | Standalone |  | 6 | 1800.4 | 947.5
2030-06-15 00:24 | 2030-06-15 03:24 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 14 | 27 | 24 | 1 |  | Standalone |  | 3 | 1803.4 | 944.5
2030-06-15 03:24 | 2030-06-15 04:24 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 14 | 27 | 25 | 1 |  | Standalone |  | 1 | 1804.4 | 943.5
2030-06-15 04:24 | 2030-06-15 06:24 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 14 | 27 | 26 | 1 |  | Standalone |  | 2 | 1806.4 | 941.5
2030-06-15 06:24 | 2030-06-15 07:24 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 14 | 27 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1807.4 | 940.5
2030-06-15 07:24 | 2030-06-15 10:54 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 27 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1810.9 | 937
2030-06-15 10:54 | 2030-06-15 11:24 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 14 | 27 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1811.4 | 936.5
2030-06-15 11:24 | 2030-06-15 11:54 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 14 | 27 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1811.9 | 936
2030-06-15 11:54 | 2030-06-15 14:09 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 27 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1814.15 | 933.75
2030-06-15 14:09 | 2030-06-15 14:39 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 14 | 27 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1814.65 | 933.25
2030-06-15 14:39 | 2030-06-15 15:09 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 14 | 27 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1815.15 | 932.75
2030-06-15 15:09 | 2030-06-15 16:54 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 27 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1816.9 | 931
2030-06-15 16:54 | 2030-06-15 18:24 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 14 | 27 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1818.4 | 929.5
2030-06-15 18:24 | 2030-06-15 20:09 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 27 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1820.15 | 927.75
2030-06-15 20:09 | 2030-06-15 21:39 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 14 | 27 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1821.65 | 926.25
2030-06-15 21:39 | 2030-06-15 23:24 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 27 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1823.4 | 924.5
2030-06-15 23:24 | 2030-06-16 00:54 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 14 | 27 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1824.9 | 923
2030-06-16 00:54 | 2030-06-16 01:54 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 14 | 27 | 40 | 1 |  | Standalone |  | 1 | 1825.9 | 922
2030-06-16 01:54 | 2030-06-16 02:54 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 14 | 27 | 41 | 1 |  | Standalone |  | 1 | 1826.9 | 921
2030-06-16 02:54 | 2030-06-16 05:54 | 3 | Turbine general completion works | OFFSHORE | Working | 14 | 27 | 42 | 1 |  | Standalone |  | 3 | 1829.9 | 918
2030-06-16 05:54 | 2030-06-16 08:54 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 14 | 27 | 43 | 1 |  | Standalone |  | 3 | 1832.9 | 915
2030-06-16 08:54 | 2030-06-16 10:54 | 2 | Jacking down at site | OFFSHORE | Working | 14 | 27 | 44 | 1 |  | Standalone |  | 3 | 1834.9 | 913
2030-06-16 10:54 | 2030-06-16 11:54 | 1 | Transit to next foundation | OFFSHORE | Working | 14 | 28 | 21 | 1 |  | Standalone |  | 1.5 | 1835.9 | 912
2030-06-16 11:54 | 2030-06-16 12:54 | 1 | Positioning at WTG location | OFFSHORE | Working | 14 | 28 | 22 | 1 |  | Standalone |  | 1.5 | 1836.9 | 911
2030-06-16 12:54 | 2030-06-16 16:54 | 4 | Preload and jacking up at site | OFFSHORE | Working | 14 | 28 | 23 | 1 |  | Standalone |  | 6 | 1840.9 | 907
2030-06-16 16:54 | 2030-06-16 19:54 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 14 | 28 | 24 | 1 |  | Standalone |  | 3 | 1843.9 | 904
2030-06-16 19:54 | 2030-06-16 20:54 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 14 | 28 | 25 | 1 |  | Standalone |  | 1 | 1844.9 | 903
2030-06-16 20:54 | 2030-06-16 22:54 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 14 | 28 | 26 | 1 |  | Standalone |  | 2 | 1846.9 | 901
2030-06-16 22:54 | 2030-06-16 23:54 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 14 | 28 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1847.9 | 900
2030-06-16 23:54 | 2030-06-17 03:24 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 28 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1851.4 | 896.5
2030-06-17 03:24 | 2030-06-17 03:54 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 14 | 28 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1851.9 | 896
2030-06-17 03:54 | 2030-06-17 04:24 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 14 | 28 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1852.4 | 895.5
2030-06-17 04:24 | 2030-06-17 06:39 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 28 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1854.65 | 893.25
2030-06-17 06:39 | 2030-06-17 07:09 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 14 | 28 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1855.15 | 892.75
2030-06-17 07:09 | 2030-06-17 07:39 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 14 | 28 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1855.65 | 892.25
2030-06-17 07:39 | 2030-06-17 09:24 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 28 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1857.4 | 890.5
2030-06-17 09:24 | 2030-06-17 10:54 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 14 | 28 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1858.9 | 889
2030-06-17 10:54 | 2030-06-17 12:39 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 28 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1860.65 | 887.25
2030-06-17 12:39 | 2030-06-17 14:09 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 14 | 28 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1862.15 | 885.75
2030-06-17 14:09 | 2030-06-17 15:54 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 14 | 28 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1863.9 | 884
2030-06-17 15:54 | 2030-06-17 17:24 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 14 | 28 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1865.4 | 882.5
2030-06-17 17:24 | 2030-06-17 18:24 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 14 | 28 | 40 | 1 |  | Standalone |  | 1 | 1866.4 | 881.5
2030-06-17 18:24 | 2030-06-17 19:24 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 14 | 28 | 41 | 1 |  | Standalone |  | 1 | 1867.4 | 880.5
2030-06-17 19:24 | 2030-06-17 22:24 | 3 | Turbine general completion works | OFFSHORE | Working | 14 | 28 | 42 | 1 |  | Standalone |  | 3 | 1870.4 | 877.5
2030-06-17 22:24 | 2030-06-18 01:24 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 14 | 28 | 43 | 1 |  | Standalone |  | 3 | 1873.4 | 874.5
2030-06-18 01:24 | 2030-06-18 03:24 | 2 | Jacking down at site | OFFSHORE | Working | 14 | 28 | 44 | 1 |  | Standalone |  | 3 | 1875.4 | 872.5
2030-06-18 03:24 | 2030-06-18 08:36 | 5.2 | Transit from site to port | OFFSHORE | Working | 14 |  | 45 | 1 |  | Standalone |  | 7.8 | 1880.6 | 867.3
2030-06-18 08:36 | 2030-06-18 09:36 | 1 | Port maneuvering | OFFSHORE | Working | 15 |  | 1 | 1 |  | Standalone |  | 1.5 | 1881.6 | 866.3
2030-06-18 09:36 | 2030-06-18 11:36 | 2 | Preload and jacking up at port | OFFSHORE | Working | 15 |  | 2 | 1 |  | Standalone |  | 3 | 1883.6 | 864.3
2030-06-18 11:36 | 2030-06-18 14:36 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 15 |  | 3 | 1 |  | Standalone |  | 3 | 1886.6 | 861.3
2030-06-18 14:36 | 2030-06-18 15:36 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 15 |  | 4 | 1 |  | Standalone |  | 1 | 1887.6 | 860.3
2030-06-18 15:36 | 2030-06-18 17:51 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 15 |  | 5 | 1 |  | Standalone |  | 3.375 | 1889.85 | 858.05
2030-06-18 17:51 | 2030-06-18 20:06 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 15 |  | 6 | 1 |  | Standalone |  | 3.375 | 1892.1 | 855.8
2030-06-18 20:06 | 2030-06-18 21:36 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 15 |  | 7 | 1 |  | Standalone |  | 2.25 | 1893.6 | 854.3
2030-06-18 21:36 | 2030-06-18 23:06 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 15 |  | 8 | 1 |  | Standalone |  | 2.25 | 1895.1 | 852.8
2030-06-18 23:06 | 2030-06-19 00:36 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 15 |  | 9 | 1 |  | Standalone |  | 2.25 | 1896.6 | 851.3
2030-06-19 00:36 | 2030-06-19 01:36 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 15 |  | 10 | 1 |  | Standalone |  | 1 | 1897.6 | 850.3
2030-06-19 01:36 | 2030-06-19 03:51 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 15 |  | 11 | 1 |  | Standalone |  | 3.375 | 1899.85 | 848.05
2030-06-19 03:51 | 2030-06-19 06:06 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 15 |  | 12 | 1 |  | Standalone |  | 3.375 | 1902.1 | 845.8
2030-06-19 06:06 | 2030-06-19 07:36 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 15 |  | 13 | 1 |  | Standalone |  | 2.25 | 1903.6 | 844.3
2030-06-19 07:36 | 2030-06-19 09:06 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 15 |  | 14 | 1 |  | Standalone |  | 2.25 | 1905.1 | 842.8
2030-06-19 09:06 | 2030-06-19 10:36 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 15 |  | 15 | 1 |  | Standalone |  | 2.25 | 1906.6 | 841.3
2030-06-19 10:36 | 2030-06-19 13:36 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 15 |  | 16 | 1 |  | Standalone |  | 3 | 1909.6 | 838.3
2030-06-19 13:36 | 2030-06-19 15:36 | 2 | Jacking down at port | OFFSHORE | Working | 15 |  | 17 | 1 |  | Standalone |  | 3 | 1911.6 | 836.3
2030-06-19 15:36 | 2030-06-19 16:36 | 1 | Port maneuvering | OFFSHORE | Working | 15 |  | 18 | 1 |  | Standalone |  | 1.5 | 1912.6 | 835.3
2030-06-19 16:36 | 2030-06-19 21:48 | 5.2 | Transit from port to site | OFFSHORE | Working | 15 |  | 19 | 1 |  | Standalone |  | 7.8 | 1917.8 | 830.1
2030-06-19 21:48 | 2030-06-19 22:18 | 0.5 | DP field check | OFFSHORE | Working | 15 |  | 20 | 1 |  | Standalone |  | 0.75 | 1918.3 | 829.6
2030-06-19 22:18 | 2030-06-19 23:18 | 1 | Transit to next foundation | OFFSHORE | Working | 15 | 29 | 21 | 1 |  | Standalone |  | 1.5 | 1919.3 | 828.6
2030-06-19 23:18 | 2030-06-20 00:18 | 1 | Positioning at WTG location | OFFSHORE | Working | 15 | 29 | 22 | 1 |  | Standalone |  | 1.5 | 1920.3 | 827.6
2030-06-20 00:18 | 2030-06-20 04:18 | 4 | Preload and jacking up at site | OFFSHORE | Working | 15 | 29 | 23 | 1 |  | Standalone |  | 6 | 1924.3 | 823.6
2030-06-20 04:18 | 2030-06-20 07:18 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 15 | 29 | 24 | 1 |  | Standalone |  | 3 | 1927.3 | 820.6
2030-06-20 07:18 | 2030-06-20 08:18 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 15 | 29 | 25 | 1 |  | Standalone |  | 1 | 1928.3 | 819.6
2030-06-20 08:18 | 2030-06-20 10:18 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 15 | 29 | 26 | 1 |  | Standalone |  | 2 | 1930.3 | 817.6
2030-06-20 10:18 | 2030-06-20 11:18 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 15 | 29 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1931.3 | 816.6
2030-06-20 11:18 | 2030-06-20 14:48 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 29 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1934.8 | 813.1
2030-06-20 14:48 | 2030-06-20 15:18 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 15 | 29 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1935.3 | 812.6
2030-06-20 15:18 | 2030-06-20 15:48 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 15 | 29 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1935.8 | 812.1
2030-06-20 15:48 | 2030-06-20 18:03 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 29 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1938.05 | 809.85
2030-06-20 18:03 | 2030-06-20 18:33 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 15 | 29 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1938.55 | 809.35
2030-06-20 18:33 | 2030-06-20 19:03 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 15 | 29 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1939.05 | 808.85
2030-06-20 19:03 | 2030-06-20 20:48 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 29 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1940.8 | 807.1
2030-06-20 20:48 | 2030-06-20 22:18 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 15 | 29 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1942.3 | 805.6
2030-06-20 22:18 | 2030-06-21 00:03 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 29 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1944.05 | 803.85
2030-06-21 00:03 | 2030-06-21 01:33 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 15 | 29 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1945.55 | 802.35
2030-06-21 01:33 | 2030-06-21 03:18 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 29 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1947.3 | 800.6
2030-06-21 03:18 | 2030-06-21 04:48 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 15 | 29 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1948.8 | 799.1
2030-06-21 04:48 | 2030-06-21 05:48 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 15 | 29 | 40 | 1 |  | Standalone |  | 1 | 1949.8 | 798.1
2030-06-21 05:48 | 2030-06-21 06:48 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 15 | 29 | 41 | 1 |  | Standalone |  | 1 | 1950.8 | 797.1
2030-06-21 06:48 | 2030-06-21 09:48 | 3 | Turbine general completion works | OFFSHORE | Working | 15 | 29 | 42 | 1 |  | Standalone |  | 3 | 1953.8 | 794.1
2030-06-21 09:48 | 2030-06-21 12:48 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 15 | 29 | 43 | 1 |  | Standalone |  | 3 | 1956.8 | 791.1
2030-06-21 12:48 | 2030-06-21 14:48 | 2 | Jacking down at site | OFFSHORE | Working | 15 | 29 | 44 | 1 |  | Standalone |  | 3 | 1958.8 | 789.1
2030-06-21 14:48 | 2030-06-21 15:48 | 1 | Transit to next foundation | OFFSHORE | Working | 15 | 30 | 21 | 1 |  | Standalone |  | 1.5 | 1959.8 | 788.1
2030-06-21 15:48 | 2030-06-21 16:48 | 1 | Positioning at WTG location | OFFSHORE | Working | 15 | 30 | 22 | 1 |  | Standalone |  | 1.5 | 1960.8 | 787.1
2030-06-21 16:48 | 2030-06-21 20:48 | 4 | Preload and jacking up at site | OFFSHORE | Working | 15 | 30 | 23 | 1 |  | Standalone |  | 6 | 1964.8 | 783.1
2030-06-21 20:48 | 2030-06-21 23:48 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 15 | 30 | 24 | 1 |  | Standalone |  | 3 | 1967.8 | 780.1
2030-06-21 23:48 | 2030-06-22 00:48 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 15 | 30 | 25 | 1 |  | Standalone |  | 1 | 1968.8 | 779.1
2030-06-22 00:48 | 2030-06-22 02:48 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 15 | 30 | 26 | 1 |  | Standalone |  | 2 | 1970.8 | 777.1
2030-06-22 02:48 | 2030-06-22 03:48 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 15 | 30 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 1971.8 | 776.1
2030-06-22 03:48 | 2030-06-22 07:18 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 30 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 1975.3 | 772.6
2030-06-22 07:18 | 2030-06-22 07:48 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 15 | 30 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 1975.8 | 772.1
2030-06-22 07:48 | 2030-06-22 08:18 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 15 | 30 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 1976.3 | 771.6
2030-06-22 08:18 | 2030-06-22 10:33 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 30 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 1978.55 | 769.35
2030-06-22 10:33 | 2030-06-22 11:03 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 15 | 30 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 1979.05 | 768.85
2030-06-22 11:03 | 2030-06-22 11:33 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 15 | 30 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 1979.55 | 768.35
2030-06-22 11:33 | 2030-06-22 13:18 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 30 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 1981.3 | 766.6
2030-06-22 13:18 | 2030-06-22 14:48 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 15 | 30 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 1982.8 | 765.1
2030-06-22 14:48 | 2030-06-22 16:33 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 30 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 1984.55 | 763.35
2030-06-22 16:33 | 2030-06-22 18:03 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 15 | 30 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 1986.05 | 761.85
2030-06-22 18:03 | 2030-06-22 19:48 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 15 | 30 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 1987.8 | 760.1
2030-06-22 19:48 | 2030-06-22 21:18 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 15 | 30 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 1989.3 | 758.6
2030-06-22 21:18 | 2030-06-22 22:18 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 15 | 30 | 40 | 1 |  | Standalone |  | 1 | 1990.3 | 757.6
2030-06-22 22:18 | 2030-06-22 23:18 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 15 | 30 | 41 | 1 |  | Standalone |  | 1 | 1991.3 | 756.6
2030-06-22 23:18 | 2030-06-23 02:18 | 3 | Turbine general completion works | OFFSHORE | Working | 15 | 30 | 42 | 1 |  | Standalone |  | 3 | 1994.3 | 753.6
2030-06-23 02:18 | 2030-06-23 05:18 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 15 | 30 | 43 | 1 |  | Standalone |  | 3 | 1997.3 | 750.6
2030-06-23 05:18 | 2030-06-23 07:18 | 2 | Jacking down at site | OFFSHORE | Working | 15 | 30 | 44 | 1 |  | Standalone |  | 3 | 1999.3 | 748.6
2030-06-23 07:18 | 2030-06-23 12:30 | 5.2 | Transit from site to port | OFFSHORE | Working | 15 |  | 45 | 1 |  | Standalone |  | 7.8 | 2004.5 | 743.4
2030-06-23 12:30 | 2030-06-23 13:30 | 1 | Port maneuvering | OFFSHORE | Working | 16 |  | 1 | 1 |  | Standalone |  | 1.5 | 2005.5 | 742.4
2030-06-23 13:30 | 2030-06-23 15:30 | 2 | Preload and jacking up at port | OFFSHORE | Working | 16 |  | 2 | 1 |  | Standalone |  | 3 | 2007.5 | 740.4
2030-06-23 15:30 | 2030-06-23 18:30 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 16 |  | 3 | 1 |  | Standalone |  | 3 | 2010.5 | 737.4
2030-06-23 18:30 | 2030-06-23 19:30 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 16 |  | 4 | 1 |  | Standalone |  | 1 | 2011.5 | 736.4
2030-06-23 19:30 | 2030-06-23 21:45 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 16 |  | 5 | 1 |  | Standalone |  | 3.375 | 2013.75 | 734.15
2030-06-23 21:45 | 2030-06-24 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 16 |  | 6 | 1 |  | Standalone |  | 3.375 | 2016 | 731.9
2030-06-24 | 2030-06-24 01:30 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 16 |  | 7 | 1 |  | Standalone |  | 2.25 | 2017.5 | 730.4
2030-06-24 01:30 | 2030-06-24 03:00 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 16 |  | 8 | 1 |  | Standalone |  | 2.25 | 2019 | 728.9
2030-06-24 03:00 | 2030-06-24 04:30 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 16 |  | 9 | 1 |  | Standalone |  | 2.25 | 2020.5 | 727.4
2030-06-24 04:30 | 2030-06-24 05:30 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 16 |  | 10 | 1 |  | Standalone |  | 1 | 2021.5 | 726.4
2030-06-24 05:30 | 2030-06-24 07:45 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 16 |  | 11 | 1 |  | Standalone |  | 3.375 | 2023.75 | 724.15
2030-06-24 07:45 | 2030-06-24 10:00 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 16 |  | 12 | 1 |  | Standalone |  | 3.375 | 2026 | 721.9
2030-06-24 10:00 | 2030-06-24 11:30 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 16 |  | 13 | 1 |  | Standalone |  | 2.25 | 2027.5 | 720.4
2030-06-24 11:30 | 2030-06-24 13:00 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 16 |  | 14 | 1 |  | Standalone |  | 2.25 | 2029 | 718.9
2030-06-24 13:00 | 2030-06-24 14:30 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 16 |  | 15 | 1 |  | Standalone |  | 2.25 | 2030.5 | 717.4
2030-06-24 14:30 | 2030-06-24 17:30 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 16 |  | 16 | 1 |  | Standalone |  | 3 | 2033.5 | 714.4
2030-06-24 17:30 | 2030-06-24 19:30 | 2 | Jacking down at port | OFFSHORE | Working | 16 |  | 17 | 1 |  | Standalone |  | 3 | 2035.5 | 712.4
2030-06-24 19:30 | 2030-06-24 20:30 | 1 | Port maneuvering | OFFSHORE | Working | 16 |  | 18 | 1 |  | Standalone |  | 1.5 | 2036.5 | 711.4
2030-06-24 20:30 | 2030-06-25 01:42 | 5.2 | Transit from port to site | OFFSHORE | Working | 16 |  | 19 | 1 |  | Standalone |  | 7.8 | 2041.7 | 706.2
2030-06-25 01:42 | 2030-06-25 02:12 | 0.5 | DP field check | OFFSHORE | Working | 16 |  | 20 | 1 |  | Standalone |  | 0.75 | 2042.2 | 705.7
2030-06-25 02:12 | 2030-06-25 03:12 | 1 | Transit to next foundation | OFFSHORE | Working | 16 | 31 | 21 | 1 |  | Standalone |  | 1.5 | 2043.2 | 704.7
2030-06-25 03:12 | 2030-06-25 04:12 | 1 | Positioning at WTG location | OFFSHORE | Working | 16 | 31 | 22 | 1 |  | Standalone |  | 1.5 | 2044.2 | 703.7
2030-06-25 04:12 | 2030-06-25 08:12 | 4 | Preload and jacking up at site | OFFSHORE | Working | 16 | 31 | 23 | 1 |  | Standalone |  | 6 | 2048.2 | 699.7
2030-06-25 08:12 | 2030-06-25 11:12 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 16 | 31 | 24 | 1 |  | Standalone |  | 3 | 2051.2 | 696.7
2030-06-25 11:12 | 2030-06-25 12:12 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 16 | 31 | 25 | 1 |  | Standalone |  | 1 | 2052.2 | 695.7
2030-06-25 12:12 | 2030-06-25 14:12 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 16 | 31 | 26 | 1 |  | Standalone |  | 2 | 2054.2 | 693.7
2030-06-25 14:12 | 2030-06-25 15:12 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 16 | 31 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2055.2 | 692.7
2030-06-25 15:12 | 2030-06-25 18:42 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 31 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2058.7 | 689.2
2030-06-25 18:42 | 2030-06-25 19:12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 16 | 31 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2059.2 | 688.7
2030-06-25 19:12 | 2030-06-25 19:42 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 16 | 31 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2059.7 | 688.2
2030-06-25 19:42 | 2030-06-25 21:57 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 31 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2061.95 | 685.95
2030-06-25 21:57 | 2030-06-25 22:27 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 16 | 31 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2062.45 | 685.45
2030-06-25 22:27 | 2030-06-25 22:57 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 16 | 31 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2062.95 | 684.95
2030-06-25 22:57 | 2030-06-26 00:42 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 31 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2064.7 | 683.2
2030-06-26 00:42 | 2030-06-26 02:12 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 16 | 31 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2066.2 | 681.7
2030-06-26 02:12 | 2030-06-26 03:57 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 31 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2067.95 | 679.95
2030-06-26 03:57 | 2030-06-26 05:27 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 16 | 31 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2069.45 | 678.45
2030-06-26 05:27 | 2030-06-26 07:12 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 31 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2071.2 | 676.7
2030-06-26 07:12 | 2030-06-26 08:42 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 16 | 31 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2072.7 | 675.2
2030-06-26 08:42 | 2030-06-26 09:42 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 16 | 31 | 40 | 1 |  | Standalone |  | 1 | 2073.7 | 674.2
2030-06-26 09:42 | 2030-06-26 10:42 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 16 | 31 | 41 | 1 |  | Standalone |  | 1 | 2074.7 | 673.2
2030-06-26 10:42 | 2030-06-26 13:42 | 3 | Turbine general completion works | OFFSHORE | Working | 16 | 31 | 42 | 1 |  | Standalone |  | 3 | 2077.7 | 670.2
2030-06-26 13:42 | 2030-06-26 16:42 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 16 | 31 | 43 | 1 |  | Standalone |  | 3 | 2080.7 | 667.2
2030-06-26 16:42 | 2030-06-26 18:42 | 2 | Jacking down at site | OFFSHORE | Working | 16 | 31 | 44 | 1 |  | Standalone |  | 3 | 2082.7 | 665.2
2030-06-26 18:42 | 2030-06-26 19:42 | 1 | Transit to next foundation | OFFSHORE | Working | 16 | 32 | 21 | 1 |  | Standalone |  | 1.5 | 2083.7 | 664.2
2030-06-26 19:42 | 2030-06-26 20:42 | 1 | Positioning at WTG location | OFFSHORE | Working | 16 | 32 | 22 | 1 |  | Standalone |  | 1.5 | 2084.7 | 663.2
2030-06-26 20:42 | 2030-06-27 00:42 | 4 | Preload and jacking up at site | OFFSHORE | Working | 16 | 32 | 23 | 1 |  | Standalone |  | 6 | 2088.7 | 659.2
2030-06-27 00:42 | 2030-06-27 03:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 16 | 32 | 24 | 1 |  | Standalone |  | 3 | 2091.7 | 656.2
2030-06-27 03:42 | 2030-06-27 04:42 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 16 | 32 | 25 | 1 |  | Standalone |  | 1 | 2092.7 | 655.2
2030-06-27 04:42 | 2030-06-27 06:42 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 16 | 32 | 26 | 1 |  | Standalone |  | 2 | 2094.7 | 653.2
2030-06-27 06:42 | 2030-06-27 07:42 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 16 | 32 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2095.7 | 652.2
2030-06-27 07:42 | 2030-06-27 11:12 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 32 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2099.2 | 648.7
2030-06-27 11:12 | 2030-06-27 11:42 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 16 | 32 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2099.7 | 648.2
2030-06-27 11:42 | 2030-06-27 12:12 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 16 | 32 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2100.2 | 647.7
2030-06-27 12:12 | 2030-06-27 14:27 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 32 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2102.45 | 645.45
2030-06-27 14:27 | 2030-06-27 14:57 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 16 | 32 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2102.95 | 644.95
2030-06-27 14:57 | 2030-06-27 15:27 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 16 | 32 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2103.45 | 644.45
2030-06-27 15:27 | 2030-06-27 17:12 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 32 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2105.2 | 642.7
2030-06-27 17:12 | 2030-06-27 18:42 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 16 | 32 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2106.7 | 641.2
2030-06-27 18:42 | 2030-06-27 20:27 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 32 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2108.45 | 639.45
2030-06-27 20:27 | 2030-06-27 21:57 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 16 | 32 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2109.95 | 637.95
2030-06-27 21:57 | 2030-06-27 23:42 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 16 | 32 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2111.7 | 636.2
2030-06-27 23:42 | 2030-06-28 01:12 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 16 | 32 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2113.2 | 634.7
2030-06-28 01:12 | 2030-06-28 02:12 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 16 | 32 | 40 | 1 |  | Standalone |  | 1 | 2114.2 | 633.7
2030-06-28 02:12 | 2030-06-28 03:12 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 16 | 32 | 41 | 1 |  | Standalone |  | 1 | 2115.2 | 632.7
2030-06-28 03:12 | 2030-06-28 06:12 | 3 | Turbine general completion works | OFFSHORE | Working | 16 | 32 | 42 | 1 |  | Standalone |  | 3 | 2118.2 | 629.7
2030-06-28 06:12 | 2030-06-28 09:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 16 | 32 | 43 | 1 |  | Standalone |  | 3 | 2121.2 | 626.7
2030-06-28 09:12 | 2030-06-28 11:12 | 2 | Jacking down at site | OFFSHORE | Working | 16 | 32 | 44 | 1 |  | Standalone |  | 3 | 2123.2 | 624.7
2030-06-28 11:12 | 2030-06-28 16:24 | 5.2 | Transit from site to port | OFFSHORE | Working | 16 |  | 45 | 1 |  | Standalone |  | 7.8 | 2128.4 | 619.5
2030-06-28 16:24 | 2030-06-28 17:24 | 1 | Port maneuvering | OFFSHORE | Working | 17 |  | 1 | 1 |  | Standalone |  | 1.5 | 2129.4 | 618.5
2030-06-28 17:24 | 2030-06-28 19:24 | 2 | Preload and jacking up at port | OFFSHORE | Working | 17 |  | 2 | 1 |  | Standalone |  | 3 | 2131.4 | 616.5
2030-06-28 19:24 | 2030-06-28 22:24 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 17 |  | 3 | 1 |  | Standalone |  | 3 | 2134.4 | 613.5
2030-06-28 22:24 | 2030-06-28 23:24 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 17 |  | 4 | 1 |  | Standalone |  | 1 | 2135.4 | 612.5
2030-06-28 23:24 | 2030-06-29 01:39 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 17 |  | 5 | 1 |  | Standalone |  | 3.375 | 2137.65 | 610.25
2030-06-29 01:39 | 2030-06-29 03:54 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 17 |  | 6 | 1 |  | Standalone |  | 3.375 | 2139.9 | 608
2030-06-29 03:54 | 2030-06-29 05:24 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 17 |  | 7 | 1 |  | Standalone |  | 2.25 | 2141.4 | 606.5
2030-06-29 05:24 | 2030-06-29 06:54 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 17 |  | 8 | 1 |  | Standalone |  | 2.25 | 2142.9 | 605
2030-06-29 06:54 | 2030-06-29 08:24 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 17 |  | 9 | 1 |  | Standalone |  | 2.25 | 2144.4 | 603.5
2030-06-29 08:24 | 2030-06-29 09:24 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 17 |  | 10 | 1 |  | Standalone |  | 1 | 2145.4 | 602.5
2030-06-29 09:24 | 2030-06-29 11:39 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 17 |  | 11 | 1 |  | Standalone |  | 3.375 | 2147.65 | 600.25
2030-06-29 11:39 | 2030-06-29 13:54 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 17 |  | 12 | 1 |  | Standalone |  | 3.375 | 2149.9 | 598
2030-06-29 13:54 | 2030-06-29 15:24 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 17 |  | 13 | 1 |  | Standalone |  | 2.25 | 2151.4 | 596.5
2030-06-29 15:24 | 2030-06-29 16:54 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 17 |  | 14 | 1 |  | Standalone |  | 2.25 | 2152.9 | 595
2030-06-29 16:54 | 2030-06-29 18:24 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 17 |  | 15 | 1 |  | Standalone |  | 2.25 | 2154.4 | 593.5
2030-06-29 18:24 | 2030-06-29 21:24 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 17 |  | 16 | 1 |  | Standalone |  | 3 | 2157.4 | 590.5
2030-06-29 21:24 | 2030-06-29 23:24 | 2 | Jacking down at port | OFFSHORE | Working | 17 |  | 17 | 1 |  | Standalone |  | 3 | 2159.4 | 588.5
2030-06-29 23:24 | 2030-06-30 00:24 | 1 | Port maneuvering | OFFSHORE | Working | 17 |  | 18 | 1 |  | Standalone |  | 1.5 | 2160.4 | 587.5
2030-06-30 00:24 | 2030-06-30 05:36 | 5.2 | Transit from port to site | OFFSHORE | Working | 17 |  | 19 | 1 |  | Standalone |  | 7.8 | 2165.6 | 582.3
2030-06-30 05:36 | 2030-06-30 06:06 | 0.5 | DP field check | OFFSHORE | Working | 17 |  | 20 | 1 |  | Standalone |  | 0.75 | 2166.1 | 581.8
2030-06-30 06:06 | 2030-06-30 07:06 | 1 | Transit to next foundation | OFFSHORE | Working | 17 | 33 | 21 | 1 |  | Standalone |  | 1.5 | 2167.1 | 580.8
2030-06-30 07:06 | 2030-06-30 08:06 | 1 | Positioning at WTG location | OFFSHORE | Working | 17 | 33 | 22 | 1 |  | Standalone |  | 1.5 | 2168.1 | 579.8
2030-06-30 08:06 | 2030-06-30 12:06 | 4 | Preload and jacking up at site | OFFSHORE | Working | 17 | 33 | 23 | 1 |  | Standalone |  | 6 | 2172.1 | 575.8
2030-06-30 12:06 | 2030-06-30 15:06 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 17 | 33 | 24 | 1 |  | Standalone |  | 3 | 2175.1 | 572.8
2030-06-30 15:06 | 2030-06-30 16:06 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 17 | 33 | 25 | 1 |  | Standalone |  | 1 | 2176.1 | 571.8
2030-06-30 16:06 | 2030-06-30 18:06 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 17 | 33 | 26 | 1 |  | Standalone |  | 2 | 2178.1 | 569.8
2030-06-30 18:06 | 2030-06-30 19:06 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 17 | 33 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2179.1 | 568.8
2030-06-30 19:06 | 2030-06-30 22:36 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 33 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2182.6 | 565.3
2030-06-30 22:36 | 2030-06-30 23:06 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 17 | 33 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2183.1 | 564.8
2030-06-30 23:06 | 2030-06-30 23:36 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 17 | 33 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2183.6 | 564.3
2030-06-30 23:36 | 2030-07-01 01:51 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 33 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2185.85 | 562.05
2030-07-01 01:51 | 2030-07-01 02:21 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 17 | 33 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2186.35 | 561.55
2030-07-01 02:21 | 2030-07-01 02:51 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 17 | 33 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2186.85 | 561.05
2030-07-01 02:51 | 2030-07-01 04:36 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 33 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2188.6 | 559.3
2030-07-01 04:36 | 2030-07-01 06:06 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 17 | 33 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2190.1 | 557.8
2030-07-01 06:06 | 2030-07-01 07:51 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 33 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2191.85 | 556.05
2030-07-01 07:51 | 2030-07-01 09:21 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 17 | 33 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2193.35 | 554.55
2030-07-01 09:21 | 2030-07-01 11:06 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 33 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2195.1 | 552.8
2030-07-01 11:06 | 2030-07-01 12:36 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 17 | 33 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2196.6 | 551.3
2030-07-01 12:36 | 2030-07-01 13:36 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 17 | 33 | 40 | 1 |  | Standalone |  | 1 | 2197.6 | 550.3
2030-07-01 13:36 | 2030-07-01 14:36 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 17 | 33 | 41 | 1 |  | Standalone |  | 1 | 2198.6 | 549.3
2030-07-01 14:36 | 2030-07-01 17:36 | 3 | Turbine general completion works | OFFSHORE | Working | 17 | 33 | 42 | 1 |  | Standalone |  | 3 | 2201.6 | 546.3
2030-07-01 17:36 | 2030-07-01 20:36 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 17 | 33 | 43 | 1 |  | Standalone |  | 3 | 2204.6 | 543.3
2030-07-01 20:36 | 2030-07-01 22:36 | 2 | Jacking down at site | OFFSHORE | Working | 17 | 33 | 44 | 1 |  | Standalone |  | 3 | 2206.6 | 541.3
2030-07-01 22:36 | 2030-07-01 23:36 | 1 | Transit to next foundation | OFFSHORE | Working | 17 | 34 | 21 | 1 |  | Standalone |  | 1.5 | 2207.6 | 540.3
2030-07-01 23:36 | 2030-07-02 00:36 | 1 | Positioning at WTG location | OFFSHORE | Working | 17 | 34 | 22 | 1 |  | Standalone |  | 1.5 | 2208.6 | 539.3
2030-07-02 00:36 | 2030-07-02 04:36 | 4 | Preload and jacking up at site | OFFSHORE | Working | 17 | 34 | 23 | 1 |  | Standalone |  | 6 | 2212.6 | 535.3
2030-07-02 04:36 | 2030-07-02 07:36 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 17 | 34 | 24 | 1 |  | Standalone |  | 3 | 2215.6 | 532.3
2030-07-02 07:36 | 2030-07-02 08:36 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 17 | 34 | 25 | 1 |  | Standalone |  | 1 | 2216.6 | 531.3
2030-07-02 08:36 | 2030-07-02 10:36 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 17 | 34 | 26 | 1 |  | Standalone |  | 2 | 2218.6 | 529.3
2030-07-02 10:36 | 2030-07-02 11:36 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 17 | 34 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2219.6 | 528.3
2030-07-02 11:36 | 2030-07-02 15:06 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 34 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2223.1 | 524.8
2030-07-02 15:06 | 2030-07-02 15:36 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 17 | 34 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2223.6 | 524.3
2030-07-02 15:36 | 2030-07-02 16:06 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 17 | 34 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2224.1 | 523.8
2030-07-02 16:06 | 2030-07-02 18:21 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 34 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2226.35 | 521.55
2030-07-02 18:21 | 2030-07-02 18:51 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 17 | 34 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2226.85 | 521.05
2030-07-02 18:51 | 2030-07-02 19:21 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 17 | 34 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2227.35 | 520.55
2030-07-02 19:21 | 2030-07-02 21:06 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 34 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2229.1 | 518.8
2030-07-02 21:06 | 2030-07-02 22:36 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 17 | 34 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2230.6 | 517.3
2030-07-02 22:36 | 2030-07-03 00:21 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 34 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2232.35 | 515.55
2030-07-03 00:21 | 2030-07-03 01:51 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 17 | 34 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2233.85 | 514.05
2030-07-03 01:51 | 2030-07-03 03:36 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 17 | 34 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2235.6 | 512.3
2030-07-03 03:36 | 2030-07-03 05:06 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 17 | 34 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2237.1 | 510.8
2030-07-03 05:06 | 2030-07-03 06:06 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 17 | 34 | 40 | 1 |  | Standalone |  | 1 | 2238.1 | 509.8
2030-07-03 06:06 | 2030-07-03 07:06 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 17 | 34 | 41 | 1 |  | Standalone |  | 1 | 2239.1 | 508.8
2030-07-03 07:06 | 2030-07-03 10:06 | 3 | Turbine general completion works | OFFSHORE | Working | 17 | 34 | 42 | 1 |  | Standalone |  | 3 | 2242.1 | 505.8
2030-07-03 10:06 | 2030-07-03 13:06 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 17 | 34 | 43 | 1 |  | Standalone |  | 3 | 2245.1 | 502.8
2030-07-03 13:06 | 2030-07-03 15:06 | 2 | Jacking down at site | OFFSHORE | Working | 17 | 34 | 44 | 1 |  | Standalone |  | 3 | 2247.1 | 500.8
2030-07-03 15:06 | 2030-07-03 20:18 | 5.2 | Transit from site to port | OFFSHORE | Working | 17 |  | 45 | 1 |  | Standalone |  | 7.8 | 2252.3 | 495.6
2030-07-03 20:18 | 2030-07-03 21:18 | 1 | Port maneuvering | OFFSHORE | Working | 18 |  | 1 | 1 |  | Standalone |  | 1.5 | 2253.3 | 494.6
2030-07-03 21:18 | 2030-07-03 23:18 | 2 | Preload and jacking up at port | OFFSHORE | Working | 18 |  | 2 | 1 |  | Standalone |  | 3 | 2255.3 | 492.6
2030-07-03 23:18 | 2030-07-04 02:18 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 18 |  | 3 | 1 |  | Standalone |  | 3 | 2258.3 | 489.6
2030-07-04 02:18 | 2030-07-04 03:18 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 18 |  | 4 | 1 |  | Standalone |  | 1 | 2259.3 | 488.6
2030-07-04 03:18 | 2030-07-04 05:33 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 18 |  | 5 | 1 |  | Standalone |  | 3.375 | 2261.55 | 486.35
2030-07-04 05:33 | 2030-07-04 07:48 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 18 |  | 6 | 1 |  | Standalone |  | 3.375 | 2263.8 | 484.1
2030-07-04 07:48 | 2030-07-04 09:18 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 18 |  | 7 | 1 |  | Standalone |  | 2.25 | 2265.3 | 482.6
2030-07-04 09:18 | 2030-07-04 10:48 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 18 |  | 8 | 1 |  | Standalone |  | 2.25 | 2266.8 | 481.1
2030-07-04 10:48 | 2030-07-04 12:18 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 18 |  | 9 | 1 |  | Standalone |  | 2.25 | 2268.3 | 479.6
2030-07-04 12:18 | 2030-07-04 13:18 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 18 |  | 10 | 1 |  | Standalone |  | 1 | 2269.3 | 478.6
2030-07-04 13:18 | 2030-07-04 15:33 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 18 |  | 11 | 1 |  | Standalone |  | 3.375 | 2271.55 | 476.35
2030-07-04 15:33 | 2030-07-04 17:48 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 18 |  | 12 | 1 |  | Standalone |  | 3.375 | 2273.8 | 474.1
2030-07-04 17:48 | 2030-07-04 19:18 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 18 |  | 13 | 1 |  | Standalone |  | 2.25 | 2275.3 | 472.6
2030-07-04 19:18 | 2030-07-04 20:48 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 18 |  | 14 | 1 |  | Standalone |  | 2.25 | 2276.8 | 471.1
2030-07-04 20:48 | 2030-07-04 22:18 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 18 |  | 15 | 1 |  | Standalone |  | 2.25 | 2278.3 | 469.6
2030-07-04 22:18 | 2030-07-05 01:18 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 18 |  | 16 | 1 |  | Standalone |  | 3 | 2281.3 | 466.6
2030-07-05 01:18 | 2030-07-05 03:18 | 2 | Jacking down at port | OFFSHORE | Working | 18 |  | 17 | 1 |  | Standalone |  | 3 | 2283.3 | 464.6
2030-07-05 03:18 | 2030-07-05 04:18 | 1 | Port maneuvering | OFFSHORE | Working | 18 |  | 18 | 1 |  | Standalone |  | 1.5 | 2284.3 | 463.6
2030-07-05 04:18 | 2030-07-05 09:30 | 5.2 | Transit from port to site | OFFSHORE | Working | 18 |  | 19 | 1 |  | Standalone |  | 7.8 | 2289.5 | 458.4
2030-07-05 09:30 | 2030-07-05 10:00 | 0.5 | DP field check | OFFSHORE | Working | 18 |  | 20 | 1 |  | Standalone |  | 0.75 | 2290 | 457.9
2030-07-05 10:00 | 2030-07-05 11:00 | 1 | Transit to next foundation | OFFSHORE | Working | 18 | 35 | 21 | 1 |  | Standalone |  | 1.5 | 2291 | 456.9
2030-07-05 11:00 | 2030-07-05 12:00 | 1 | Positioning at WTG location | OFFSHORE | Working | 18 | 35 | 22 | 1 |  | Standalone |  | 1.5 | 2292 | 455.9
2030-07-05 12:00 | 2030-07-05 16:00 | 4 | Preload and jacking up at site | OFFSHORE | Working | 18 | 35 | 23 | 1 |  | Standalone |  | 6 | 2296 | 451.9
2030-07-05 16:00 | 2030-07-05 19:00 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 18 | 35 | 24 | 1 |  | Standalone |  | 3 | 2299 | 448.9
2030-07-05 19:00 | 2030-07-05 20:00 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 18 | 35 | 25 | 1 |  | Standalone |  | 1 | 2300 | 447.9
2030-07-05 20:00 | 2030-07-05 22:00 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 18 | 35 | 26 | 1 |  | Standalone |  | 2 | 2302 | 445.9
2030-07-05 22:00 | 2030-07-05 23:00 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 18 | 35 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2303 | 444.9
2030-07-05 23:00 | 2030-07-06 02:30 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 35 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2306.5 | 441.4
2030-07-06 02:30 | 2030-07-06 03:00 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 18 | 35 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2307 | 440.9
2030-07-06 03:00 | 2030-07-06 03:30 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 18 | 35 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2307.5 | 440.4
2030-07-06 03:30 | 2030-07-06 05:45 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 35 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2309.75 | 438.15
2030-07-06 05:45 | 2030-07-06 06:15 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 18 | 35 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2310.25 | 437.65
2030-07-06 06:15 | 2030-07-06 06:45 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 18 | 35 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2310.75 | 437.15
2030-07-06 06:45 | 2030-07-06 08:30 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 35 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2312.5 | 435.4
2030-07-06 08:30 | 2030-07-06 10:00 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 18 | 35 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2314 | 433.9
2030-07-06 10:00 | 2030-07-06 11:45 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 35 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2315.75 | 432.15
2030-07-06 11:45 | 2030-07-06 13:15 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 18 | 35 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2317.25 | 430.65
2030-07-06 13:15 | 2030-07-06 15:00 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 35 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2319 | 428.9
2030-07-06 15:00 | 2030-07-06 16:30 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 18 | 35 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2320.5 | 427.4
2030-07-06 16:30 | 2030-07-06 17:30 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 18 | 35 | 40 | 1 |  | Standalone |  | 1 | 2321.5 | 426.4
2030-07-06 17:30 | 2030-07-06 18:30 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 18 | 35 | 41 | 1 |  | Standalone |  | 1 | 2322.5 | 425.4
2030-07-06 18:30 | 2030-07-06 21:30 | 3 | Turbine general completion works | OFFSHORE | Working | 18 | 35 | 42 | 1 |  | Standalone |  | 3 | 2325.5 | 422.4
2030-07-06 21:30 | 2030-07-07 00:30 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 18 | 35 | 43 | 1 |  | Standalone |  | 3 | 2328.5 | 419.4
2030-07-07 00:30 | 2030-07-07 02:30 | 2 | Jacking down at site | OFFSHORE | Working | 18 | 35 | 44 | 1 |  | Standalone |  | 3 | 2330.5 | 417.4
2030-07-07 02:30 | 2030-07-07 03:30 | 1 | Transit to next foundation | OFFSHORE | Working | 18 | 36 | 21 | 1 |  | Standalone |  | 1.5 | 2331.5 | 416.4
2030-07-07 03:30 | 2030-07-07 04:30 | 1 | Positioning at WTG location | OFFSHORE | Working | 18 | 36 | 22 | 1 |  | Standalone |  | 1.5 | 2332.5 | 415.4
2030-07-07 04:30 | 2030-07-07 08:30 | 4 | Preload and jacking up at site | OFFSHORE | Working | 18 | 36 | 23 | 1 |  | Standalone |  | 6 | 2336.5 | 411.4
2030-07-07 08:30 | 2030-07-07 11:30 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 18 | 36 | 24 | 1 |  | Standalone |  | 3 | 2339.5 | 408.4
2030-07-07 11:30 | 2030-07-07 12:30 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 18 | 36 | 25 | 1 |  | Standalone |  | 1 | 2340.5 | 407.4
2030-07-07 12:30 | 2030-07-07 14:30 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 18 | 36 | 26 | 1 |  | Standalone |  | 2 | 2342.5 | 405.4
2030-07-07 14:30 | 2030-07-07 15:30 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 18 | 36 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2343.5 | 404.4
2030-07-07 15:30 | 2030-07-07 19:00 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 36 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2347 | 400.9
2030-07-07 19:00 | 2030-07-07 19:30 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 18 | 36 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2347.5 | 400.4
2030-07-07 19:30 | 2030-07-07 20:00 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 18 | 36 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2348 | 399.9
2030-07-07 20:00 | 2030-07-07 22:15 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 36 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2350.25 | 397.65
2030-07-07 22:15 | 2030-07-07 22:45 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 18 | 36 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2350.75 | 397.15
2030-07-07 22:45 | 2030-07-07 23:15 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 18 | 36 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2351.25 | 396.65
2030-07-07 23:15 | 2030-07-08 01:00 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 36 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2353 | 394.9
2030-07-08 01:00 | 2030-07-08 02:30 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 18 | 36 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2354.5 | 393.4
2030-07-08 02:30 | 2030-07-08 04:15 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 36 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2356.25 | 391.65
2030-07-08 04:15 | 2030-07-08 05:45 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 18 | 36 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2357.75 | 390.15
2030-07-08 05:45 | 2030-07-08 07:30 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 18 | 36 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2359.5 | 388.4
2030-07-08 07:30 | 2030-07-08 09:00 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 18 | 36 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2361 | 386.9
2030-07-08 09:00 | 2030-07-08 10:00 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 18 | 36 | 40 | 1 |  | Standalone |  | 1 | 2362 | 385.9
2030-07-08 10:00 | 2030-07-08 11:00 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 18 | 36 | 41 | 1 |  | Standalone |  | 1 | 2363 | 384.9
2030-07-08 11:00 | 2030-07-08 14:00 | 3 | Turbine general completion works | OFFSHORE | Working | 18 | 36 | 42 | 1 |  | Standalone |  | 3 | 2366 | 381.9
2030-07-08 14:00 | 2030-07-08 17:00 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 18 | 36 | 43 | 1 |  | Standalone |  | 3 | 2369 | 378.9
2030-07-08 17:00 | 2030-07-08 19:00 | 2 | Jacking down at site | OFFSHORE | Working | 18 | 36 | 44 | 1 |  | Standalone |  | 3 | 2371 | 376.9
2030-07-08 19:00 | 2030-07-09 00:12 | 5.2 | Transit from site to port | OFFSHORE | Working | 18 |  | 45 | 1 |  | Standalone |  | 7.8 | 2376.2 | 371.7
2030-07-09 00:12 | 2030-07-09 01:12 | 1 | Port maneuvering | OFFSHORE | Working | 19 |  | 1 | 1 |  | Standalone |  | 1.5 | 2377.2 | 370.7
2030-07-09 01:12 | 2030-07-09 03:12 | 2 | Preload and jacking up at port | OFFSHORE | Working | 19 |  | 2 | 1 |  | Standalone |  | 3 | 2379.2 | 368.7
2030-07-09 03:12 | 2030-07-09 06:12 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 19 |  | 3 | 1 |  | Standalone |  | 3 | 2382.2 | 365.7
2030-07-09 06:12 | 2030-07-09 07:12 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 19 |  | 4 | 1 |  | Standalone |  | 1 | 2383.2 | 364.7
2030-07-09 07:12 | 2030-07-09 09:27 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 19 |  | 5 | 1 |  | Standalone |  | 3.375 | 2385.45 | 362.45
2030-07-09 09:27 | 2030-07-09 11:42 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 19 |  | 6 | 1 |  | Standalone |  | 3.375 | 2387.7 | 360.2
2030-07-09 11:42 | 2030-07-09 13:12 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 19 |  | 7 | 1 |  | Standalone |  | 2.25 | 2389.2 | 358.7
2030-07-09 13:12 | 2030-07-09 14:42 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 19 |  | 8 | 1 |  | Standalone |  | 2.25 | 2390.7 | 357.2
2030-07-09 14:42 | 2030-07-09 16:12 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 19 |  | 9 | 1 |  | Standalone |  | 2.25 | 2392.2 | 355.7
2030-07-09 16:12 | 2030-07-09 17:12 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 19 |  | 10 | 1 |  | Standalone |  | 1 | 2393.2 | 354.7
2030-07-09 17:12 | 2030-07-09 19:27 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 19 |  | 11 | 1 |  | Standalone |  | 3.375 | 2395.45 | 352.45
2030-07-09 19:27 | 2030-07-09 21:42 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 19 |  | 12 | 1 |  | Standalone |  | 3.375 | 2397.7 | 350.2
2030-07-09 21:42 | 2030-07-09 23:12 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 19 |  | 13 | 1 |  | Standalone |  | 2.25 | 2399.2 | 348.7
2030-07-09 23:12 | 2030-07-10 00:42 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 19 |  | 14 | 1 |  | Standalone |  | 2.25 | 2400.7 | 347.2
2030-07-10 00:42 | 2030-07-10 02:12 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 19 |  | 15 | 1 |  | Standalone |  | 2.25 | 2402.2 | 345.7
2030-07-10 02:12 | 2030-07-10 05:12 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 19 |  | 16 | 1 |  | Standalone |  | 3 | 2405.2 | 342.7
2030-07-10 05:12 | 2030-07-10 07:12 | 2 | Jacking down at port | OFFSHORE | Working | 19 |  | 17 | 1 |  | Standalone |  | 3 | 2407.2 | 340.7
2030-07-10 07:12 | 2030-07-10 08:12 | 1 | Port maneuvering | OFFSHORE | Working | 19 |  | 18 | 1 |  | Standalone |  | 1.5 | 2408.2 | 339.7
2030-07-10 08:12 | 2030-07-10 13:24 | 5.2 | Transit from port to site | OFFSHORE | Working | 19 |  | 19 | 1 |  | Standalone |  | 7.8 | 2413.4 | 334.5
2030-07-10 13:24 | 2030-07-10 13:54 | 0.5 | DP field check | OFFSHORE | Working | 19 |  | 20 | 1 |  | Standalone |  | 0.75 | 2413.9 | 334
2030-07-10 13:54 | 2030-07-10 14:54 | 1 | Transit to next foundation | OFFSHORE | Working | 19 | 37 | 21 | 1 |  | Standalone |  | 1.5 | 2414.9 | 333
2030-07-10 14:54 | 2030-07-10 15:54 | 1 | Positioning at WTG location | OFFSHORE | Working | 19 | 37 | 22 | 1 |  | Standalone |  | 1.5 | 2415.9 | 332
2030-07-10 15:54 | 2030-07-10 19:54 | 4 | Preload and jacking up at site | OFFSHORE | Working | 19 | 37 | 23 | 1 |  | Standalone |  | 6 | 2419.9 | 328
2030-07-10 19:54 | 2030-07-10 22:54 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 19 | 37 | 24 | 1 |  | Standalone |  | 3 | 2422.9 | 325
2030-07-10 22:54 | 2030-07-10 23:54 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 19 | 37 | 25 | 1 |  | Standalone |  | 1 | 2423.9 | 324
2030-07-10 23:54 | 2030-07-11 01:54 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 19 | 37 | 26 | 1 |  | Standalone |  | 2 | 2425.9 | 322
2030-07-11 01:54 | 2030-07-11 02:54 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 19 | 37 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2426.9 | 321
2030-07-11 02:54 | 2030-07-11 06:24 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 37 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2430.4 | 317.5
2030-07-11 06:24 | 2030-07-11 06:54 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 19 | 37 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2430.9 | 317
2030-07-11 06:54 | 2030-07-11 07:24 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 19 | 37 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2431.4 | 316.5
2030-07-11 07:24 | 2030-07-11 09:39 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 37 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2433.65 | 314.25
2030-07-11 09:39 | 2030-07-11 10:09 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 19 | 37 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2434.15 | 313.75
2030-07-11 10:09 | 2030-07-11 10:39 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 19 | 37 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2434.65 | 313.25
2030-07-11 10:39 | 2030-07-11 12:24 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 37 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2436.4 | 311.5
2030-07-11 12:24 | 2030-07-11 13:54 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 19 | 37 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2437.9 | 310
2030-07-11 13:54 | 2030-07-11 15:39 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 37 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2439.65 | 308.25
2030-07-11 15:39 | 2030-07-11 17:09 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 19 | 37 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2441.15 | 306.75
2030-07-11 17:09 | 2030-07-11 18:54 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 37 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2442.9 | 305
2030-07-11 18:54 | 2030-07-11 20:24 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 19 | 37 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2444.4 | 303.5
2030-07-11 20:24 | 2030-07-11 21:24 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 19 | 37 | 40 | 1 |  | Standalone |  | 1 | 2445.4 | 302.5
2030-07-11 21:24 | 2030-07-11 22:24 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 19 | 37 | 41 | 1 |  | Standalone |  | 1 | 2446.4 | 301.5
2030-07-11 22:24 | 2030-07-12 01:24 | 3 | Turbine general completion works | OFFSHORE | Working | 19 | 37 | 42 | 1 |  | Standalone |  | 3 | 2449.4 | 298.5
2030-07-12 01:24 | 2030-07-12 04:24 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 19 | 37 | 43 | 1 |  | Standalone |  | 3 | 2452.4 | 295.5
2030-07-12 04:24 | 2030-07-12 06:24 | 2 | Jacking down at site | OFFSHORE | Working | 19 | 37 | 44 | 1 |  | Standalone |  | 3 | 2454.4 | 293.5
2030-07-12 06:24 | 2030-07-12 07:24 | 1 | Transit to next foundation | OFFSHORE | Working | 19 | 38 | 21 | 1 |  | Standalone |  | 1.5 | 2455.4 | 292.5
2030-07-12 07:24 | 2030-07-12 08:24 | 1 | Positioning at WTG location | OFFSHORE | Working | 19 | 38 | 22 | 1 |  | Standalone |  | 1.5 | 2456.4 | 291.5
2030-07-12 08:24 | 2030-07-12 12:24 | 4 | Preload and jacking up at site | OFFSHORE | Working | 19 | 38 | 23 | 1 |  | Standalone |  | 6 | 2460.4 | 287.5
2030-07-12 12:24 | 2030-07-12 15:24 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 19 | 38 | 24 | 1 |  | Standalone |  | 3 | 2463.4 | 284.5
2030-07-12 15:24 | 2030-07-12 16:24 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 19 | 38 | 25 | 1 |  | Standalone |  | 1 | 2464.4 | 283.5
2030-07-12 16:24 | 2030-07-12 18:24 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 19 | 38 | 26 | 1 |  | Standalone |  | 2 | 2466.4 | 281.5
2030-07-12 18:24 | 2030-07-12 19:24 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 19 | 38 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2467.4 | 280.5
2030-07-12 19:24 | 2030-07-12 22:54 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 38 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2470.9 | 277
2030-07-12 22:54 | 2030-07-12 23:24 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 19 | 38 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2471.4 | 276.5
2030-07-12 23:24 | 2030-07-12 23:54 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 19 | 38 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2471.9 | 276
2030-07-12 23:54 | 2030-07-13 02:09 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 38 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2474.15 | 273.75
2030-07-13 02:09 | 2030-07-13 02:39 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 19 | 38 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2474.65 | 273.25
2030-07-13 02:39 | 2030-07-13 03:09 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 19 | 38 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2475.15 | 272.75
2030-07-13 03:09 | 2030-07-13 04:54 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 38 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2476.9 | 271
2030-07-13 04:54 | 2030-07-13 06:24 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 19 | 38 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2478.4 | 269.5
2030-07-13 06:24 | 2030-07-13 08:09 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 38 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2480.15 | 267.75
2030-07-13 08:09 | 2030-07-13 09:39 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 19 | 38 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2481.65 | 266.25
2030-07-13 09:39 | 2030-07-13 11:24 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 19 | 38 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2483.4 | 264.5
2030-07-13 11:24 | 2030-07-13 12:54 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 19 | 38 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2484.9 | 263
2030-07-13 12:54 | 2030-07-13 13:54 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 19 | 38 | 40 | 1 |  | Standalone |  | 1 | 2485.9 | 262
2030-07-13 13:54 | 2030-07-13 14:54 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 19 | 38 | 41 | 1 |  | Standalone |  | 1 | 2486.9 | 261
2030-07-13 14:54 | 2030-07-13 17:54 | 3 | Turbine general completion works | OFFSHORE | Working | 19 | 38 | 42 | 1 |  | Standalone |  | 3 | 2489.9 | 258
2030-07-13 17:54 | 2030-07-13 20:54 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 19 | 38 | 43 | 1 |  | Standalone |  | 3 | 2492.9 | 255
2030-07-13 20:54 | 2030-07-13 22:54 | 2 | Jacking down at site | OFFSHORE | Working | 19 | 38 | 44 | 1 |  | Standalone |  | 3 | 2494.9 | 253
2030-07-13 22:54 | 2030-07-14 04:06 | 5.2 | Transit from site to port | OFFSHORE | Working | 19 |  | 45 | 1 |  | Standalone |  | 7.8 | 2500.1 | 247.8
2030-07-14 04:06 | 2030-07-14 05:06 | 1 | Port maneuvering | OFFSHORE | Working | 20 |  | 1 | 1 |  | Standalone |  | 1.5 | 2501.1 | 246.8
2030-07-14 05:06 | 2030-07-14 07:06 | 2 | Preload and jacking up at port | OFFSHORE | Working | 20 |  | 2 | 1 |  | Standalone |  | 3 | 2503.1 | 244.8
2030-07-14 07:06 | 2030-07-14 10:06 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 20 |  | 3 | 1 |  | Standalone |  | 3 | 2506.1 | 241.8
2030-07-14 10:06 | 2030-07-14 11:06 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 20 |  | 4 | 1 |  | Standalone |  | 1 | 2507.1 | 240.8
2030-07-14 11:06 | 2030-07-14 13:21 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 20 |  | 5 | 1 |  | Standalone |  | 3.375 | 2509.35 | 238.55
2030-07-14 13:21 | 2030-07-14 15:36 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 20 |  | 6 | 1 |  | Standalone |  | 3.375 | 2511.6 | 236.3
2030-07-14 15:36 | 2030-07-14 17:06 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 20 |  | 7 | 1 |  | Standalone |  | 2.25 | 2513.1 | 234.8
2030-07-14 17:06 | 2030-07-14 18:36 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 20 |  | 8 | 1 |  | Standalone |  | 2.25 | 2514.6 | 233.3
2030-07-14 18:36 | 2030-07-14 20:06 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 20 |  | 9 | 1 |  | Standalone |  | 2.25 | 2516.1 | 231.8
2030-07-14 20:06 | 2030-07-14 21:06 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 20 |  | 10 | 1 |  | Standalone |  | 1 | 2517.1 | 230.8
2030-07-14 21:06 | 2030-07-14 23:21 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 20 |  | 11 | 1 |  | Standalone |  | 3.375 | 2519.35 | 228.55
2030-07-14 23:21 | 2030-07-15 01:36 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 20 |  | 12 | 1 |  | Standalone |  | 3.375 | 2521.6 | 226.3
2030-07-15 01:36 | 2030-07-15 03:06 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 20 |  | 13 | 1 |  | Standalone |  | 2.25 | 2523.1 | 224.8
2030-07-15 03:06 | 2030-07-15 04:36 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 20 |  | 14 | 1 |  | Standalone |  | 2.25 | 2524.6 | 223.3
2030-07-15 04:36 | 2030-07-15 06:06 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 20 |  | 15 | 1 |  | Standalone |  | 2.25 | 2526.1 | 221.8
2030-07-15 06:06 | 2030-07-15 09:06 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 20 |  | 16 | 1 |  | Standalone |  | 3 | 2529.1 | 218.8
2030-07-15 09:06 | 2030-07-15 11:06 | 2 | Jacking down at port | OFFSHORE | Working | 20 |  | 17 | 1 |  | Standalone |  | 3 | 2531.1 | 216.8
2030-07-15 11:06 | 2030-07-15 12:06 | 1 | Port maneuvering | OFFSHORE | Working | 20 |  | 18 | 1 |  | Standalone |  | 1.5 | 2532.1 | 215.8
2030-07-15 12:06 | 2030-07-15 17:18 | 5.2 | Transit from port to site | OFFSHORE | Working | 20 |  | 19 | 1 |  | Standalone |  | 7.8 | 2537.3 | 210.6
2030-07-15 17:18 | 2030-07-15 17:48 | 0.5 | DP field check | OFFSHORE | Working | 20 |  | 20 | 1 |  | Standalone |  | 0.75 | 2537.8 | 210.1
2030-07-15 17:48 | 2030-07-15 18:48 | 1 | Transit to next foundation | OFFSHORE | Working | 20 | 39 | 21 | 1 |  | Standalone |  | 1.5 | 2538.8 | 209.1
2030-07-15 18:48 | 2030-07-15 19:48 | 1 | Positioning at WTG location | OFFSHORE | Working | 20 | 39 | 22 | 1 |  | Standalone |  | 1.5 | 2539.8 | 208.1
2030-07-15 19:48 | 2030-07-15 23:48 | 4 | Preload and jacking up at site | OFFSHORE | Working | 20 | 39 | 23 | 1 |  | Standalone |  | 6 | 2543.8 | 204.1
2030-07-15 23:48 | 2030-07-16 02:48 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 20 | 39 | 24 | 1 |  | Standalone |  | 3 | 2546.8 | 201.1
2030-07-16 02:48 | 2030-07-16 03:48 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 20 | 39 | 25 | 1 |  | Standalone |  | 1 | 2547.8 | 200.1
2030-07-16 03:48 | 2030-07-16 05:48 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 20 | 39 | 26 | 1 |  | Standalone |  | 2 | 2549.8 | 198.1
2030-07-16 05:48 | 2030-07-16 06:48 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 20 | 39 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2550.8 | 197.1
2030-07-16 06:48 | 2030-07-16 10:18 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 39 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2554.3 | 193.6
2030-07-16 10:18 | 2030-07-16 10:48 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 20 | 39 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2554.8 | 193.1
2030-07-16 10:48 | 2030-07-16 11:18 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 20 | 39 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2555.3 | 192.6
2030-07-16 11:18 | 2030-07-16 13:33 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 39 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2557.55 | 190.35
2030-07-16 13:33 | 2030-07-16 14:03 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 20 | 39 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2558.05 | 189.85
2030-07-16 14:03 | 2030-07-16 14:33 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 20 | 39 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2558.55 | 189.35
2030-07-16 14:33 | 2030-07-16 16:18 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 39 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2560.3 | 187.6
2030-07-16 16:18 | 2030-07-16 17:48 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 20 | 39 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2561.8 | 186.1
2030-07-16 17:48 | 2030-07-16 19:33 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 39 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2563.55 | 184.35
2030-07-16 19:33 | 2030-07-16 21:03 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 20 | 39 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2565.05 | 182.85
2030-07-16 21:03 | 2030-07-16 22:48 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 39 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2566.8 | 181.1
2030-07-16 22:48 | 2030-07-17 00:18 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 20 | 39 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2568.3 | 179.6
2030-07-17 00:18 | 2030-07-17 01:18 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 20 | 39 | 40 | 1 |  | Standalone |  | 1 | 2569.3 | 178.6
2030-07-17 01:18 | 2030-07-17 02:18 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 20 | 39 | 41 | 1 |  | Standalone |  | 1 | 2570.3 | 177.6
2030-07-17 02:18 | 2030-07-17 05:18 | 3 | Turbine general completion works | OFFSHORE | Working | 20 | 39 | 42 | 1 |  | Standalone |  | 3 | 2573.3 | 174.6
2030-07-17 05:18 | 2030-07-17 08:18 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 20 | 39 | 43 | 1 |  | Standalone |  | 3 | 2576.3 | 171.6
2030-07-17 08:18 | 2030-07-17 10:18 | 2 | Jacking down at site | OFFSHORE | Working | 20 | 39 | 44 | 1 |  | Standalone |  | 3 | 2578.3 | 169.6
2030-07-17 10:18 | 2030-07-17 11:18 | 1 | Transit to next foundation | OFFSHORE | Working | 20 | 40 | 21 | 1 |  | Standalone |  | 1.5 | 2579.3 | 168.6
2030-07-17 11:18 | 2030-07-17 12:18 | 1 | Positioning at WTG location | OFFSHORE | Working | 20 | 40 | 22 | 1 |  | Standalone |  | 1.5 | 2580.3 | 167.6
2030-07-17 12:18 | 2030-07-17 16:18 | 4 | Preload and jacking up at site | OFFSHORE | Working | 20 | 40 | 23 | 1 |  | Standalone |  | 6 | 2584.3 | 163.6
2030-07-17 16:18 | 2030-07-17 19:18 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 20 | 40 | 24 | 1 |  | Standalone |  | 3 | 2587.3 | 160.6
2030-07-17 19:18 | 2030-07-17 20:18 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 20 | 40 | 25 | 1 |  | Standalone |  | 1 | 2588.3 | 159.6
2030-07-17 20:18 | 2030-07-17 22:18 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 20 | 40 | 26 | 1 |  | Standalone |  | 2 | 2590.3 | 157.6
2030-07-17 22:18 | 2030-07-17 23:18 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 20 | 40 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2591.3 | 156.6
2030-07-17 23:18 | 2030-07-18 02:48 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 40 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2594.8 | 153.1
2030-07-18 02:48 | 2030-07-18 03:18 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 20 | 40 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2595.3 | 152.6
2030-07-18 03:18 | 2030-07-18 03:48 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 20 | 40 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2595.8 | 152.1
2030-07-18 03:48 | 2030-07-18 06:03 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 40 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2598.05 | 149.85
2030-07-18 06:03 | 2030-07-18 06:33 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 20 | 40 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2598.55 | 149.35
2030-07-18 06:33 | 2030-07-18 07:03 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 20 | 40 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2599.05 | 148.85
2030-07-18 07:03 | 2030-07-18 08:48 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 40 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2600.8 | 147.1
2030-07-18 08:48 | 2030-07-18 10:18 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 20 | 40 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2602.3 | 145.6
2030-07-18 10:18 | 2030-07-18 12:03 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 40 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2604.05 | 143.85
2030-07-18 12:03 | 2030-07-18 13:33 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 20 | 40 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2605.55 | 142.35
2030-07-18 13:33 | 2030-07-18 15:18 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 20 | 40 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2607.3 | 140.6
2030-07-18 15:18 | 2030-07-18 16:48 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 20 | 40 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2608.8 | 139.1
2030-07-18 16:48 | 2030-07-18 17:48 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 20 | 40 | 40 | 1 |  | Standalone |  | 1 | 2609.8 | 138.1
2030-07-18 17:48 | 2030-07-18 18:48 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 20 | 40 | 41 | 1 |  | Standalone |  | 1 | 2610.8 | 137.1
2030-07-18 18:48 | 2030-07-18 21:48 | 3 | Turbine general completion works | OFFSHORE | Working | 20 | 40 | 42 | 1 |  | Standalone |  | 3 | 2613.8 | 134.1
2030-07-18 21:48 | 2030-07-19 00:48 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 20 | 40 | 43 | 1 |  | Standalone |  | 3 | 2616.8 | 131.1
2030-07-19 00:48 | 2030-07-19 02:48 | 2 | Jacking down at site | OFFSHORE | Working | 20 | 40 | 44 | 1 |  | Standalone |  | 3 | 2618.8 | 129.1
2030-07-19 02:48 | 2030-07-19 08:00 | 5.2 | Transit from site to port | OFFSHORE | Working | 20 |  | 45 | 1 |  | Standalone |  | 7.8 | 2624 | 123.9
2030-07-19 08:00 | 2030-07-19 09:00 | 1 | Port maneuvering | OFFSHORE | Working | 21 |  | 1 | 1 |  | Standalone |  | 1.5 | 2625 | 122.9
2030-07-19 09:00 | 2030-07-19 11:00 | 2 | Preload and jacking up at port | OFFSHORE | Working | 21 |  | 2 | 1 |  | Standalone |  | 3 | 2627 | 120.9
2030-07-19 11:00 | 2030-07-19 14:00 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working | 21 |  | 3 | 1 |  | Standalone |  | 3 | 2630 | 117.9
2030-07-19 14:00 | 2030-07-19 15:00 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 21 |  | 4 | 1 |  | Standalone |  | 1 | 2631 | 116.9
2030-07-19 15:00 | 2030-07-19 17:15 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working | 21 |  | 5 | 1 |  | Standalone |  | 3.375 | 2633.25 | 114.65
2030-07-19 17:15 | 2030-07-19 19:30 | 2.25 | Loadout Tower #1 | OFFSHORE | Working | 21 |  | 6 | 1 |  | Standalone |  | 3.375 | 2635.5 | 112.4
2030-07-19 19:30 | 2030-07-19 21:00 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 21 |  | 7 | 1 |  | Standalone |  | 2.25 | 2637 | 110.9
2030-07-19 21:00 | 2030-07-19 22:30 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 21 |  | 8 | 1 |  | Standalone |  | 2.25 | 2638.5 | 109.4
2030-07-19 22:30 | 2030-07-20 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 21 |  | 9 | 1 |  | Standalone |  | 2.25 | 2640 | 107.9
2030-07-20 | 2030-07-20 01:00 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working | 21 |  | 10 | 1 |  | Standalone |  | 1 | 2641 | 106.9
2030-07-20 01:00 | 2030-07-20 03:15 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working | 21 |  | 11 | 1 |  | Standalone |  | 3.375 | 2643.25 | 104.65
2030-07-20 03:15 | 2030-07-20 05:30 | 2.25 | Loadout Tower #2 | OFFSHORE | Working | 21 |  | 12 | 1 |  | Standalone |  | 3.375 | 2645.5 | 102.4
2030-07-20 05:30 | 2030-07-20 07:00 | 1.5 | Loadout Blade 1 | OFFSHORE | Working | 21 |  | 13 | 1 |  | Standalone |  | 2.25 | 2647 | 100.9
2030-07-20 07:00 | 2030-07-20 08:30 | 1.5 | Loadout Blade 2 | OFFSHORE | Working | 21 |  | 14 | 1 |  | Standalone |  | 2.25 | 2648.5 | 99.4
2030-07-20 08:30 | 2030-07-20 10:00 | 1.5 | Loadout Blade 3 | OFFSHORE | Working | 21 |  | 15 | 1 |  | Standalone |  | 2.25 | 2650 | 97.9
2030-07-20 10:00 | 2030-07-20 13:00 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working | 21 |  | 16 | 1 |  | Standalone |  | 3 | 2653 | 94.9
2030-07-20 13:00 | 2030-07-20 15:00 | 2 | Jacking down at port | OFFSHORE | Working | 21 |  | 17 | 1 |  | Standalone |  | 3 | 2655 | 92.9
2030-07-20 15:00 | 2030-07-20 16:00 | 1 | Port maneuvering | OFFSHORE | Working | 21 |  | 18 | 1 |  | Standalone |  | 1.5 | 2656 | 91.9
2030-07-20 16:00 | 2030-07-20 21:12 | 5.2 | Transit from port to site | OFFSHORE | Working | 21 |  | 19 | 1 |  | Standalone |  | 7.8 | 2661.2 | 86.7
2030-07-20 21:12 | 2030-07-20 21:42 | 0.5 | DP field check | OFFSHORE | Working | 21 |  | 20 | 1 |  | Standalone |  | 0.75 | 2661.7 | 86.2
2030-07-20 21:42 | 2030-07-20 22:42 | 1 | Transit to next foundation | OFFSHORE | Working | 21 | 41 | 21 | 1 |  | Standalone |  | 1.5 | 2662.7 | 85.2
2030-07-20 22:42 | 2030-07-20 23:42 | 1 | Positioning at WTG location | OFFSHORE | Working | 21 | 41 | 22 | 1 |  | Standalone |  | 1.5 | 2663.7 | 84.2
2030-07-20 23:42 | 2030-07-21 03:42 | 4 | Preload and jacking up at site | OFFSHORE | Working | 21 | 41 | 23 | 1 |  | Standalone |  | 6 | 2667.7 | 80.2
2030-07-21 03:42 | 2030-07-21 06:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 21 | 41 | 24 | 1 |  | Standalone |  | 3 | 2670.7 | 77.2
2030-07-21 06:42 | 2030-07-21 07:42 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 21 | 41 | 25 | 1 |  | Standalone |  | 1 | 2671.7 | 76.2
2030-07-21 07:42 | 2030-07-21 09:42 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 21 | 41 | 26 | 1 |  | Standalone |  | 2 | 2673.7 | 74.2
2030-07-21 09:42 | 2030-07-21 10:42 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 21 | 41 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2674.7 | 73.2
2030-07-21 10:42 | 2030-07-21 14:12 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 41 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2678.2 | 69.7
2030-07-21 14:12 | 2030-07-21 14:42 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 21 | 41 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2678.7 | 69.2
2030-07-21 14:42 | 2030-07-21 15:12 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 21 | 41 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2679.2 | 68.7
2030-07-21 15:12 | 2030-07-21 17:27 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 41 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2681.45 | 66.45
2030-07-21 17:27 | 2030-07-21 17:57 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 21 | 41 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2681.95 | 65.95
2030-07-21 17:57 | 2030-07-21 18:27 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 21 | 41 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2682.45 | 65.45
2030-07-21 18:27 | 2030-07-21 20:12 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 41 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2684.2 | 63.7
2030-07-21 20:12 | 2030-07-21 21:42 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 21 | 41 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2685.7 | 62.2
2030-07-21 21:42 | 2030-07-21 23:27 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 41 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2687.45 | 60.45
2030-07-21 23:27 | 2030-07-22 00:57 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 21 | 41 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2688.95 | 58.95
2030-07-22 00:57 | 2030-07-22 02:42 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 41 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2690.7 | 57.2
2030-07-22 02:42 | 2030-07-22 04:12 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 21 | 41 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2692.2 | 55.7
2030-07-22 04:12 | 2030-07-22 05:12 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 21 | 41 | 40 | 1 |  | Standalone |  | 1 | 2693.2 | 54.7
2030-07-22 05:12 | 2030-07-22 06:12 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 21 | 41 | 41 | 1 |  | Standalone |  | 1 | 2694.2 | 53.7
2030-07-22 06:12 | 2030-07-22 09:12 | 3 | Turbine general completion works | OFFSHORE | Working | 21 | 41 | 42 | 1 |  | Standalone |  | 3 | 2697.2 | 50.7
2030-07-22 09:12 | 2030-07-22 12:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 21 | 41 | 43 | 1 |  | Standalone |  | 3 | 2700.2 | 47.7
2030-07-22 12:12 | 2030-07-22 14:12 | 2 | Jacking down at site | OFFSHORE | Working | 21 | 41 | 44 | 1 |  | Standalone |  | 3 | 2702.2 | 45.7
2030-07-22 14:12 | 2030-07-22 15:12 | 1 | Transit to next foundation | OFFSHORE | Working | 21 | 42 | 21 | 1 |  | Standalone |  | 1.5 | 2703.2 | 44.7
2030-07-22 15:12 | 2030-07-22 16:12 | 1 | Positioning at WTG location | OFFSHORE | Working | 21 | 42 | 22 | 1 |  | Standalone |  | 1.5 | 2704.2 | 43.7
2030-07-22 16:12 | 2030-07-22 20:12 | 4 | Preload and jacking up at site | OFFSHORE | Working | 21 | 42 | 23 | 1 |  | Standalone |  | 6 | 2708.2 | 39.7
2030-07-22 20:12 | 2030-07-22 23:12 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working | 21 | 42 | 24 | 1 |  | Standalone |  | 3 | 2711.2 | 36.7
2030-07-22 23:12 | 2030-07-23 00:12 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working | 21 | 42 | 25 | 1 |  | Standalone |  | 1 | 2712.2 | 35.7
2030-07-23 00:12 | 2030-07-23 02:12 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working | 21 | 42 | 26 | 1 |  | Standalone |  | 2 | 2714.2 | 33.7
2030-07-23 02:12 | 2030-07-23 03:12 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working | 21 | 42 | 27 | 1 | G1 | Start | MOST_STRINGENT | 1.5 | 2715.2 | 32.7
2030-07-23 03:12 | 2030-07-23 06:42 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 42 | 28 | 1 | G1 | Continue | MOST_STRINGENT | 5.25 | 2718.7 | 29.2
2030-07-23 06:42 | 2030-07-23 07:12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working | 21 | 42 | 29 | 1 | G1 | End | MOST_STRINGENT | 0.75 | 2719.2 | 28.7
2030-07-23 07:12 | 2030-07-23 07:42 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working | 21 | 42 | 30 | 1 | G2 | Start | MOST_STRINGENT | 0.75 | 2719.7 | 28.2
2030-07-23 07:42 | 2030-07-23 09:57 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 42 | 31 | 1 | G2 | Continue | MOST_STRINGENT | 3.375 | 2721.95 | 25.95
2030-07-23 09:57 | 2030-07-23 10:27 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working | 21 | 42 | 32 | 1 | G2 | End | MOST_STRINGENT | 0.75 | 2722.45 | 25.45
2030-07-23 10:27 | 2030-07-23 10:57 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working | 21 | 42 | 33 | 1 | G3 | Start | MOST_STRINGENT | 0.75 | 2722.95 | 24.95
2030-07-23 10:57 | 2030-07-23 12:42 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 42 | 34 | 1 | G3 | Continue | MOST_STRINGENT | 2.625 | 2724.7 | 23.2
2030-07-23 12:42 | 2030-07-23 14:12 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 21 | 42 | 35 | 1 | G3 | End | MOST_STRINGENT | 2.25 | 2726.2 | 21.7
2030-07-23 14:12 | 2030-07-23 15:57 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 42 | 36 | 1 | G4 | Start | MOST_STRINGENT | 2.625 | 2727.95 | 19.95
2030-07-23 15:57 | 2030-07-23 17:27 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working | 21 | 42 | 37 | 1 | G4 | End | MOST_STRINGENT | 2.25 | 2729.45 | 18.45
2030-07-23 17:27 | 2030-07-23 19:12 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working | 21 | 42 | 38 | 1 | G5 | Start | MOST_STRINGENT | 2.625 | 2731.2 | 16.7
2030-07-23 19:12 | 2030-07-23 20:42 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working | 21 | 42 | 39 | 1 | G5 | End | MOST_STRINGENT | 2.25 | 2732.7 | 15.2
2030-07-23 20:42 | 2030-07-23 21:42 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working | 21 | 42 | 40 | 1 |  | Standalone |  | 1 | 2733.7 | 14.2
2030-07-23 21:42 | 2030-07-23 22:42 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working | 21 | 42 | 41 | 1 |  | Standalone |  | 1 | 2734.7 | 13.2
2030-07-23 22:42 | 2030-07-24 01:42 | 3 | Turbine general completion works | OFFSHORE | Working | 21 | 42 | 42 | 1 |  | Standalone |  | 3 | 2737.7 | 10.2
2030-07-24 01:42 | 2030-07-24 04:42 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working | 21 | 42 | 43 | 1 |  | Standalone |  | 3 | 2740.7 | 7.2
2030-07-24 04:42 | 2030-07-24 06:42 | 2 | Jacking down at site | OFFSHORE | Working | 21 | 42 | 44 | 1 |  | Standalone |  | 3 | 2742.7 | 5.2
2030-07-24 06:42 | 2030-07-24 11:54 | 5.2 | Transit from site to port | OFFSHORE | Working | 21 |  | 45 | 1 |  | Standalone |  | 7.8 | 2747.9 | 1.3642e-12

## OUT_run
OUT_run — Detailed P0 (no weather)
Exact continuous no-weather trace. Weather downtime = 0; simulation-timestep rounding is not applied.
Timestamp | End timestamp | Duration [h] | Activity | Location | Status | Downtime type | Main factor | Downtime category | Cycle | Position | Activity ID | Safe-to-safe group | Group role | Group method | Learning multiplier | Weather window [h] | Cumulative P0 [h] | Remaining campaign [h]
2030-04-01 | 2030-04-01 01:00 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 1 |  | 1 |  | Standalone |  | 1 | 1.5 | 1 | 2746.9
2030-04-01 01:00 | 2030-04-01 03:00 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 1 |  | 2 |  | Standalone |  | 1 | 3 | 3 | 2744.9
2030-04-01 03:00 | 2030-04-01 06:00 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 1 |  | 3 |  | Standalone |  | 1 | 3 | 6 | 2741.9
2030-04-01 06:00 | 2030-04-01 07:30 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 1 |  | 4 |  | Standalone |  | 1.5 | 1 | 7.5 | 2740.4
2030-04-01 07:30 | 2030-04-01 10:52 | 3.375 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 1 |  | 5 |  | Standalone |  | 1.5 | 3.375 | 10.875 | 2737.025
2030-04-01 10:52 | 2030-04-01 14:15 | 3.375 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 1 |  | 6 |  | Standalone |  | 1.5 | 3.375 | 14.25 | 2733.65
2030-04-01 14:15 | 2030-04-01 16:30 | 2.25 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 1 |  | 7 |  | Standalone |  | 1.5 | 2.25 | 16.5 | 2731.4
2030-04-01 16:30 | 2030-04-01 18:45 | 2.25 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 1 |  | 8 |  | Standalone |  | 1.5 | 2.25 | 18.75 | 2729.15
2030-04-01 18:45 | 2030-04-01 21:00 | 2.25 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 1 |  | 9 |  | Standalone |  | 1.5 | 2.25 | 21 | 2726.9
2030-04-01 21:00 | 2030-04-01 22:30 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 1 |  | 10 |  | Standalone |  | 1.5 | 1 | 22.5 | 2725.4
2030-04-01 22:30 | 2030-04-02 01:52 | 3.375 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 1 |  | 11 |  | Standalone |  | 1.5 | 3.375 | 25.875 | 2722.025
2030-04-02 01:52 | 2030-04-02 05:15 | 3.375 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 1 |  | 12 |  | Standalone |  | 1.5 | 3.375 | 29.25 | 2718.65
2030-04-02 05:15 | 2030-04-02 07:30 | 2.25 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 1 |  | 13 |  | Standalone |  | 1.5 | 2.25 | 31.5 | 2716.4
2030-04-02 07:30 | 2030-04-02 09:45 | 2.25 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 1 |  | 14 |  | Standalone |  | 1.5 | 2.25 | 33.75 | 2714.15
2030-04-02 09:45 | 2030-04-02 12:00 | 2.25 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 1 |  | 15 |  | Standalone |  | 1.5 | 2.25 | 36 | 2711.9
2030-04-02 12:00 | 2030-04-02 15:00 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 1 |  | 16 |  | Standalone |  | 1 | 3 | 39 | 2708.9
2030-04-02 15:00 | 2030-04-02 17:00 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 1 |  | 17 |  | Standalone |  | 1 | 3 | 41 | 2706.9
2030-04-02 17:00 | 2030-04-02 18:00 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 1 |  | 18 |  | Standalone |  | 1 | 1.5 | 42 | 2705.9
2030-04-02 18:00 | 2030-04-02 23:12 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 1 |  | 19 |  | Standalone |  | 1 | 7.8 | 47.2 | 2700.7
2030-04-02 23:12 | 2030-04-02 23:42 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 1 |  | 20 |  | Standalone |  | 1 | 0.75 | 47.7 | 2700.2
2030-04-02 23:42 | 2030-04-03 00:42 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 1 | 1 | 21 |  | Standalone |  | 1 | 1.5 | 48.7 | 2699.2
2030-04-03 00:42 | 2030-04-03 01:42 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 1 | 1 | 22 |  | Standalone |  | 1 | 1.5 | 49.7 | 2698.2
2030-04-03 01:42 | 2030-04-03 05:42 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 1 | 1 | 23 |  | Standalone |  | 1 | 6 | 53.7 | 2694.2
2030-04-03 05:42 | 2030-04-03 08:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 1 | 1 | 24 |  | Standalone |  | 1 | 3 | 56.7 | 2691.2
2030-04-03 08:42 | 2030-04-03 10:12 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 1 | 1 | 25 |  | Standalone |  | 1.5 | 1 | 58.2 | 2689.7
2030-04-03 10:12 | 2030-04-03 13:12 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 1 | 1 | 26 |  | Standalone |  | 1.5 | 2 | 61.2 | 2686.7
2030-04-03 13:12 | 2030-04-03 14:42 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 1 | 1 | 27 | G1 | Start | MOST_STRINGENT | 1.5 | 1.5 | 62.7 | 2685.2
2030-04-03 14:42 | 2030-04-03 19:57 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 1 | 28 | G1 | Continue | MOST_STRINGENT | 1.5 | 5.25 | 67.95 | 2679.95
2030-04-03 19:57 | 2030-04-03 20:42 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 1 | 1 | 29 | G1 | End | MOST_STRINGENT | 1.5 | 0.75 | 68.7 | 2679.2
2030-04-03 20:42 | 2030-04-03 21:27 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 1 | 1 | 30 | G2 | Start | MOST_STRINGENT | 1.5 | 0.75 | 69.45 | 2678.45
2030-04-03 21:27 | 2030-04-04 00:50 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 1 | 31 | G2 | Continue | MOST_STRINGENT | 1.5 | 3.375 | 72.825 | 2675.075
2030-04-04 00:50 | 2030-04-04 01:35 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 1 | 1 | 32 | G2 | End | MOST_STRINGENT | 1.5 | 0.75 | 73.575 | 2674.325
2030-04-04 01:35 | 2030-04-04 02:20 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 1 | 1 | 33 | G3 | Start | MOST_STRINGENT | 1.5 | 0.75 | 74.325 | 2673.575
2030-04-04 02:20 | 2030-04-04 04:57 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 1 | 34 | G3 | Continue | MOST_STRINGENT | 1.5 | 2.625 | 76.95 | 2670.95
2030-04-04 04:57 | 2030-04-04 07:12 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 1 | 1 | 35 | G3 | End | MOST_STRINGENT | 1.5 | 2.25 | 79.2 | 2668.7
2030-04-04 07:12 | 2030-04-04 09:50 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 1 | 36 | G4 | Start | MOST_STRINGENT | 1.5 | 2.625 | 81.825 | 2666.075
2030-04-04 09:50 | 2030-04-04 12:05 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 1 | 1 | 37 | G4 | End | MOST_STRINGENT | 1.5 | 2.25 | 84.075 | 2663.825
2030-04-04 12:05 | 2030-04-04 14:42 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 1 | 38 | G5 | Start | MOST_STRINGENT | 1.5 | 2.625 | 86.7 | 2661.2
2030-04-04 14:42 | 2030-04-04 16:57 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 1 | 1 | 39 | G5 | End | MOST_STRINGENT | 1.5 | 2.25 | 88.95 | 2658.95
2030-04-04 16:57 | 2030-04-04 18:27 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 1 | 1 | 40 |  | Standalone |  | 1.5 | 1 | 90.45 | 2657.45
2030-04-04 18:27 | 2030-04-04 19:57 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 1 | 1 | 41 |  | Standalone |  | 1.5 | 1 | 91.95 | 2655.95
2030-04-04 19:57 | 2030-04-05 00:27 | 4.5 | Turbine general completion works | OFFSHORE | Working |  |  |  | 1 | 1 | 42 |  | Standalone |  | 1.5 | 3 | 96.45 | 2651.45
2030-04-05 00:27 | 2030-04-05 03:27 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 1 | 1 | 43 |  | Standalone |  | 1 | 3 | 99.45 | 2648.45
2030-04-05 03:27 | 2030-04-05 05:27 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 1 | 1 | 44 |  | Standalone |  | 1 | 3 | 101.45 | 2646.45
2030-04-05 05:27 | 2030-04-05 06:27 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 1 | 2 | 21 |  | Standalone |  | 1 | 1.5 | 102.45 | 2645.45
2030-04-05 06:27 | 2030-04-05 07:27 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 1 | 2 | 22 |  | Standalone |  | 1 | 1.5 | 103.45 | 2644.45
2030-04-05 07:27 | 2030-04-05 11:27 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 1 | 2 | 23 |  | Standalone |  | 1 | 6 | 107.45 | 2640.45
2030-04-05 11:27 | 2030-04-05 14:27 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 1 | 2 | 24 |  | Standalone |  | 1 | 3 | 110.45 | 2637.45
2030-04-05 14:27 | 2030-04-05 15:57 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 1 | 2 | 25 |  | Standalone |  | 1.5 | 1 | 111.95 | 2635.95
2030-04-05 15:57 | 2030-04-05 18:57 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 1 | 2 | 26 |  | Standalone |  | 1.5 | 2 | 114.95 | 2632.95
2030-04-05 18:57 | 2030-04-05 20:27 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 1 | 2 | 27 | G1 | Start | MOST_STRINGENT | 1.5 | 1.5 | 116.45 | 2631.45
2030-04-05 20:27 | 2030-04-06 01:42 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 2 | 28 | G1 | Continue | MOST_STRINGENT | 1.5 | 5.25 | 121.7 | 2626.2
2030-04-06 01:42 | 2030-04-06 02:27 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 1 | 2 | 29 | G1 | End | MOST_STRINGENT | 1.5 | 0.75 | 122.45 | 2625.45
2030-04-06 02:27 | 2030-04-06 03:12 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 1 | 2 | 30 | G2 | Start | MOST_STRINGENT | 1.5 | 0.75 | 123.2 | 2624.7
2030-04-06 03:12 | 2030-04-06 06:34 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 2 | 31 | G2 | Continue | MOST_STRINGENT | 1.5 | 3.375 | 126.575 | 2621.325
2030-04-06 06:34 | 2030-04-06 07:20 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 1 | 2 | 32 | G2 | End | MOST_STRINGENT | 1.5 | 0.75 | 127.325 | 2620.575
2030-04-06 07:20 | 2030-04-06 08:04 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 1 | 2 | 33 | G3 | Start | MOST_STRINGENT | 1.5 | 0.75 | 128.075 | 2619.825
2030-04-06 08:04 | 2030-04-06 10:42 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 2 | 34 | G3 | Continue | MOST_STRINGENT | 1.5 | 2.625 | 130.7 | 2617.2
2030-04-06 10:42 | 2030-04-06 12:57 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 1 | 2 | 35 | G3 | End | MOST_STRINGENT | 1.5 | 2.25 | 132.95 | 2614.95
2030-04-06 12:57 | 2030-04-06 15:34 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 2 | 36 | G4 | Start | MOST_STRINGENT | 1.5 | 2.625 | 135.575 | 2612.325
2030-04-06 15:34 | 2030-04-06 17:50 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 1 | 2 | 37 | G4 | End | MOST_STRINGENT | 1.5 | 2.25 | 137.825 | 2610.075
2030-04-06 17:50 | 2030-04-06 20:27 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 1 | 2 | 38 | G5 | Start | MOST_STRINGENT | 1.5 | 2.625 | 140.45 | 2607.45
2030-04-06 20:27 | 2030-04-06 22:42 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 1 | 2 | 39 | G5 | End | MOST_STRINGENT | 1.5 | 2.25 | 142.7 | 2605.2
2030-04-06 22:42 | 2030-04-07 00:12 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 1 | 2 | 40 |  | Standalone |  | 1.5 | 1 | 144.2 | 2603.7
2030-04-07 00:12 | 2030-04-07 01:42 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 1 | 2 | 41 |  | Standalone |  | 1.5 | 1 | 145.7 | 2602.2
2030-04-07 01:42 | 2030-04-07 06:12 | 4.5 | Turbine general completion works | OFFSHORE | Working |  |  |  | 1 | 2 | 42 |  | Standalone |  | 1.5 | 3 | 150.2 | 2597.7
2030-04-07 06:12 | 2030-04-07 09:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 1 | 2 | 43 |  | Standalone |  | 1 | 3 | 153.2 | 2594.7
2030-04-07 09:12 | 2030-04-07 11:12 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 1 | 2 | 44 |  | Standalone |  | 1 | 3 | 155.2 | 2592.7
2030-04-07 11:12 | 2030-04-07 16:24 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 1 |  | 45 |  | Standalone |  | 1 | 7.8 | 160.4 | 2587.5
2030-04-07 16:24 | 2030-04-07 17:24 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 2 |  | 1 |  | Standalone |  | 1 | 1.5 | 161.4 | 2586.5
2030-04-07 17:24 | 2030-04-07 19:24 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 2 |  | 2 |  | Standalone |  | 1 | 3 | 163.4 | 2584.5
2030-04-07 19:24 | 2030-04-07 22:24 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 2 |  | 3 |  | Standalone |  | 1 | 3 | 166.4 | 2581.5
2030-04-07 22:24 | 2030-04-07 23:54 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 2 |  | 4 |  | Standalone |  | 1.5 | 1 | 167.9 | 2580
2030-04-07 23:54 | 2030-04-08 03:16 | 3.375 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 2 |  | 5 |  | Standalone |  | 1.5 | 3.375 | 171.275 | 2576.625
2030-04-08 03:16 | 2030-04-08 06:39 | 3.375 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 2 |  | 6 |  | Standalone |  | 1.5 | 3.375 | 174.65 | 2573.25
2030-04-08 06:39 | 2030-04-08 08:54 | 2.25 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 2 |  | 7 |  | Standalone |  | 1.5 | 2.25 | 176.9 | 2571
2030-04-08 08:54 | 2030-04-08 11:09 | 2.25 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 2 |  | 8 |  | Standalone |  | 1.5 | 2.25 | 179.15 | 2568.75
2030-04-08 11:09 | 2030-04-08 13:24 | 2.25 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 2 |  | 9 |  | Standalone |  | 1.5 | 2.25 | 181.4 | 2566.5
2030-04-08 13:24 | 2030-04-08 14:54 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 2 |  | 10 |  | Standalone |  | 1.5 | 1 | 182.9 | 2565
2030-04-08 14:54 | 2030-04-08 18:16 | 3.375 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 2 |  | 11 |  | Standalone |  | 1.5 | 3.375 | 186.275 | 2561.625
2030-04-08 18:16 | 2030-04-08 21:39 | 3.375 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 2 |  | 12 |  | Standalone |  | 1.5 | 3.375 | 189.65 | 2558.25
2030-04-08 21:39 | 2030-04-08 23:54 | 2.25 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 2 |  | 13 |  | Standalone |  | 1.5 | 2.25 | 191.9 | 2556
2030-04-08 23:54 | 2030-04-09 02:09 | 2.25 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 2 |  | 14 |  | Standalone |  | 1.5 | 2.25 | 194.15 | 2553.75
2030-04-09 02:09 | 2030-04-09 04:24 | 2.25 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 2 |  | 15 |  | Standalone |  | 1.5 | 2.25 | 196.4 | 2551.5
2030-04-09 04:24 | 2030-04-09 07:24 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 2 |  | 16 |  | Standalone |  | 1 | 3 | 199.4 | 2548.5
2030-04-09 07:24 | 2030-04-09 09:24 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 2 |  | 17 |  | Standalone |  | 1 | 3 | 201.4 | 2546.5
2030-04-09 09:24 | 2030-04-09 10:24 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 2 |  | 18 |  | Standalone |  | 1 | 1.5 | 202.4 | 2545.5
2030-04-09 10:24 | 2030-04-09 15:36 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 2 |  | 19 |  | Standalone |  | 1 | 7.8 | 207.6 | 2540.3
2030-04-09 15:36 | 2030-04-09 16:06 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 2 |  | 20 |  | Standalone |  | 1 | 0.75 | 208.1 | 2539.8
2030-04-09 16:06 | 2030-04-09 17:06 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 2 | 3 | 21 |  | Standalone |  | 1 | 1.5 | 209.1 | 2538.8
2030-04-09 17:06 | 2030-04-09 18:06 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 2 | 3 | 22 |  | Standalone |  | 1 | 1.5 | 210.1 | 2537.8
2030-04-09 18:06 | 2030-04-09 22:06 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 2 | 3 | 23 |  | Standalone |  | 1 | 6 | 214.1 | 2533.8
2030-04-09 22:06 | 2030-04-10 01:06 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 2 | 3 | 24 |  | Standalone |  | 1 | 3 | 217.1 | 2530.8
2030-04-10 01:06 | 2030-04-10 02:36 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 2 | 3 | 25 |  | Standalone |  | 1.5 | 1 | 218.6 | 2529.3
2030-04-10 02:36 | 2030-04-10 05:36 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 2 | 3 | 26 |  | Standalone |  | 1.5 | 2 | 221.6 | 2526.3
2030-04-10 05:36 | 2030-04-10 07:06 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 2 | 3 | 27 | G1 | Start | MOST_STRINGENT | 1.5 | 1.5 | 223.1 | 2524.8
2030-04-10 07:06 | 2030-04-10 12:21 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 3 | 28 | G1 | Continue | MOST_STRINGENT | 1.5 | 5.25 | 228.35 | 2519.55
2030-04-10 12:21 | 2030-04-10 13:06 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 2 | 3 | 29 | G1 | End | MOST_STRINGENT | 1.5 | 0.75 | 229.1 | 2518.8
2030-04-10 13:06 | 2030-04-10 13:51 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 2 | 3 | 30 | G2 | Start | MOST_STRINGENT | 1.5 | 0.75 | 229.85 | 2518.05
2030-04-10 13:51 | 2030-04-10 17:13 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 3 | 31 | G2 | Continue | MOST_STRINGENT | 1.5 | 3.375 | 233.225 | 2514.675
2030-04-10 17:13 | 2030-04-10 17:58 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 2 | 3 | 32 | G2 | End | MOST_STRINGENT | 1.5 | 0.75 | 233.975 | 2513.925
2030-04-10 17:58 | 2030-04-10 18:43 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 2 | 3 | 33 | G3 | Start | MOST_STRINGENT | 1.5 | 0.75 | 234.725 | 2513.175
2030-04-10 18:43 | 2030-04-10 21:21 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 3 | 34 | G3 | Continue | MOST_STRINGENT | 1.5 | 2.625 | 237.35 | 2510.55
2030-04-10 21:21 | 2030-04-10 23:36 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 2 | 3 | 35 | G3 | End | MOST_STRINGENT | 1.5 | 2.25 | 239.6 | 2508.3
2030-04-10 23:36 | 2030-04-11 02:13 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 3 | 36 | G4 | Start | MOST_STRINGENT | 1.5 | 2.625 | 242.225 | 2505.675
2030-04-11 02:13 | 2030-04-11 04:28 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 2 | 3 | 37 | G4 | End | MOST_STRINGENT | 1.5 | 2.25 | 244.475 | 2503.425
2030-04-11 04:28 | 2030-04-11 07:06 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 3 | 38 | G5 | Start | MOST_STRINGENT | 1.5 | 2.625 | 247.1 | 2500.8
2030-04-11 07:06 | 2030-04-11 09:21 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 2 | 3 | 39 | G5 | End | MOST_STRINGENT | 1.5 | 2.25 | 249.35 | 2498.55
2030-04-11 09:21 | 2030-04-11 10:51 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 2 | 3 | 40 |  | Standalone |  | 1.5 | 1 | 250.85 | 2497.05
2030-04-11 10:51 | 2030-04-11 12:21 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 2 | 3 | 41 |  | Standalone |  | 1.5 | 1 | 252.35 | 2495.55
2030-04-11 12:21 | 2030-04-11 16:51 | 4.5 | Turbine general completion works | OFFSHORE | Working |  |  |  | 2 | 3 | 42 |  | Standalone |  | 1.5 | 3 | 256.85 | 2491.05
2030-04-11 16:51 | 2030-04-11 19:51 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 2 | 3 | 43 |  | Standalone |  | 1 | 3 | 259.85 | 2488.05
2030-04-11 19:51 | 2030-04-11 21:51 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 2 | 3 | 44 |  | Standalone |  | 1 | 3 | 261.85 | 2486.05
2030-04-11 21:51 | 2030-04-11 22:51 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 2 | 4 | 21 |  | Standalone |  | 1 | 1.5 | 262.85 | 2485.05
2030-04-11 22:51 | 2030-04-11 23:51 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 2 | 4 | 22 |  | Standalone |  | 1 | 1.5 | 263.85 | 2484.05
2030-04-11 23:51 | 2030-04-12 03:51 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 2 | 4 | 23 |  | Standalone |  | 1 | 6 | 267.85 | 2480.05
2030-04-12 03:51 | 2030-04-12 06:51 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 2 | 4 | 24 |  | Standalone |  | 1 | 3 | 270.85 | 2477.05
2030-04-12 06:51 | 2030-04-12 08:21 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 2 | 4 | 25 |  | Standalone |  | 1.5 | 1 | 272.35 | 2475.55
2030-04-12 08:21 | 2030-04-12 11:21 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 2 | 4 | 26 |  | Standalone |  | 1.5 | 2 | 275.35 | 2472.55
2030-04-12 11:21 | 2030-04-12 12:51 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 2 | 4 | 27 | G1 | Start | MOST_STRINGENT | 1.5 | 1.5 | 276.85 | 2471.05
2030-04-12 12:51 | 2030-04-12 18:06 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 4 | 28 | G1 | Continue | MOST_STRINGENT | 1.5 | 5.25 | 282.1 | 2465.8
2030-04-12 18:06 | 2030-04-12 18:51 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 2 | 4 | 29 | G1 | End | MOST_STRINGENT | 1.5 | 0.75 | 282.85 | 2465.05
2030-04-12 18:51 | 2030-04-12 19:36 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 2 | 4 | 30 | G2 | Start | MOST_STRINGENT | 1.5 | 0.75 | 283.6 | 2464.3
2030-04-12 19:36 | 2030-04-12 22:59 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 4 | 31 | G2 | Continue | MOST_STRINGENT | 1.5 | 3.375 | 286.975 | 2460.925
2030-04-12 22:59 | 2030-04-12 23:44 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 2 | 4 | 32 | G2 | End | MOST_STRINGENT | 1.5 | 0.75 | 287.725 | 2460.175
2030-04-12 23:44 | 2030-04-13 00:29 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 2 | 4 | 33 | G3 | Start | MOST_STRINGENT | 1.5 | 0.75 | 288.475 | 2459.425
2030-04-13 00:29 | 2030-04-13 03:06 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 4 | 34 | G3 | Continue | MOST_STRINGENT | 1.5 | 2.625 | 291.1 | 2456.8
2030-04-13 03:06 | 2030-04-13 05:21 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 2 | 4 | 35 | G3 | End | MOST_STRINGENT | 1.5 | 2.25 | 293.35 | 2454.55
2030-04-13 05:21 | 2030-04-13 07:59 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 4 | 36 | G4 | Start | MOST_STRINGENT | 1.5 | 2.625 | 295.975 | 2451.925
2030-04-13 07:59 | 2030-04-13 10:14 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 2 | 4 | 37 | G4 | End | MOST_STRINGENT | 1.5 | 2.25 | 298.225 | 2449.675
2030-04-13 10:14 | 2030-04-13 12:51 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 2 | 4 | 38 | G5 | Start | MOST_STRINGENT | 1.5 | 2.625 | 300.85 | 2447.05
2030-04-13 12:51 | 2030-04-13 15:06 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 2 | 4 | 39 | G5 | End | MOST_STRINGENT | 1.5 | 2.25 | 303.1 | 2444.8
2030-04-13 15:06 | 2030-04-13 16:36 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 2 | 4 | 40 |  | Standalone |  | 1.5 | 1 | 304.6 | 2443.3
2030-04-13 16:36 | 2030-04-13 18:06 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 2 | 4 | 41 |  | Standalone |  | 1.5 | 1 | 306.1 | 2441.8
2030-04-13 18:06 | 2030-04-13 22:36 | 4.5 | Turbine general completion works | OFFSHORE | Working |  |  |  | 2 | 4 | 42 |  | Standalone |  | 1.5 | 3 | 310.6 | 2437.3
2030-04-13 22:36 | 2030-04-14 01:36 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 2 | 4 | 43 |  | Standalone |  | 1 | 3 | 313.6 | 2434.3
2030-04-14 01:36 | 2030-04-14 03:36 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 2 | 4 | 44 |  | Standalone |  | 1 | 3 | 315.6 | 2432.3
2030-04-14 03:36 | 2030-04-14 08:48 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 2 |  | 45 |  | Standalone |  | 1 | 7.8 | 320.8 | 2427.1
2030-04-14 08:48 | 2030-04-14 09:48 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 3 |  | 1 |  | Standalone |  | 1 | 1.5 | 321.8 | 2426.1
2030-04-14 09:48 | 2030-04-14 11:48 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 3 |  | 2 |  | Standalone |  | 1 | 3 | 323.8 | 2424.1
2030-04-14 11:48 | 2030-04-14 14:48 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 3 |  | 3 |  | Standalone |  | 1 | 3 | 326.8 | 2421.1
2030-04-14 14:48 | 2030-04-14 16:18 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 3 |  | 4 |  | Standalone |  | 1.5 | 1 | 328.3 | 2419.6
2030-04-14 16:18 | 2030-04-14 19:40 | 3.375 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 3 |  | 5 |  | Standalone |  | 1.5 | 3.375 | 331.675 | 2416.225
2030-04-14 19:40 | 2030-04-14 23:03 | 3.375 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 3 |  | 6 |  | Standalone |  | 1.5 | 3.375 | 335.05 | 2412.85
2030-04-14 23:03 | 2030-04-15 01:18 | 2.25 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 3 |  | 7 |  | Standalone |  | 1.5 | 2.25 | 337.3 | 2410.6
2030-04-15 01:18 | 2030-04-15 03:33 | 2.25 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 3 |  | 8 |  | Standalone |  | 1.5 | 2.25 | 339.55 | 2408.35
2030-04-15 03:33 | 2030-04-15 05:48 | 2.25 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 3 |  | 9 |  | Standalone |  | 1.5 | 2.25 | 341.8 | 2406.1
2030-04-15 05:48 | 2030-04-15 07:18 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 3 |  | 10 |  | Standalone |  | 1.5 | 1 | 343.3 | 2404.6
2030-04-15 07:18 | 2030-04-15 10:40 | 3.375 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 3 |  | 11 |  | Standalone |  | 1.5 | 3.375 | 346.675 | 2401.225
2030-04-15 10:40 | 2030-04-15 14:03 | 3.375 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 3 |  | 12 |  | Standalone |  | 1.5 | 3.375 | 350.05 | 2397.85
2030-04-15 14:03 | 2030-04-15 16:18 | 2.25 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 3 |  | 13 |  | Standalone |  | 1.5 | 2.25 | 352.3 | 2395.6
2030-04-15 16:18 | 2030-04-15 18:33 | 2.25 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 3 |  | 14 |  | Standalone |  | 1.5 | 2.25 | 354.55 | 2393.35
2030-04-15 18:33 | 2030-04-15 20:48 | 2.25 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 3 |  | 15 |  | Standalone |  | 1.5 | 2.25 | 356.8 | 2391.1
2030-04-15 20:48 | 2030-04-15 23:48 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 3 |  | 16 |  | Standalone |  | 1 | 3 | 359.8 | 2388.1
2030-04-15 23:48 | 2030-04-16 01:48 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 3 |  | 17 |  | Standalone |  | 1 | 3 | 361.8 | 2386.1
2030-04-16 01:48 | 2030-04-16 02:48 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 3 |  | 18 |  | Standalone |  | 1 | 1.5 | 362.8 | 2385.1
2030-04-16 02:48 | 2030-04-16 08:00 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 3 |  | 19 |  | Standalone |  | 1 | 7.8 | 368 | 2379.9
2030-04-16 08:00 | 2030-04-16 08:30 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 3 |  | 20 |  | Standalone |  | 1 | 0.75 | 368.5 | 2379.4
2030-04-16 08:30 | 2030-04-16 09:30 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 3 | 5 | 21 |  | Standalone |  | 1 | 1.5 | 369.5 | 2378.4
2030-04-16 09:30 | 2030-04-16 10:30 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 3 | 5 | 22 |  | Standalone |  | 1 | 1.5 | 370.5 | 2377.4
2030-04-16 10:30 | 2030-04-16 14:30 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 3 | 5 | 23 |  | Standalone |  | 1 | 6 | 374.5 | 2373.4
2030-04-16 14:30 | 2030-04-16 17:30 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 3 | 5 | 24 |  | Standalone |  | 1 | 3 | 377.5 | 2370.4
2030-04-16 17:30 | 2030-04-16 19:00 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 3 | 5 | 25 |  | Standalone |  | 1.5 | 1 | 379 | 2368.9
2030-04-16 19:00 | 2030-04-16 22:00 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 3 | 5 | 26 |  | Standalone |  | 1.5 | 2 | 382 | 2365.9
2030-04-16 22:00 | 2030-04-16 23:30 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 3 | 5 | 27 | G1 | Start | MOST_STRINGENT | 1.5 | 1.5 | 383.5 | 2364.4
2030-04-16 23:30 | 2030-04-17 04:45 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 5 | 28 | G1 | Continue | MOST_STRINGENT | 1.5 | 5.25 | 388.75 | 2359.15
2030-04-17 04:45 | 2030-04-17 05:30 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 3 | 5 | 29 | G1 | End | MOST_STRINGENT | 1.5 | 0.75 | 389.5 | 2358.4
2030-04-17 05:30 | 2030-04-17 06:15 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 3 | 5 | 30 | G2 | Start | MOST_STRINGENT | 1.5 | 0.75 | 390.25 | 2357.65
2030-04-17 06:15 | 2030-04-17 09:37 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 5 | 31 | G2 | Continue | MOST_STRINGENT | 1.5 | 3.375 | 393.625 | 2354.275
2030-04-17 09:37 | 2030-04-17 10:22 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 3 | 5 | 32 | G2 | End | MOST_STRINGENT | 1.5 | 0.75 | 394.375 | 2353.525
2030-04-17 10:22 | 2030-04-17 11:07 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 3 | 5 | 33 | G3 | Start | MOST_STRINGENT | 1.5 | 0.75 | 395.125 | 2352.775
2030-04-17 11:07 | 2030-04-17 13:45 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 5 | 34 | G3 | Continue | MOST_STRINGENT | 1.5 | 2.625 | 397.75 | 2350.15
2030-04-17 13:45 | 2030-04-17 16:00 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 3 | 5 | 35 | G3 | End | MOST_STRINGENT | 1.5 | 2.25 | 400 | 2347.9
2030-04-17 16:00 | 2030-04-17 18:37 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 5 | 36 | G4 | Start | MOST_STRINGENT | 1.5 | 2.625 | 402.625 | 2345.275
2030-04-17 18:37 | 2030-04-17 20:52 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 3 | 5 | 37 | G4 | End | MOST_STRINGENT | 1.5 | 2.25 | 404.875 | 2343.025
2030-04-17 20:52 | 2030-04-17 23:30 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 5 | 38 | G5 | Start | MOST_STRINGENT | 1.5 | 2.625 | 407.5 | 2340.4
2030-04-17 23:30 | 2030-04-18 01:45 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 3 | 5 | 39 | G5 | End | MOST_STRINGENT | 1.5 | 2.25 | 409.75 | 2338.15
2030-04-18 01:45 | 2030-04-18 03:15 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 3 | 5 | 40 |  | Standalone |  | 1.5 | 1 | 411.25 | 2336.65
2030-04-18 03:15 | 2030-04-18 04:45 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 3 | 5 | 41 |  | Standalone |  | 1.5 | 1 | 412.75 | 2335.15
2030-04-18 04:45 | 2030-04-18 09:15 | 4.5 | Turbine general completion works | OFFSHORE | Working |  |  |  | 3 | 5 | 42 |  | Standalone |  | 1.5 | 3 | 417.25 | 2330.65
2030-04-18 09:15 | 2030-04-18 12:15 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 3 | 5 | 43 |  | Standalone |  | 1 | 3 | 420.25 | 2327.65
2030-04-18 12:15 | 2030-04-18 14:15 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 3 | 5 | 44 |  | Standalone |  | 1 | 3 | 422.25 | 2325.65
2030-04-18 14:15 | 2030-04-18 15:15 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 3 | 6 | 21 |  | Standalone |  | 1 | 1.5 | 423.25 | 2324.65
2030-04-18 15:15 | 2030-04-18 16:15 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 3 | 6 | 22 |  | Standalone |  | 1 | 1.5 | 424.25 | 2323.65
2030-04-18 16:15 | 2030-04-18 20:15 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 3 | 6 | 23 |  | Standalone |  | 1 | 6 | 428.25 | 2319.65
2030-04-18 20:15 | 2030-04-18 23:15 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 3 | 6 | 24 |  | Standalone |  | 1 | 3 | 431.25 | 2316.65
2030-04-18 23:15 | 2030-04-19 00:45 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 3 | 6 | 25 |  | Standalone |  | 1.5 | 1 | 432.75 | 2315.15
2030-04-19 00:45 | 2030-04-19 03:45 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 3 | 6 | 26 |  | Standalone |  | 1.5 | 2 | 435.75 | 2312.15
2030-04-19 03:45 | 2030-04-19 05:15 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 3 | 6 | 27 | G1 | Start | MOST_STRINGENT | 1.5 | 1.5 | 437.25 | 2310.65
2030-04-19 05:15 | 2030-04-19 10:30 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 6 | 28 | G1 | Continue | MOST_STRINGENT | 1.5 | 5.25 | 442.5 | 2305.4
2030-04-19 10:30 | 2030-04-19 11:15 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 3 | 6 | 29 | G1 | End | MOST_STRINGENT | 1.5 | 0.75 | 443.25 | 2304.65
2030-04-19 11:15 | 2030-04-19 12:00 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 3 | 6 | 30 | G2 | Start | MOST_STRINGENT | 1.5 | 0.75 | 444 | 2303.9
2030-04-19 12:00 | 2030-04-19 15:22 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 6 | 31 | G2 | Continue | MOST_STRINGENT | 1.5 | 3.375 | 447.375 | 2300.525
2030-04-19 15:22 | 2030-04-19 16:08 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 3 | 6 | 32 | G2 | End | MOST_STRINGENT | 1.5 | 0.75 | 448.125 | 2299.775
2030-04-19 16:08 | 2030-04-19 16:52 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 3 | 6 | 33 | G3 | Start | MOST_STRINGENT | 1.5 | 0.75 | 448.875 | 2299.025
2030-04-19 16:52 | 2030-04-19 19:30 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 6 | 34 | G3 | Continue | MOST_STRINGENT | 1.5 | 2.625 | 451.5 | 2296.4
2030-04-19 19:30 | 2030-04-19 21:45 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 3 | 6 | 35 | G3 | End | MOST_STRINGENT | 1.5 | 2.25 | 453.75 | 2294.15
2030-04-19 21:45 | 2030-04-20 00:22 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 6 | 36 | G4 | Start | MOST_STRINGENT | 1.5 | 2.625 | 456.375 | 2291.525
2030-04-20 00:22 | 2030-04-20 02:38 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 3 | 6 | 37 | G4 | End | MOST_STRINGENT | 1.5 | 2.25 | 458.625 | 2289.275
2030-04-20 02:38 | 2030-04-20 05:15 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 3 | 6 | 38 | G5 | Start | MOST_STRINGENT | 1.5 | 2.625 | 461.25 | 2286.65
2030-04-20 05:15 | 2030-04-20 07:30 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 3 | 6 | 39 | G5 | End | MOST_STRINGENT | 1.5 | 2.25 | 463.5 | 2284.4
2030-04-20 07:30 | 2030-04-20 09:00 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 3 | 6 | 40 |  | Standalone |  | 1.5 | 1 | 465 | 2282.9
2030-04-20 09:00 | 2030-04-20 10:30 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 3 | 6 | 41 |  | Standalone |  | 1.5 | 1 | 466.5 | 2281.4
2030-04-20 10:30 | 2030-04-20 15:00 | 4.5 | Turbine general completion works | OFFSHORE | Working |  |  |  | 3 | 6 | 42 |  | Standalone |  | 1.5 | 3 | 471 | 2276.9
2030-04-20 15:00 | 2030-04-20 18:00 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 3 | 6 | 43 |  | Standalone |  | 1 | 3 | 474 | 2273.9
2030-04-20 18:00 | 2030-04-20 20:00 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 3 | 6 | 44 |  | Standalone |  | 1 | 3 | 476 | 2271.9
2030-04-20 20:00 | 2030-04-21 01:12 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 3 |  | 45 |  | Standalone |  | 1 | 7.8 | 481.2 | 2266.7
2030-04-21 01:12 | 2030-04-21 02:12 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 4 |  | 1 |  | Standalone |  | 1 | 1.5 | 482.2 | 2265.7
2030-04-21 02:12 | 2030-04-21 04:12 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 4 |  | 2 |  | Standalone |  | 1 | 3 | 484.2 | 2263.7
2030-04-21 04:12 | 2030-04-21 07:12 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 4 |  | 3 |  | Standalone |  | 1 | 3 | 487.2 | 2260.7
2030-04-21 07:12 | 2030-04-21 08:42 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 4 |  | 4 |  | Standalone |  | 1.5 | 1 | 488.7 | 2259.2
2030-04-21 08:42 | 2030-04-21 12:05 | 3.375 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 4 |  | 5 |  | Standalone |  | 1.5 | 3.375 | 492.075 | 2255.825
2030-04-21 12:05 | 2030-04-21 15:27 | 3.375 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 4 |  | 6 |  | Standalone |  | 1.5 | 3.375 | 495.45 | 2252.45
2030-04-21 15:27 | 2030-04-21 17:42 | 2.25 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 4 |  | 7 |  | Standalone |  | 1.5 | 2.25 | 497.7 | 2250.2
2030-04-21 17:42 | 2030-04-21 19:57 | 2.25 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 4 |  | 8 |  | Standalone |  | 1.5 | 2.25 | 499.95 | 2247.95
2030-04-21 19:57 | 2030-04-21 22:12 | 2.25 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 4 |  | 9 |  | Standalone |  | 1.5 | 2.25 | 502.2 | 2245.7
2030-04-21 22:12 | 2030-04-21 23:42 | 1.5 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 4 |  | 10 |  | Standalone |  | 1.5 | 1 | 503.7 | 2244.2
2030-04-21 23:42 | 2030-04-22 03:05 | 3.375 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 4 |  | 11 |  | Standalone |  | 1.5 | 3.375 | 507.075 | 2240.825
2030-04-22 03:05 | 2030-04-22 06:27 | 3.375 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 4 |  | 12 |  | Standalone |  | 1.5 | 3.375 | 510.45 | 2237.45
2030-04-22 06:27 | 2030-04-22 08:42 | 2.25 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 4 |  | 13 |  | Standalone |  | 1.5 | 2.25 | 512.7 | 2235.2
2030-04-22 08:42 | 2030-04-22 10:57 | 2.25 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 4 |  | 14 |  | Standalone |  | 1.5 | 2.25 | 514.95 | 2232.95
2030-04-22 10:57 | 2030-04-22 13:12 | 2.25 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 4 |  | 15 |  | Standalone |  | 1.5 | 2.25 | 517.2 | 2230.7
2030-04-22 13:12 | 2030-04-22 16:12 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 4 |  | 16 |  | Standalone |  | 1 | 3 | 520.2 | 2227.7
2030-04-22 16:12 | 2030-04-22 18:12 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 4 |  | 17 |  | Standalone |  | 1 | 3 | 522.2 | 2225.7
2030-04-22 18:12 | 2030-04-22 19:12 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 4 |  | 18 |  | Standalone |  | 1 | 1.5 | 523.2 | 2224.7
2030-04-22 19:12 | 2030-04-23 00:24 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 4 |  | 19 |  | Standalone |  | 1 | 7.8 | 528.4 | 2219.5
2030-04-23 00:24 | 2030-04-23 00:54 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 4 |  | 20 |  | Standalone |  | 1 | 0.75 | 528.9 | 2219
2030-04-23 00:54 | 2030-04-23 01:54 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 4 | 7 | 21 |  | Standalone |  | 1 | 1.5 | 529.9 | 2218
2030-04-23 01:54 | 2030-04-23 02:54 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 4 | 7 | 22 |  | Standalone |  | 1 | 1.5 | 530.9 | 2217
2030-04-23 02:54 | 2030-04-23 06:54 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 4 | 7 | 23 |  | Standalone |  | 1 | 6 | 534.9 | 2213
2030-04-23 06:54 | 2030-04-23 09:54 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 4 | 7 | 24 |  | Standalone |  | 1 | 3 | 537.9 | 2210
2030-04-23 09:54 | 2030-04-23 11:24 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 4 | 7 | 25 |  | Standalone |  | 1.5 | 1 | 539.4 | 2208.5
2030-04-23 11:24 | 2030-04-23 14:24 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 4 | 7 | 26 |  | Standalone |  | 1.5 | 2 | 542.4 | 2205.5
2030-04-23 14:24 | 2030-04-23 15:54 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 4 | 7 | 27 | G1 | Start | MOST_STRINGENT | 1.5 | 1.5 | 543.9 | 2204
2030-04-23 15:54 | 2030-04-23 21:09 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 7 | 28 | G1 | Continue | MOST_STRINGENT | 1.5 | 5.25 | 549.15 | 2198.75
2030-04-23 21:09 | 2030-04-23 21:54 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 4 | 7 | 29 | G1 | End | MOST_STRINGENT | 1.5 | 0.75 | 549.9 | 2198
2030-04-23 21:54 | 2030-04-23 22:39 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 4 | 7 | 30 | G2 | Start | MOST_STRINGENT | 1.5 | 0.75 | 550.65 | 2197.25
2030-04-23 22:39 | 2030-04-24 02:02 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 7 | 31 | G2 | Continue | MOST_STRINGENT | 1.5 | 3.375 | 554.025 | 2193.875
2030-04-24 02:02 | 2030-04-24 02:46 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 4 | 7 | 32 | G2 | End | MOST_STRINGENT | 1.5 | 0.75 | 554.775 | 2193.125
2030-04-24 02:46 | 2030-04-24 03:32 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 4 | 7 | 33 | G3 | Start | MOST_STRINGENT | 1.5 | 0.75 | 555.525 | 2192.375
2030-04-24 03:32 | 2030-04-24 06:09 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 7 | 34 | G3 | Continue | MOST_STRINGENT | 1.5 | 2.625 | 558.15 | 2189.75
2030-04-24 06:09 | 2030-04-24 08:24 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 4 | 7 | 35 | G3 | End | MOST_STRINGENT | 1.5 | 2.25 | 560.4 | 2187.5
2030-04-24 08:24 | 2030-04-24 11:02 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 7 | 36 | G4 | Start | MOST_STRINGENT | 1.5 | 2.625 | 563.025 | 2184.875
2030-04-24 11:02 | 2030-04-24 13:16 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 4 | 7 | 37 | G4 | End | MOST_STRINGENT | 1.5 | 2.25 | 565.275 | 2182.625
2030-04-24 13:16 | 2030-04-24 15:54 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 7 | 38 | G5 | Start | MOST_STRINGENT | 1.5 | 2.625 | 567.9 | 2180
2030-04-24 15:54 | 2030-04-24 18:09 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 4 | 7 | 39 | G5 | End | MOST_STRINGENT | 1.5 | 2.25 | 570.15 | 2177.75
2030-04-24 18:09 | 2030-04-24 19:39 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 4 | 7 | 40 |  | Standalone |  | 1.5 | 1 | 571.65 | 2176.25
2030-04-24 19:39 | 2030-04-24 21:09 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 4 | 7 | 41 |  | Standalone |  | 1.5 | 1 | 573.15 | 2174.75
2030-04-24 21:09 | 2030-04-25 01:39 | 4.5 | Turbine general completion works | OFFSHORE | Working |  |  |  | 4 | 7 | 42 |  | Standalone |  | 1.5 | 3 | 577.65 | 2170.25
2030-04-25 01:39 | 2030-04-25 04:39 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 4 | 7 | 43 |  | Standalone |  | 1 | 3 | 580.65 | 2167.25
2030-04-25 04:39 | 2030-04-25 06:39 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 4 | 7 | 44 |  | Standalone |  | 1 | 3 | 582.65 | 2165.25
2030-04-25 06:39 | 2030-04-25 07:39 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 4 | 8 | 21 |  | Standalone |  | 1 | 1.5 | 583.65 | 2164.25
2030-04-25 07:39 | 2030-04-25 08:39 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 4 | 8 | 22 |  | Standalone |  | 1 | 1.5 | 584.65 | 2163.25
2030-04-25 08:39 | 2030-04-25 12:39 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 4 | 8 | 23 |  | Standalone |  | 1 | 6 | 588.65 | 2159.25
2030-04-25 12:39 | 2030-04-25 15:39 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 4 | 8 | 24 |  | Standalone |  | 1 | 3 | 591.65 | 2156.25
2030-04-25 15:39 | 2030-04-25 17:09 | 1.5 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 4 | 8 | 25 |  | Standalone |  | 1.5 | 1 | 593.15 | 2154.75
2030-04-25 17:09 | 2030-04-25 20:09 | 3 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 4 | 8 | 26 |  | Standalone |  | 1.5 | 2 | 596.15 | 2151.75
2030-04-25 20:09 | 2030-04-25 21:39 | 1.5 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 4 | 8 | 27 | G1 | Start | MOST_STRINGENT | 1.5 | 1.5 | 597.65 | 2150.25
2030-04-25 21:39 | 2030-04-26 02:54 | 5.25 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 8 | 28 | G1 | Continue | MOST_STRINGENT | 1.5 | 5.25 | 602.9 | 2145
2030-04-26 02:54 | 2030-04-26 03:39 | 0.75 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 4 | 8 | 29 | G1 | End | MOST_STRINGENT | 1.5 | 0.75 | 603.65 | 2144.25
2030-04-26 03:39 | 2030-04-26 04:24 | 0.75 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 4 | 8 | 30 | G2 | Start | MOST_STRINGENT | 1.5 | 0.75 | 604.4 | 2143.5
2030-04-26 04:24 | 2030-04-26 07:46 | 3.375 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 8 | 31 | G2 | Continue | MOST_STRINGENT | 1.5 | 3.375 | 607.775 | 2140.125
2030-04-26 07:46 | 2030-04-26 08:31 | 0.75 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 4 | 8 | 32 | G2 | End | MOST_STRINGENT | 1.5 | 0.75 | 608.525 | 2139.375
2030-04-26 08:31 | 2030-04-26 09:16 | 0.75 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 4 | 8 | 33 | G3 | Start | MOST_STRINGENT | 1.5 | 0.75 | 609.275 | 2138.625
2030-04-26 09:16 | 2030-04-26 11:54 | 2.625 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 8 | 34 | G3 | Continue | MOST_STRINGENT | 1.5 | 2.625 | 611.9 | 2136
2030-04-26 11:54 | 2030-04-26 14:09 | 2.25 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 4 | 8 | 35 | G3 | End | MOST_STRINGENT | 1.5 | 2.25 | 614.15 | 2133.75
2030-04-26 14:09 | 2030-04-26 16:46 | 2.625 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 8 | 36 | G4 | Start | MOST_STRINGENT | 1.5 | 2.625 | 616.775 | 2131.125
2030-04-26 16:46 | 2030-04-26 19:01 | 2.25 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 4 | 8 | 37 | G4 | End | MOST_STRINGENT | 1.5 | 2.25 | 619.025 | 2128.875
2030-04-26 19:01 | 2030-04-26 21:39 | 2.625 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 4 | 8 | 38 | G5 | Start | MOST_STRINGENT | 1.5 | 2.625 | 621.65 | 2126.25
2030-04-26 21:39 | 2030-04-26 23:54 | 2.25 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 4 | 8 | 39 | G5 | End | MOST_STRINGENT | 1.5 | 2.25 | 623.9 | 2124
2030-04-26 23:54 | 2030-04-27 01:24 | 1.5 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 4 | 8 | 40 |  | Standalone |  | 1.5 | 1 | 625.4 | 2122.5
2030-04-27 01:24 | 2030-04-27 02:54 | 1.5 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 4 | 8 | 41 |  | Standalone |  | 1.5 | 1 | 626.9 | 2121
2030-04-27 02:54 | 2030-04-27 07:24 | 4.5 | Turbine general completion works | OFFSHORE | Working |  |  |  | 4 | 8 | 42 |  | Standalone |  | 1.5 | 3 | 631.4 | 2116.5
2030-04-27 07:24 | 2030-04-27 10:24 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 4 | 8 | 43 |  | Standalone |  | 1 | 3 | 634.4 | 2113.5
2030-04-27 10:24 | 2030-04-27 12:24 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 4 | 8 | 44 |  | Standalone |  | 1 | 3 | 636.4 | 2111.5
2030-04-27 12:24 | 2030-04-27 17:36 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 4 |  | 45 |  | Standalone |  | 1 | 7.8 | 641.6 | 2106.3
2030-04-27 17:36 | 2030-04-27 18:36 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 5 |  | 1 |  | Standalone |  | 1 | 1.5 | 642.6 | 2105.3
2030-04-27 18:36 | 2030-04-27 20:36 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 5 |  | 2 |  | Standalone |  | 1 | 3 | 644.6 | 2103.3
2030-04-27 20:36 | 2030-04-27 23:36 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 5 |  | 3 |  | Standalone |  | 1 | 3 | 647.6 | 2100.3
2030-04-27 23:36 | 2030-04-28 00:36 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 5 |  | 4 |  | Standalone |  | 1 | 1 | 648.6 | 2099.3
2030-04-28 00:36 | 2030-04-28 02:51 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 5 |  | 5 |  | Standalone |  | 1 | 3.375 | 650.85 | 2097.05
2030-04-28 02:51 | 2030-04-28 05:06 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 5 |  | 6 |  | Standalone |  | 1 | 3.375 | 653.1 | 2094.8
2030-04-28 05:06 | 2030-04-28 06:36 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 5 |  | 7 |  | Standalone |  | 1 | 2.25 | 654.6 | 2093.3
2030-04-28 06:36 | 2030-04-28 08:06 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 5 |  | 8 |  | Standalone |  | 1 | 2.25 | 656.1 | 2091.8
2030-04-28 08:06 | 2030-04-28 09:36 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 5 |  | 9 |  | Standalone |  | 1 | 2.25 | 657.6 | 2090.3
2030-04-28 09:36 | 2030-04-28 10:36 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 5 |  | 10 |  | Standalone |  | 1 | 1 | 658.6 | 2089.3
2030-04-28 10:36 | 2030-04-28 12:51 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 5 |  | 11 |  | Standalone |  | 1 | 3.375 | 660.85 | 2087.05
2030-04-28 12:51 | 2030-04-28 15:06 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 5 |  | 12 |  | Standalone |  | 1 | 3.375 | 663.1 | 2084.8
2030-04-28 15:06 | 2030-04-28 16:36 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 5 |  | 13 |  | Standalone |  | 1 | 2.25 | 664.6 | 2083.3
2030-04-28 16:36 | 2030-04-28 18:06 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 5 |  | 14 |  | Standalone |  | 1 | 2.25 | 666.1 | 2081.8
2030-04-28 18:06 | 2030-04-28 19:36 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 5 |  | 15 |  | Standalone |  | 1 | 2.25 | 667.6 | 2080.3
2030-04-28 19:36 | 2030-04-28 22:36 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 5 |  | 16 |  | Standalone |  | 1 | 3 | 670.6 | 2077.3
2030-04-28 22:36 | 2030-04-29 00:36 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 5 |  | 17 |  | Standalone |  | 1 | 3 | 672.6 | 2075.3
2030-04-29 00:36 | 2030-04-29 01:36 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 5 |  | 18 |  | Standalone |  | 1 | 1.5 | 673.6 | 2074.3
2030-04-29 01:36 | 2030-04-29 06:48 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 5 |  | 19 |  | Standalone |  | 1 | 7.8 | 678.8 | 2069.1
2030-04-29 06:48 | 2030-04-29 07:18 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 5 |  | 20 |  | Standalone |  | 1 | 0.75 | 679.3 | 2068.6
2030-04-29 07:18 | 2030-04-29 08:18 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 5 | 9 | 21 |  | Standalone |  | 1 | 1.5 | 680.3 | 2067.6
2030-04-29 08:18 | 2030-04-29 09:18 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 5 | 9 | 22 |  | Standalone |  | 1 | 1.5 | 681.3 | 2066.6
2030-04-29 09:18 | 2030-04-29 13:18 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 5 | 9 | 23 |  | Standalone |  | 1 | 6 | 685.3 | 2062.6
2030-04-29 13:18 | 2030-04-29 16:18 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 5 | 9 | 24 |  | Standalone |  | 1 | 3 | 688.3 | 2059.6
2030-04-29 16:18 | 2030-04-29 17:18 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 5 | 9 | 25 |  | Standalone |  | 1 | 1 | 689.3 | 2058.6
2030-04-29 17:18 | 2030-04-29 19:18 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 5 | 9 | 26 |  | Standalone |  | 1 | 2 | 691.3 | 2056.6
2030-04-29 19:18 | 2030-04-29 20:18 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 5 | 9 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 692.3 | 2055.6
2030-04-29 20:18 | 2030-04-29 23:48 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 9 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 695.8 | 2052.1
2030-04-29 23:48 | 2030-04-30 00:18 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 5 | 9 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 696.3 | 2051.6
2030-04-30 00:18 | 2030-04-30 00:48 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 5 | 9 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 696.8 | 2051.1
2030-04-30 00:48 | 2030-04-30 03:03 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 9 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 699.05 | 2048.85
2030-04-30 03:03 | 2030-04-30 03:33 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 5 | 9 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 699.55 | 2048.35
2030-04-30 03:33 | 2030-04-30 04:03 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 5 | 9 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 700.05 | 2047.85
2030-04-30 04:03 | 2030-04-30 05:48 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 9 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 701.8 | 2046.1
2030-04-30 05:48 | 2030-04-30 07:18 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 5 | 9 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 703.3 | 2044.6
2030-04-30 07:18 | 2030-04-30 09:03 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 9 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 705.05 | 2042.85
2030-04-30 09:03 | 2030-04-30 10:33 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 5 | 9 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 706.55 | 2041.35
2030-04-30 10:33 | 2030-04-30 12:18 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 9 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 708.3 | 2039.6
2030-04-30 12:18 | 2030-04-30 13:48 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 5 | 9 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 709.8 | 2038.1
2030-04-30 13:48 | 2030-04-30 14:48 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 5 | 9 | 40 |  | Standalone |  | 1 | 1 | 710.8 | 2037.1
2030-04-30 14:48 | 2030-04-30 15:48 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 5 | 9 | 41 |  | Standalone |  | 1 | 1 | 711.8 | 2036.1
2030-04-30 15:48 | 2030-04-30 18:48 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 5 | 9 | 42 |  | Standalone |  | 1 | 3 | 714.8 | 2033.1
2030-04-30 18:48 | 2030-04-30 21:48 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 5 | 9 | 43 |  | Standalone |  | 1 | 3 | 717.8 | 2030.1
2030-04-30 21:48 | 2030-04-30 23:48 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 5 | 9 | 44 |  | Standalone |  | 1 | 3 | 719.8 | 2028.1
2030-04-30 23:48 | 2030-05-01 00:48 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 5 | 10 | 21 |  | Standalone |  | 1 | 1.5 | 720.8 | 2027.1
2030-05-01 00:48 | 2030-05-01 01:48 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 5 | 10 | 22 |  | Standalone |  | 1 | 1.5 | 721.8 | 2026.1
2030-05-01 01:48 | 2030-05-01 05:48 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 5 | 10 | 23 |  | Standalone |  | 1 | 6 | 725.8 | 2022.1
2030-05-01 05:48 | 2030-05-01 08:48 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 5 | 10 | 24 |  | Standalone |  | 1 | 3 | 728.8 | 2019.1
2030-05-01 08:48 | 2030-05-01 09:48 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 5 | 10 | 25 |  | Standalone |  | 1 | 1 | 729.8 | 2018.1
2030-05-01 09:48 | 2030-05-01 11:48 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 5 | 10 | 26 |  | Standalone |  | 1 | 2 | 731.8 | 2016.1
2030-05-01 11:48 | 2030-05-01 12:48 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 5 | 10 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 732.8 | 2015.1
2030-05-01 12:48 | 2030-05-01 16:18 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 10 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 736.3 | 2011.6
2030-05-01 16:18 | 2030-05-01 16:48 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 5 | 10 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 736.8 | 2011.1
2030-05-01 16:48 | 2030-05-01 17:18 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 5 | 10 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 737.3 | 2010.6
2030-05-01 17:18 | 2030-05-01 19:33 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 10 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 739.55 | 2008.35
2030-05-01 19:33 | 2030-05-01 20:03 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 5 | 10 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 740.05 | 2007.85
2030-05-01 20:03 | 2030-05-01 20:33 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 5 | 10 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 740.55 | 2007.35
2030-05-01 20:33 | 2030-05-01 22:18 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 10 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 742.3 | 2005.6
2030-05-01 22:18 | 2030-05-01 23:48 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 5 | 10 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 743.8 | 2004.1
2030-05-01 23:48 | 2030-05-02 01:33 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 10 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 745.55 | 2002.35
2030-05-02 01:33 | 2030-05-02 03:03 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 5 | 10 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 747.05 | 2000.85
2030-05-02 03:03 | 2030-05-02 04:48 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 5 | 10 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 748.8 | 1999.1
2030-05-02 04:48 | 2030-05-02 06:18 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 5 | 10 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 750.3 | 1997.6
2030-05-02 06:18 | 2030-05-02 07:18 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 5 | 10 | 40 |  | Standalone |  | 1 | 1 | 751.3 | 1996.6
2030-05-02 07:18 | 2030-05-02 08:18 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 5 | 10 | 41 |  | Standalone |  | 1 | 1 | 752.3 | 1995.6
2030-05-02 08:18 | 2030-05-02 11:18 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 5 | 10 | 42 |  | Standalone |  | 1 | 3 | 755.3 | 1992.6
2030-05-02 11:18 | 2030-05-02 14:18 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 5 | 10 | 43 |  | Standalone |  | 1 | 3 | 758.3 | 1989.6
2030-05-02 14:18 | 2030-05-02 16:18 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 5 | 10 | 44 |  | Standalone |  | 1 | 3 | 760.3 | 1987.6
2030-05-02 16:18 | 2030-05-02 21:30 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 5 |  | 45 |  | Standalone |  | 1 | 7.8 | 765.5 | 1982.4
2030-05-02 21:30 | 2030-05-02 22:30 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 6 |  | 1 |  | Standalone |  | 1 | 1.5 | 766.5 | 1981.4
2030-05-02 22:30 | 2030-05-03 00:30 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 6 |  | 2 |  | Standalone |  | 1 | 3 | 768.5 | 1979.4
2030-05-03 00:30 | 2030-05-03 03:30 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 6 |  | 3 |  | Standalone |  | 1 | 3 | 771.5 | 1976.4
2030-05-03 03:30 | 2030-05-03 04:30 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 6 |  | 4 |  | Standalone |  | 1 | 1 | 772.5 | 1975.4
2030-05-03 04:30 | 2030-05-03 06:45 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 6 |  | 5 |  | Standalone |  | 1 | 3.375 | 774.75 | 1973.15
2030-05-03 06:45 | 2030-05-03 09:00 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 6 |  | 6 |  | Standalone |  | 1 | 3.375 | 777 | 1970.9
2030-05-03 09:00 | 2030-05-03 10:30 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 6 |  | 7 |  | Standalone |  | 1 | 2.25 | 778.5 | 1969.4
2030-05-03 10:30 | 2030-05-03 12:00 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 6 |  | 8 |  | Standalone |  | 1 | 2.25 | 780 | 1967.9
2030-05-03 12:00 | 2030-05-03 13:30 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 6 |  | 9 |  | Standalone |  | 1 | 2.25 | 781.5 | 1966.4
2030-05-03 13:30 | 2030-05-03 14:30 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 6 |  | 10 |  | Standalone |  | 1 | 1 | 782.5 | 1965.4
2030-05-03 14:30 | 2030-05-03 16:45 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 6 |  | 11 |  | Standalone |  | 1 | 3.375 | 784.75 | 1963.15
2030-05-03 16:45 | 2030-05-03 19:00 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 6 |  | 12 |  | Standalone |  | 1 | 3.375 | 787 | 1960.9
2030-05-03 19:00 | 2030-05-03 20:30 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 6 |  | 13 |  | Standalone |  | 1 | 2.25 | 788.5 | 1959.4
2030-05-03 20:30 | 2030-05-03 22:00 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 6 |  | 14 |  | Standalone |  | 1 | 2.25 | 790 | 1957.9
2030-05-03 22:00 | 2030-05-03 23:30 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 6 |  | 15 |  | Standalone |  | 1 | 2.25 | 791.5 | 1956.4
2030-05-03 23:30 | 2030-05-04 02:30 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 6 |  | 16 |  | Standalone |  | 1 | 3 | 794.5 | 1953.4
2030-05-04 02:30 | 2030-05-04 04:30 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 6 |  | 17 |  | Standalone |  | 1 | 3 | 796.5 | 1951.4
2030-05-04 04:30 | 2030-05-04 05:30 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 6 |  | 18 |  | Standalone |  | 1 | 1.5 | 797.5 | 1950.4
2030-05-04 05:30 | 2030-05-04 10:42 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 6 |  | 19 |  | Standalone |  | 1 | 7.8 | 802.7 | 1945.2
2030-05-04 10:42 | 2030-05-04 11:12 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 6 |  | 20 |  | Standalone |  | 1 | 0.75 | 803.2 | 1944.7
2030-05-04 11:12 | 2030-05-04 12:12 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 6 | 11 | 21 |  | Standalone |  | 1 | 1.5 | 804.2 | 1943.7
2030-05-04 12:12 | 2030-05-04 13:12 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 6 | 11 | 22 |  | Standalone |  | 1 | 1.5 | 805.2 | 1942.7
2030-05-04 13:12 | 2030-05-04 17:12 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 6 | 11 | 23 |  | Standalone |  | 1 | 6 | 809.2 | 1938.7
2030-05-04 17:12 | 2030-05-04 20:12 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 6 | 11 | 24 |  | Standalone |  | 1 | 3 | 812.2 | 1935.7
2030-05-04 20:12 | 2030-05-04 21:12 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 6 | 11 | 25 |  | Standalone |  | 1 | 1 | 813.2 | 1934.7
2030-05-04 21:12 | 2030-05-04 23:12 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 6 | 11 | 26 |  | Standalone |  | 1 | 2 | 815.2 | 1932.7
2030-05-04 23:12 | 2030-05-05 00:12 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 6 | 11 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 816.2 | 1931.7
2030-05-05 00:12 | 2030-05-05 03:42 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 11 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 819.7 | 1928.2
2030-05-05 03:42 | 2030-05-05 04:12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 6 | 11 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 820.2 | 1927.7
2030-05-05 04:12 | 2030-05-05 04:42 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 6 | 11 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 820.7 | 1927.2
2030-05-05 04:42 | 2030-05-05 06:57 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 11 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 822.95 | 1924.95
2030-05-05 06:57 | 2030-05-05 07:27 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 6 | 11 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 823.45 | 1924.45
2030-05-05 07:27 | 2030-05-05 07:57 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 6 | 11 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 823.95 | 1923.95
2030-05-05 07:57 | 2030-05-05 09:42 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 11 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 825.7 | 1922.2
2030-05-05 09:42 | 2030-05-05 11:12 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 6 | 11 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 827.2 | 1920.7
2030-05-05 11:12 | 2030-05-05 12:57 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 11 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 828.95 | 1918.95
2030-05-05 12:57 | 2030-05-05 14:27 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 6 | 11 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 830.45 | 1917.45
2030-05-05 14:27 | 2030-05-05 16:12 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 11 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 832.2 | 1915.7
2030-05-05 16:12 | 2030-05-05 17:42 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 6 | 11 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 833.7 | 1914.2
2030-05-05 17:42 | 2030-05-05 18:42 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 6 | 11 | 40 |  | Standalone |  | 1 | 1 | 834.7 | 1913.2
2030-05-05 18:42 | 2030-05-05 19:42 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 6 | 11 | 41 |  | Standalone |  | 1 | 1 | 835.7 | 1912.2
2030-05-05 19:42 | 2030-05-05 22:42 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 6 | 11 | 42 |  | Standalone |  | 1 | 3 | 838.7 | 1909.2
2030-05-05 22:42 | 2030-05-06 01:42 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 6 | 11 | 43 |  | Standalone |  | 1 | 3 | 841.7 | 1906.2
2030-05-06 01:42 | 2030-05-06 03:42 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 6 | 11 | 44 |  | Standalone |  | 1 | 3 | 843.7 | 1904.2
2030-05-06 03:42 | 2030-05-06 04:42 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 6 | 12 | 21 |  | Standalone |  | 1 | 1.5 | 844.7 | 1903.2
2030-05-06 04:42 | 2030-05-06 05:42 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 6 | 12 | 22 |  | Standalone |  | 1 | 1.5 | 845.7 | 1902.2
2030-05-06 05:42 | 2030-05-06 09:42 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 6 | 12 | 23 |  | Standalone |  | 1 | 6 | 849.7 | 1898.2
2030-05-06 09:42 | 2030-05-06 12:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 6 | 12 | 24 |  | Standalone |  | 1 | 3 | 852.7 | 1895.2
2030-05-06 12:42 | 2030-05-06 13:42 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 6 | 12 | 25 |  | Standalone |  | 1 | 1 | 853.7 | 1894.2
2030-05-06 13:42 | 2030-05-06 15:42 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 6 | 12 | 26 |  | Standalone |  | 1 | 2 | 855.7 | 1892.2
2030-05-06 15:42 | 2030-05-06 16:42 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 6 | 12 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 856.7 | 1891.2
2030-05-06 16:42 | 2030-05-06 20:12 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 12 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 860.2 | 1887.7
2030-05-06 20:12 | 2030-05-06 20:42 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 6 | 12 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 860.7 | 1887.2
2030-05-06 20:42 | 2030-05-06 21:12 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 6 | 12 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 861.2 | 1886.7
2030-05-06 21:12 | 2030-05-06 23:27 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 12 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 863.45 | 1884.45
2030-05-06 23:27 | 2030-05-06 23:57 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 6 | 12 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 863.95 | 1883.95
2030-05-06 23:57 | 2030-05-07 00:27 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 6 | 12 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 864.45 | 1883.45
2030-05-07 00:27 | 2030-05-07 02:12 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 12 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 866.2 | 1881.7
2030-05-07 02:12 | 2030-05-07 03:42 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 6 | 12 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 867.7 | 1880.2
2030-05-07 03:42 | 2030-05-07 05:27 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 12 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 869.45 | 1878.45
2030-05-07 05:27 | 2030-05-07 06:57 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 6 | 12 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 870.95 | 1876.95
2030-05-07 06:57 | 2030-05-07 08:42 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 6 | 12 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 872.7 | 1875.2
2030-05-07 08:42 | 2030-05-07 10:12 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 6 | 12 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 874.2 | 1873.7
2030-05-07 10:12 | 2030-05-07 11:12 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 6 | 12 | 40 |  | Standalone |  | 1 | 1 | 875.2 | 1872.7
2030-05-07 11:12 | 2030-05-07 12:12 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 6 | 12 | 41 |  | Standalone |  | 1 | 1 | 876.2 | 1871.7
2030-05-07 12:12 | 2030-05-07 15:12 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 6 | 12 | 42 |  | Standalone |  | 1 | 3 | 879.2 | 1868.7
2030-05-07 15:12 | 2030-05-07 18:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 6 | 12 | 43 |  | Standalone |  | 1 | 3 | 882.2 | 1865.7
2030-05-07 18:12 | 2030-05-07 20:12 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 6 | 12 | 44 |  | Standalone |  | 1 | 3 | 884.2 | 1863.7
2030-05-07 20:12 | 2030-05-08 01:24 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 6 |  | 45 |  | Standalone |  | 1 | 7.8 | 889.4 | 1858.5
2030-05-08 01:24 | 2030-05-08 02:24 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 7 |  | 1 |  | Standalone |  | 1 | 1.5 | 890.4 | 1857.5
2030-05-08 02:24 | 2030-05-08 04:24 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 7 |  | 2 |  | Standalone |  | 1 | 3 | 892.4 | 1855.5
2030-05-08 04:24 | 2030-05-08 07:24 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 7 |  | 3 |  | Standalone |  | 1 | 3 | 895.4 | 1852.5
2030-05-08 07:24 | 2030-05-08 08:24 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 7 |  | 4 |  | Standalone |  | 1 | 1 | 896.4 | 1851.5
2030-05-08 08:24 | 2030-05-08 10:39 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 7 |  | 5 |  | Standalone |  | 1 | 3.375 | 898.65 | 1849.25
2030-05-08 10:39 | 2030-05-08 12:54 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 7 |  | 6 |  | Standalone |  | 1 | 3.375 | 900.9 | 1847
2030-05-08 12:54 | 2030-05-08 14:24 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 7 |  | 7 |  | Standalone |  | 1 | 2.25 | 902.4 | 1845.5
2030-05-08 14:24 | 2030-05-08 15:54 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 7 |  | 8 |  | Standalone |  | 1 | 2.25 | 903.9 | 1844
2030-05-08 15:54 | 2030-05-08 17:24 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 7 |  | 9 |  | Standalone |  | 1 | 2.25 | 905.4 | 1842.5
2030-05-08 17:24 | 2030-05-08 18:24 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 7 |  | 10 |  | Standalone |  | 1 | 1 | 906.4 | 1841.5
2030-05-08 18:24 | 2030-05-08 20:39 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 7 |  | 11 |  | Standalone |  | 1 | 3.375 | 908.65 | 1839.25
2030-05-08 20:39 | 2030-05-08 22:54 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 7 |  | 12 |  | Standalone |  | 1 | 3.375 | 910.9 | 1837
2030-05-08 22:54 | 2030-05-09 00:24 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 7 |  | 13 |  | Standalone |  | 1 | 2.25 | 912.4 | 1835.5
2030-05-09 00:24 | 2030-05-09 01:54 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 7 |  | 14 |  | Standalone |  | 1 | 2.25 | 913.9 | 1834
2030-05-09 01:54 | 2030-05-09 03:24 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 7 |  | 15 |  | Standalone |  | 1 | 2.25 | 915.4 | 1832.5
2030-05-09 03:24 | 2030-05-09 06:24 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 7 |  | 16 |  | Standalone |  | 1 | 3 | 918.4 | 1829.5
2030-05-09 06:24 | 2030-05-09 08:24 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 7 |  | 17 |  | Standalone |  | 1 | 3 | 920.4 | 1827.5
2030-05-09 08:24 | 2030-05-09 09:24 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 7 |  | 18 |  | Standalone |  | 1 | 1.5 | 921.4 | 1826.5
2030-05-09 09:24 | 2030-05-09 14:36 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 7 |  | 19 |  | Standalone |  | 1 | 7.8 | 926.6 | 1821.3
2030-05-09 14:36 | 2030-05-09 15:06 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 7 |  | 20 |  | Standalone |  | 1 | 0.75 | 927.1 | 1820.8
2030-05-09 15:06 | 2030-05-09 16:06 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 7 | 13 | 21 |  | Standalone |  | 1 | 1.5 | 928.1 | 1819.8
2030-05-09 16:06 | 2030-05-09 17:06 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 7 | 13 | 22 |  | Standalone |  | 1 | 1.5 | 929.1 | 1818.8
2030-05-09 17:06 | 2030-05-09 21:06 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 7 | 13 | 23 |  | Standalone |  | 1 | 6 | 933.1 | 1814.8
2030-05-09 21:06 | 2030-05-10 00:06 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 7 | 13 | 24 |  | Standalone |  | 1 | 3 | 936.1 | 1811.8
2030-05-10 00:06 | 2030-05-10 01:06 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 7 | 13 | 25 |  | Standalone |  | 1 | 1 | 937.1 | 1810.8
2030-05-10 01:06 | 2030-05-10 03:06 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 7 | 13 | 26 |  | Standalone |  | 1 | 2 | 939.1 | 1808.8
2030-05-10 03:06 | 2030-05-10 04:06 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 7 | 13 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 940.1 | 1807.8
2030-05-10 04:06 | 2030-05-10 07:36 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 13 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 943.6 | 1804.3
2030-05-10 07:36 | 2030-05-10 08:06 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 7 | 13 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 944.1 | 1803.8
2030-05-10 08:06 | 2030-05-10 08:36 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 7 | 13 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 944.6 | 1803.3
2030-05-10 08:36 | 2030-05-10 10:51 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 13 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 946.85 | 1801.05
2030-05-10 10:51 | 2030-05-10 11:21 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 7 | 13 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 947.35 | 1800.55
2030-05-10 11:21 | 2030-05-10 11:51 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 7 | 13 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 947.85 | 1800.05
2030-05-10 11:51 | 2030-05-10 13:36 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 13 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 949.6 | 1798.3
2030-05-10 13:36 | 2030-05-10 15:06 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 7 | 13 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 951.1 | 1796.8
2030-05-10 15:06 | 2030-05-10 16:51 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 13 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 952.85 | 1795.05
2030-05-10 16:51 | 2030-05-10 18:21 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 7 | 13 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 954.35 | 1793.55
2030-05-10 18:21 | 2030-05-10 20:06 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 13 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 956.1 | 1791.8
2030-05-10 20:06 | 2030-05-10 21:36 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 7 | 13 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 957.6 | 1790.3
2030-05-10 21:36 | 2030-05-10 22:36 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 7 | 13 | 40 |  | Standalone |  | 1 | 1 | 958.6 | 1789.3
2030-05-10 22:36 | 2030-05-10 23:36 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 7 | 13 | 41 |  | Standalone |  | 1 | 1 | 959.6 | 1788.3
2030-05-10 23:36 | 2030-05-11 02:36 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 7 | 13 | 42 |  | Standalone |  | 1 | 3 | 962.6 | 1785.3
2030-05-11 02:36 | 2030-05-11 05:36 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 7 | 13 | 43 |  | Standalone |  | 1 | 3 | 965.6 | 1782.3
2030-05-11 05:36 | 2030-05-11 07:36 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 7 | 13 | 44 |  | Standalone |  | 1 | 3 | 967.6 | 1780.3
2030-05-11 07:36 | 2030-05-11 08:36 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 7 | 14 | 21 |  | Standalone |  | 1 | 1.5 | 968.6 | 1779.3
2030-05-11 08:36 | 2030-05-11 09:36 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 7 | 14 | 22 |  | Standalone |  | 1 | 1.5 | 969.6 | 1778.3
2030-05-11 09:36 | 2030-05-11 13:36 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 7 | 14 | 23 |  | Standalone |  | 1 | 6 | 973.6 | 1774.3
2030-05-11 13:36 | 2030-05-11 16:36 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 7 | 14 | 24 |  | Standalone |  | 1 | 3 | 976.6 | 1771.3
2030-05-11 16:36 | 2030-05-11 17:36 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 7 | 14 | 25 |  | Standalone |  | 1 | 1 | 977.6 | 1770.3
2030-05-11 17:36 | 2030-05-11 19:36 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 7 | 14 | 26 |  | Standalone |  | 1 | 2 | 979.6 | 1768.3
2030-05-11 19:36 | 2030-05-11 20:36 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 7 | 14 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 980.6 | 1767.3
2030-05-11 20:36 | 2030-05-12 00:06 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 14 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 984.1 | 1763.8
2030-05-12 00:06 | 2030-05-12 00:36 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 7 | 14 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 984.6 | 1763.3
2030-05-12 00:36 | 2030-05-12 01:06 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 7 | 14 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 985.1 | 1762.8
2030-05-12 01:06 | 2030-05-12 03:21 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 14 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 987.35 | 1760.55
2030-05-12 03:21 | 2030-05-12 03:51 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 7 | 14 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 987.85 | 1760.05
2030-05-12 03:51 | 2030-05-12 04:21 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 7 | 14 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 988.35 | 1759.55
2030-05-12 04:21 | 2030-05-12 06:06 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 14 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 990.1 | 1757.8
2030-05-12 06:06 | 2030-05-12 07:36 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 7 | 14 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 991.6 | 1756.3
2030-05-12 07:36 | 2030-05-12 09:21 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 14 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 993.35 | 1754.55
2030-05-12 09:21 | 2030-05-12 10:51 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 7 | 14 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 994.85 | 1753.05
2030-05-12 10:51 | 2030-05-12 12:36 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 7 | 14 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 996.6 | 1751.3
2030-05-12 12:36 | 2030-05-12 14:06 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 7 | 14 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 998.1 | 1749.8
2030-05-12 14:06 | 2030-05-12 15:06 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 7 | 14 | 40 |  | Standalone |  | 1 | 1 | 999.1 | 1748.8
2030-05-12 15:06 | 2030-05-12 16:06 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 7 | 14 | 41 |  | Standalone |  | 1 | 1 | 1000.1 | 1747.8
2030-05-12 16:06 | 2030-05-12 19:06 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 7 | 14 | 42 |  | Standalone |  | 1 | 3 | 1003.1 | 1744.8
2030-05-12 19:06 | 2030-05-12 22:06 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 7 | 14 | 43 |  | Standalone |  | 1 | 3 | 1006.1 | 1741.8
2030-05-12 22:06 | 2030-05-13 00:06 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 7 | 14 | 44 |  | Standalone |  | 1 | 3 | 1008.1 | 1739.8
2030-05-13 00:06 | 2030-05-13 05:18 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 7 |  | 45 |  | Standalone |  | 1 | 7.8 | 1013.3 | 1734.6
2030-05-13 05:18 | 2030-05-13 06:18 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 8 |  | 1 |  | Standalone |  | 1 | 1.5 | 1014.3 | 1733.6
2030-05-13 06:18 | 2030-05-13 08:18 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 8 |  | 2 |  | Standalone |  | 1 | 3 | 1016.3 | 1731.6
2030-05-13 08:18 | 2030-05-13 11:18 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 8 |  | 3 |  | Standalone |  | 1 | 3 | 1019.3 | 1728.6
2030-05-13 11:18 | 2030-05-13 12:18 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 8 |  | 4 |  | Standalone |  | 1 | 1 | 1020.3 | 1727.6
2030-05-13 12:18 | 2030-05-13 14:33 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 8 |  | 5 |  | Standalone |  | 1 | 3.375 | 1022.55 | 1725.35
2030-05-13 14:33 | 2030-05-13 16:48 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 8 |  | 6 |  | Standalone |  | 1 | 3.375 | 1024.8 | 1723.1
2030-05-13 16:48 | 2030-05-13 18:18 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 8 |  | 7 |  | Standalone |  | 1 | 2.25 | 1026.3 | 1721.6
2030-05-13 18:18 | 2030-05-13 19:48 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 8 |  | 8 |  | Standalone |  | 1 | 2.25 | 1027.8 | 1720.1
2030-05-13 19:48 | 2030-05-13 21:18 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 8 |  | 9 |  | Standalone |  | 1 | 2.25 | 1029.3 | 1718.6
2030-05-13 21:18 | 2030-05-13 22:18 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 8 |  | 10 |  | Standalone |  | 1 | 1 | 1030.3 | 1717.6
2030-05-13 22:18 | 2030-05-14 00:33 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 8 |  | 11 |  | Standalone |  | 1 | 3.375 | 1032.55 | 1715.35
2030-05-14 00:33 | 2030-05-14 02:48 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 8 |  | 12 |  | Standalone |  | 1 | 3.375 | 1034.8 | 1713.1
2030-05-14 02:48 | 2030-05-14 04:18 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 8 |  | 13 |  | Standalone |  | 1 | 2.25 | 1036.3 | 1711.6
2030-05-14 04:18 | 2030-05-14 05:48 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 8 |  | 14 |  | Standalone |  | 1 | 2.25 | 1037.8 | 1710.1
2030-05-14 05:48 | 2030-05-14 07:18 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 8 |  | 15 |  | Standalone |  | 1 | 2.25 | 1039.3 | 1708.6
2030-05-14 07:18 | 2030-05-14 10:18 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 8 |  | 16 |  | Standalone |  | 1 | 3 | 1042.3 | 1705.6
2030-05-14 10:18 | 2030-05-14 12:18 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 8 |  | 17 |  | Standalone |  | 1 | 3 | 1044.3 | 1703.6
2030-05-14 12:18 | 2030-05-14 13:18 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 8 |  | 18 |  | Standalone |  | 1 | 1.5 | 1045.3 | 1702.6
2030-05-14 13:18 | 2030-05-14 18:30 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 8 |  | 19 |  | Standalone |  | 1 | 7.8 | 1050.5 | 1697.4
2030-05-14 18:30 | 2030-05-14 19:00 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 8 |  | 20 |  | Standalone |  | 1 | 0.75 | 1051 | 1696.9
2030-05-14 19:00 | 2030-05-14 20:00 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 8 | 15 | 21 |  | Standalone |  | 1 | 1.5 | 1052 | 1695.9
2030-05-14 20:00 | 2030-05-14 21:00 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 8 | 15 | 22 |  | Standalone |  | 1 | 1.5 | 1053 | 1694.9
2030-05-14 21:00 | 2030-05-15 01:00 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 8 | 15 | 23 |  | Standalone |  | 1 | 6 | 1057 | 1690.9
2030-05-15 01:00 | 2030-05-15 04:00 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 8 | 15 | 24 |  | Standalone |  | 1 | 3 | 1060 | 1687.9
2030-05-15 04:00 | 2030-05-15 05:00 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 8 | 15 | 25 |  | Standalone |  | 1 | 1 | 1061 | 1686.9
2030-05-15 05:00 | 2030-05-15 07:00 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 8 | 15 | 26 |  | Standalone |  | 1 | 2 | 1063 | 1684.9
2030-05-15 07:00 | 2030-05-15 08:00 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 8 | 15 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1064 | 1683.9
2030-05-15 08:00 | 2030-05-15 11:30 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 15 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1067.5 | 1680.4
2030-05-15 11:30 | 2030-05-15 12:00 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 8 | 15 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1068 | 1679.9
2030-05-15 12:00 | 2030-05-15 12:30 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 8 | 15 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1068.5 | 1679.4
2030-05-15 12:30 | 2030-05-15 14:45 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 15 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1070.75 | 1677.15
2030-05-15 14:45 | 2030-05-15 15:15 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 8 | 15 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1071.25 | 1676.65
2030-05-15 15:15 | 2030-05-15 15:45 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 8 | 15 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1071.75 | 1676.15
2030-05-15 15:45 | 2030-05-15 17:30 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 15 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1073.5 | 1674.4
2030-05-15 17:30 | 2030-05-15 19:00 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 8 | 15 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1075 | 1672.9
2030-05-15 19:00 | 2030-05-15 20:45 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 15 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1076.75 | 1671.15
2030-05-15 20:45 | 2030-05-15 22:15 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 8 | 15 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1078.25 | 1669.65
2030-05-15 22:15 | 2030-05-16 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 15 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1080 | 1667.9
2030-05-16 | 2030-05-16 01:30 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 8 | 15 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1081.5 | 1666.4
2030-05-16 01:30 | 2030-05-16 02:30 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 8 | 15 | 40 |  | Standalone |  | 1 | 1 | 1082.5 | 1665.4
2030-05-16 02:30 | 2030-05-16 03:30 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 8 | 15 | 41 |  | Standalone |  | 1 | 1 | 1083.5 | 1664.4
2030-05-16 03:30 | 2030-05-16 06:30 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 8 | 15 | 42 |  | Standalone |  | 1 | 3 | 1086.5 | 1661.4
2030-05-16 06:30 | 2030-05-16 09:30 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 8 | 15 | 43 |  | Standalone |  | 1 | 3 | 1089.5 | 1658.4
2030-05-16 09:30 | 2030-05-16 11:30 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 8 | 15 | 44 |  | Standalone |  | 1 | 3 | 1091.5 | 1656.4
2030-05-16 11:30 | 2030-05-16 12:30 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 8 | 16 | 21 |  | Standalone |  | 1 | 1.5 | 1092.5 | 1655.4
2030-05-16 12:30 | 2030-05-16 13:30 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 8 | 16 | 22 |  | Standalone |  | 1 | 1.5 | 1093.5 | 1654.4
2030-05-16 13:30 | 2030-05-16 17:30 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 8 | 16 | 23 |  | Standalone |  | 1 | 6 | 1097.5 | 1650.4
2030-05-16 17:30 | 2030-05-16 20:30 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 8 | 16 | 24 |  | Standalone |  | 1 | 3 | 1100.5 | 1647.4
2030-05-16 20:30 | 2030-05-16 21:30 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 8 | 16 | 25 |  | Standalone |  | 1 | 1 | 1101.5 | 1646.4
2030-05-16 21:30 | 2030-05-16 23:30 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 8 | 16 | 26 |  | Standalone |  | 1 | 2 | 1103.5 | 1644.4
2030-05-16 23:30 | 2030-05-17 00:30 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 8 | 16 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1104.5 | 1643.4
2030-05-17 00:30 | 2030-05-17 04:00 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 16 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1108 | 1639.9
2030-05-17 04:00 | 2030-05-17 04:30 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 8 | 16 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1108.5 | 1639.4
2030-05-17 04:30 | 2030-05-17 05:00 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 8 | 16 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1109 | 1638.9
2030-05-17 05:00 | 2030-05-17 07:15 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 16 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1111.25 | 1636.65
2030-05-17 07:15 | 2030-05-17 07:45 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 8 | 16 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1111.75 | 1636.15
2030-05-17 07:45 | 2030-05-17 08:15 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 8 | 16 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1112.25 | 1635.65
2030-05-17 08:15 | 2030-05-17 10:00 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 16 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1114 | 1633.9
2030-05-17 10:00 | 2030-05-17 11:30 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 8 | 16 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1115.5 | 1632.4
2030-05-17 11:30 | 2030-05-17 13:15 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 16 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1117.25 | 1630.65
2030-05-17 13:15 | 2030-05-17 14:45 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 8 | 16 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1118.75 | 1629.15
2030-05-17 14:45 | 2030-05-17 16:30 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 8 | 16 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1120.5 | 1627.4
2030-05-17 16:30 | 2030-05-17 18:00 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 8 | 16 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1122 | 1625.9
2030-05-17 18:00 | 2030-05-17 19:00 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 8 | 16 | 40 |  | Standalone |  | 1 | 1 | 1123 | 1624.9
2030-05-17 19:00 | 2030-05-17 20:00 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 8 | 16 | 41 |  | Standalone |  | 1 | 1 | 1124 | 1623.9
2030-05-17 20:00 | 2030-05-17 23:00 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 8 | 16 | 42 |  | Standalone |  | 1 | 3 | 1127 | 1620.9
2030-05-17 23:00 | 2030-05-18 02:00 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 8 | 16 | 43 |  | Standalone |  | 1 | 3 | 1130 | 1617.9
2030-05-18 02:00 | 2030-05-18 04:00 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 8 | 16 | 44 |  | Standalone |  | 1 | 3 | 1132 | 1615.9
2030-05-18 04:00 | 2030-05-18 09:12 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 8 |  | 45 |  | Standalone |  | 1 | 7.8 | 1137.2 | 1610.7
2030-05-18 09:12 | 2030-05-18 10:12 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 9 |  | 1 |  | Standalone |  | 1 | 1.5 | 1138.2 | 1609.7
2030-05-18 10:12 | 2030-05-18 12:12 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 9 |  | 2 |  | Standalone |  | 1 | 3 | 1140.2 | 1607.7
2030-05-18 12:12 | 2030-05-18 15:12 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 9 |  | 3 |  | Standalone |  | 1 | 3 | 1143.2 | 1604.7
2030-05-18 15:12 | 2030-05-18 16:12 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 9 |  | 4 |  | Standalone |  | 1 | 1 | 1144.2 | 1603.7
2030-05-18 16:12 | 2030-05-18 18:27 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 9 |  | 5 |  | Standalone |  | 1 | 3.375 | 1146.45 | 1601.45
2030-05-18 18:27 | 2030-05-18 20:42 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 9 |  | 6 |  | Standalone |  | 1 | 3.375 | 1148.7 | 1599.2
2030-05-18 20:42 | 2030-05-18 22:12 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 9 |  | 7 |  | Standalone |  | 1 | 2.25 | 1150.2 | 1597.7
2030-05-18 22:12 | 2030-05-18 23:42 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 9 |  | 8 |  | Standalone |  | 1 | 2.25 | 1151.7 | 1596.2
2030-05-18 23:42 | 2030-05-19 01:12 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 9 |  | 9 |  | Standalone |  | 1 | 2.25 | 1153.2 | 1594.7
2030-05-19 01:12 | 2030-05-19 02:12 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 9 |  | 10 |  | Standalone |  | 1 | 1 | 1154.2 | 1593.7
2030-05-19 02:12 | 2030-05-19 04:27 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 9 |  | 11 |  | Standalone |  | 1 | 3.375 | 1156.45 | 1591.45
2030-05-19 04:27 | 2030-05-19 06:42 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 9 |  | 12 |  | Standalone |  | 1 | 3.375 | 1158.7 | 1589.2
2030-05-19 06:42 | 2030-05-19 08:12 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 9 |  | 13 |  | Standalone |  | 1 | 2.25 | 1160.2 | 1587.7
2030-05-19 08:12 | 2030-05-19 09:42 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 9 |  | 14 |  | Standalone |  | 1 | 2.25 | 1161.7 | 1586.2
2030-05-19 09:42 | 2030-05-19 11:12 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 9 |  | 15 |  | Standalone |  | 1 | 2.25 | 1163.2 | 1584.7
2030-05-19 11:12 | 2030-05-19 14:12 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 9 |  | 16 |  | Standalone |  | 1 | 3 | 1166.2 | 1581.7
2030-05-19 14:12 | 2030-05-19 16:12 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 9 |  | 17 |  | Standalone |  | 1 | 3 | 1168.2 | 1579.7
2030-05-19 16:12 | 2030-05-19 17:12 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 9 |  | 18 |  | Standalone |  | 1 | 1.5 | 1169.2 | 1578.7
2030-05-19 17:12 | 2030-05-19 22:24 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 9 |  | 19 |  | Standalone |  | 1 | 7.8 | 1174.4 | 1573.5
2030-05-19 22:24 | 2030-05-19 22:54 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 9 |  | 20 |  | Standalone |  | 1 | 0.75 | 1174.9 | 1573
2030-05-19 22:54 | 2030-05-19 23:54 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 9 | 17 | 21 |  | Standalone |  | 1 | 1.5 | 1175.9 | 1572
2030-05-19 23:54 | 2030-05-20 00:54 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 9 | 17 | 22 |  | Standalone |  | 1 | 1.5 | 1176.9 | 1571
2030-05-20 00:54 | 2030-05-20 04:54 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 9 | 17 | 23 |  | Standalone |  | 1 | 6 | 1180.9 | 1567
2030-05-20 04:54 | 2030-05-20 07:54 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 9 | 17 | 24 |  | Standalone |  | 1 | 3 | 1183.9 | 1564
2030-05-20 07:54 | 2030-05-20 08:54 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 9 | 17 | 25 |  | Standalone |  | 1 | 1 | 1184.9 | 1563
2030-05-20 08:54 | 2030-05-20 10:54 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 9 | 17 | 26 |  | Standalone |  | 1 | 2 | 1186.9 | 1561
2030-05-20 10:54 | 2030-05-20 11:54 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 9 | 17 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1187.9 | 1560
2030-05-20 11:54 | 2030-05-20 15:24 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 17 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1191.4 | 1556.5
2030-05-20 15:24 | 2030-05-20 15:54 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 9 | 17 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1191.9 | 1556
2030-05-20 15:54 | 2030-05-20 16:24 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 9 | 17 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1192.4 | 1555.5
2030-05-20 16:24 | 2030-05-20 18:39 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 17 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1194.65 | 1553.25
2030-05-20 18:39 | 2030-05-20 19:09 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 9 | 17 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1195.15 | 1552.75
2030-05-20 19:09 | 2030-05-20 19:39 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 9 | 17 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1195.65 | 1552.25
2030-05-20 19:39 | 2030-05-20 21:24 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 17 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1197.4 | 1550.5
2030-05-20 21:24 | 2030-05-20 22:54 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 9 | 17 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1198.9 | 1549
2030-05-20 22:54 | 2030-05-21 00:39 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 17 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1200.65 | 1547.25
2030-05-21 00:39 | 2030-05-21 02:09 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 9 | 17 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1202.15 | 1545.75
2030-05-21 02:09 | 2030-05-21 03:54 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 17 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1203.9 | 1544
2030-05-21 03:54 | 2030-05-21 05:24 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 9 | 17 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1205.4 | 1542.5
2030-05-21 05:24 | 2030-05-21 06:24 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 9 | 17 | 40 |  | Standalone |  | 1 | 1 | 1206.4 | 1541.5
2030-05-21 06:24 | 2030-05-21 07:24 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 9 | 17 | 41 |  | Standalone |  | 1 | 1 | 1207.4 | 1540.5
2030-05-21 07:24 | 2030-05-21 10:24 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 9 | 17 | 42 |  | Standalone |  | 1 | 3 | 1210.4 | 1537.5
2030-05-21 10:24 | 2030-05-21 13:24 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 9 | 17 | 43 |  | Standalone |  | 1 | 3 | 1213.4 | 1534.5
2030-05-21 13:24 | 2030-05-21 15:24 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 9 | 17 | 44 |  | Standalone |  | 1 | 3 | 1215.4 | 1532.5
2030-05-21 15:24 | 2030-05-21 16:24 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 9 | 18 | 21 |  | Standalone |  | 1 | 1.5 | 1216.4 | 1531.5
2030-05-21 16:24 | 2030-05-21 17:24 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 9 | 18 | 22 |  | Standalone |  | 1 | 1.5 | 1217.4 | 1530.5
2030-05-21 17:24 | 2030-05-21 21:24 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 9 | 18 | 23 |  | Standalone |  | 1 | 6 | 1221.4 | 1526.5
2030-05-21 21:24 | 2030-05-22 00:24 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 9 | 18 | 24 |  | Standalone |  | 1 | 3 | 1224.4 | 1523.5
2030-05-22 00:24 | 2030-05-22 01:24 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 9 | 18 | 25 |  | Standalone |  | 1 | 1 | 1225.4 | 1522.5
2030-05-22 01:24 | 2030-05-22 03:24 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 9 | 18 | 26 |  | Standalone |  | 1 | 2 | 1227.4 | 1520.5
2030-05-22 03:24 | 2030-05-22 04:24 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 9 | 18 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1228.4 | 1519.5
2030-05-22 04:24 | 2030-05-22 07:54 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 18 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1231.9 | 1516
2030-05-22 07:54 | 2030-05-22 08:24 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 9 | 18 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1232.4 | 1515.5
2030-05-22 08:24 | 2030-05-22 08:54 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 9 | 18 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1232.9 | 1515
2030-05-22 08:54 | 2030-05-22 11:09 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 18 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1235.15 | 1512.75
2030-05-22 11:09 | 2030-05-22 11:39 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 9 | 18 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1235.65 | 1512.25
2030-05-22 11:39 | 2030-05-22 12:09 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 9 | 18 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1236.15 | 1511.75
2030-05-22 12:09 | 2030-05-22 13:54 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 18 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1237.9 | 1510
2030-05-22 13:54 | 2030-05-22 15:24 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 9 | 18 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1239.4 | 1508.5
2030-05-22 15:24 | 2030-05-22 17:09 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 18 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1241.15 | 1506.75
2030-05-22 17:09 | 2030-05-22 18:39 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 9 | 18 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1242.65 | 1505.25
2030-05-22 18:39 | 2030-05-22 20:24 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 9 | 18 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1244.4 | 1503.5
2030-05-22 20:24 | 2030-05-22 21:54 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 9 | 18 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1245.9 | 1502
2030-05-22 21:54 | 2030-05-22 22:54 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 9 | 18 | 40 |  | Standalone |  | 1 | 1 | 1246.9 | 1501
2030-05-22 22:54 | 2030-05-22 23:54 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 9 | 18 | 41 |  | Standalone |  | 1 | 1 | 1247.9 | 1500
2030-05-22 23:54 | 2030-05-23 02:54 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 9 | 18 | 42 |  | Standalone |  | 1 | 3 | 1250.9 | 1497
2030-05-23 02:54 | 2030-05-23 05:54 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 9 | 18 | 43 |  | Standalone |  | 1 | 3 | 1253.9 | 1494
2030-05-23 05:54 | 2030-05-23 07:54 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 9 | 18 | 44 |  | Standalone |  | 1 | 3 | 1255.9 | 1492
2030-05-23 07:54 | 2030-05-23 13:06 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 9 |  | 45 |  | Standalone |  | 1 | 7.8 | 1261.1 | 1486.8
2030-05-23 13:06 | 2030-05-23 14:06 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 10 |  | 1 |  | Standalone |  | 1 | 1.5 | 1262.1 | 1485.8
2030-05-23 14:06 | 2030-05-23 16:06 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 10 |  | 2 |  | Standalone |  | 1 | 3 | 1264.1 | 1483.8
2030-05-23 16:06 | 2030-05-23 19:06 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 10 |  | 3 |  | Standalone |  | 1 | 3 | 1267.1 | 1480.8
2030-05-23 19:06 | 2030-05-23 20:06 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 10 |  | 4 |  | Standalone |  | 1 | 1 | 1268.1 | 1479.8
2030-05-23 20:06 | 2030-05-23 22:21 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 10 |  | 5 |  | Standalone |  | 1 | 3.375 | 1270.35 | 1477.55
2030-05-23 22:21 | 2030-05-24 00:36 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 10 |  | 6 |  | Standalone |  | 1 | 3.375 | 1272.6 | 1475.3
2030-05-24 00:36 | 2030-05-24 02:06 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 10 |  | 7 |  | Standalone |  | 1 | 2.25 | 1274.1 | 1473.8
2030-05-24 02:06 | 2030-05-24 03:36 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 10 |  | 8 |  | Standalone |  | 1 | 2.25 | 1275.6 | 1472.3
2030-05-24 03:36 | 2030-05-24 05:06 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 10 |  | 9 |  | Standalone |  | 1 | 2.25 | 1277.1 | 1470.8
2030-05-24 05:06 | 2030-05-24 06:06 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 10 |  | 10 |  | Standalone |  | 1 | 1 | 1278.1 | 1469.8
2030-05-24 06:06 | 2030-05-24 08:21 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 10 |  | 11 |  | Standalone |  | 1 | 3.375 | 1280.35 | 1467.55
2030-05-24 08:21 | 2030-05-24 10:36 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 10 |  | 12 |  | Standalone |  | 1 | 3.375 | 1282.6 | 1465.3
2030-05-24 10:36 | 2030-05-24 12:06 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 10 |  | 13 |  | Standalone |  | 1 | 2.25 | 1284.1 | 1463.8
2030-05-24 12:06 | 2030-05-24 13:36 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 10 |  | 14 |  | Standalone |  | 1 | 2.25 | 1285.6 | 1462.3
2030-05-24 13:36 | 2030-05-24 15:06 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 10 |  | 15 |  | Standalone |  | 1 | 2.25 | 1287.1 | 1460.8
2030-05-24 15:06 | 2030-05-24 18:06 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 10 |  | 16 |  | Standalone |  | 1 | 3 | 1290.1 | 1457.8
2030-05-24 18:06 | 2030-05-24 20:06 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 10 |  | 17 |  | Standalone |  | 1 | 3 | 1292.1 | 1455.8
2030-05-24 20:06 | 2030-05-24 21:06 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 10 |  | 18 |  | Standalone |  | 1 | 1.5 | 1293.1 | 1454.8
2030-05-24 21:06 | 2030-05-25 02:18 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 10 |  | 19 |  | Standalone |  | 1 | 7.8 | 1298.3 | 1449.6
2030-05-25 02:18 | 2030-05-25 02:48 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 10 |  | 20 |  | Standalone |  | 1 | 0.75 | 1298.8 | 1449.1
2030-05-25 02:48 | 2030-05-25 03:48 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 10 | 19 | 21 |  | Standalone |  | 1 | 1.5 | 1299.8 | 1448.1
2030-05-25 03:48 | 2030-05-25 04:48 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 10 | 19 | 22 |  | Standalone |  | 1 | 1.5 | 1300.8 | 1447.1
2030-05-25 04:48 | 2030-05-25 08:48 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 10 | 19 | 23 |  | Standalone |  | 1 | 6 | 1304.8 | 1443.1
2030-05-25 08:48 | 2030-05-25 11:48 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 10 | 19 | 24 |  | Standalone |  | 1 | 3 | 1307.8 | 1440.1
2030-05-25 11:48 | 2030-05-25 12:48 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 10 | 19 | 25 |  | Standalone |  | 1 | 1 | 1308.8 | 1439.1
2030-05-25 12:48 | 2030-05-25 14:48 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 10 | 19 | 26 |  | Standalone |  | 1 | 2 | 1310.8 | 1437.1
2030-05-25 14:48 | 2030-05-25 15:48 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 10 | 19 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1311.8 | 1436.1
2030-05-25 15:48 | 2030-05-25 19:18 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 19 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1315.3 | 1432.6
2030-05-25 19:18 | 2030-05-25 19:48 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 10 | 19 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1315.8 | 1432.1
2030-05-25 19:48 | 2030-05-25 20:18 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 10 | 19 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1316.3 | 1431.6
2030-05-25 20:18 | 2030-05-25 22:33 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 19 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1318.55 | 1429.35
2030-05-25 22:33 | 2030-05-25 23:03 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 10 | 19 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1319.05 | 1428.85
2030-05-25 23:03 | 2030-05-25 23:33 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 10 | 19 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1319.55 | 1428.35
2030-05-25 23:33 | 2030-05-26 01:18 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 19 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1321.3 | 1426.6
2030-05-26 01:18 | 2030-05-26 02:48 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 10 | 19 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1322.8 | 1425.1
2030-05-26 02:48 | 2030-05-26 04:33 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 19 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1324.55 | 1423.35
2030-05-26 04:33 | 2030-05-26 06:03 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 10 | 19 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1326.05 | 1421.85
2030-05-26 06:03 | 2030-05-26 07:48 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 19 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1327.8 | 1420.1
2030-05-26 07:48 | 2030-05-26 09:18 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 10 | 19 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1329.3 | 1418.6
2030-05-26 09:18 | 2030-05-26 10:18 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 10 | 19 | 40 |  | Standalone |  | 1 | 1 | 1330.3 | 1417.6
2030-05-26 10:18 | 2030-05-26 11:18 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 10 | 19 | 41 |  | Standalone |  | 1 | 1 | 1331.3 | 1416.6
2030-05-26 11:18 | 2030-05-26 14:18 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 10 | 19 | 42 |  | Standalone |  | 1 | 3 | 1334.3 | 1413.6
2030-05-26 14:18 | 2030-05-26 17:18 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 10 | 19 | 43 |  | Standalone |  | 1 | 3 | 1337.3 | 1410.6
2030-05-26 17:18 | 2030-05-26 19:18 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 10 | 19 | 44 |  | Standalone |  | 1 | 3 | 1339.3 | 1408.6
2030-05-26 19:18 | 2030-05-26 20:18 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 10 | 20 | 21 |  | Standalone |  | 1 | 1.5 | 1340.3 | 1407.6
2030-05-26 20:18 | 2030-05-26 21:18 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 10 | 20 | 22 |  | Standalone |  | 1 | 1.5 | 1341.3 | 1406.6
2030-05-26 21:18 | 2030-05-27 01:18 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 10 | 20 | 23 |  | Standalone |  | 1 | 6 | 1345.3 | 1402.6
2030-05-27 01:18 | 2030-05-27 04:18 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 10 | 20 | 24 |  | Standalone |  | 1 | 3 | 1348.3 | 1399.6
2030-05-27 04:18 | 2030-05-27 05:18 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 10 | 20 | 25 |  | Standalone |  | 1 | 1 | 1349.3 | 1398.6
2030-05-27 05:18 | 2030-05-27 07:18 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 10 | 20 | 26 |  | Standalone |  | 1 | 2 | 1351.3 | 1396.6
2030-05-27 07:18 | 2030-05-27 08:18 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 10 | 20 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1352.3 | 1395.6
2030-05-27 08:18 | 2030-05-27 11:48 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 20 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1355.8 | 1392.1
2030-05-27 11:48 | 2030-05-27 12:18 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 10 | 20 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1356.3 | 1391.6
2030-05-27 12:18 | 2030-05-27 12:48 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 10 | 20 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1356.8 | 1391.1
2030-05-27 12:48 | 2030-05-27 15:03 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 20 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1359.05 | 1388.85
2030-05-27 15:03 | 2030-05-27 15:33 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 10 | 20 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1359.55 | 1388.35
2030-05-27 15:33 | 2030-05-27 16:03 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 10 | 20 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1360.05 | 1387.85
2030-05-27 16:03 | 2030-05-27 17:48 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 20 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1361.8 | 1386.1
2030-05-27 17:48 | 2030-05-27 19:18 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 10 | 20 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1363.3 | 1384.6
2030-05-27 19:18 | 2030-05-27 21:03 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 20 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1365.05 | 1382.85
2030-05-27 21:03 | 2030-05-27 22:33 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 10 | 20 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1366.55 | 1381.35
2030-05-27 22:33 | 2030-05-28 00:18 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 10 | 20 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1368.3 | 1379.6
2030-05-28 00:18 | 2030-05-28 01:48 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 10 | 20 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1369.8 | 1378.1
2030-05-28 01:48 | 2030-05-28 02:48 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 10 | 20 | 40 |  | Standalone |  | 1 | 1 | 1370.8 | 1377.1
2030-05-28 02:48 | 2030-05-28 03:48 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 10 | 20 | 41 |  | Standalone |  | 1 | 1 | 1371.8 | 1376.1
2030-05-28 03:48 | 2030-05-28 06:48 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 10 | 20 | 42 |  | Standalone |  | 1 | 3 | 1374.8 | 1373.1
2030-05-28 06:48 | 2030-05-28 09:48 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 10 | 20 | 43 |  | Standalone |  | 1 | 3 | 1377.8 | 1370.1
2030-05-28 09:48 | 2030-05-28 11:48 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 10 | 20 | 44 |  | Standalone |  | 1 | 3 | 1379.8 | 1368.1
2030-05-28 11:48 | 2030-05-28 17:00 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 10 |  | 45 |  | Standalone |  | 1 | 7.8 | 1385 | 1362.9
2030-05-28 17:00 | 2030-05-28 18:00 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 11 |  | 1 |  | Standalone |  | 1 | 1.5 | 1386 | 1361.9
2030-05-28 18:00 | 2030-05-28 20:00 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 11 |  | 2 |  | Standalone |  | 1 | 3 | 1388 | 1359.9
2030-05-28 20:00 | 2030-05-28 23:00 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 11 |  | 3 |  | Standalone |  | 1 | 3 | 1391 | 1356.9
2030-05-28 23:00 | 2030-05-29 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 11 |  | 4 |  | Standalone |  | 1 | 1 | 1392 | 1355.9
2030-05-29 | 2030-05-29 02:15 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 11 |  | 5 |  | Standalone |  | 1 | 3.375 | 1394.25 | 1353.65
2030-05-29 02:15 | 2030-05-29 04:30 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 11 |  | 6 |  | Standalone |  | 1 | 3.375 | 1396.5 | 1351.4
2030-05-29 04:30 | 2030-05-29 06:00 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 11 |  | 7 |  | Standalone |  | 1 | 2.25 | 1398 | 1349.9
2030-05-29 06:00 | 2030-05-29 07:30 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 11 |  | 8 |  | Standalone |  | 1 | 2.25 | 1399.5 | 1348.4
2030-05-29 07:30 | 2030-05-29 09:00 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 11 |  | 9 |  | Standalone |  | 1 | 2.25 | 1401 | 1346.9
2030-05-29 09:00 | 2030-05-29 10:00 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 11 |  | 10 |  | Standalone |  | 1 | 1 | 1402 | 1345.9
2030-05-29 10:00 | 2030-05-29 12:15 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 11 |  | 11 |  | Standalone |  | 1 | 3.375 | 1404.25 | 1343.65
2030-05-29 12:15 | 2030-05-29 14:30 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 11 |  | 12 |  | Standalone |  | 1 | 3.375 | 1406.5 | 1341.4
2030-05-29 14:30 | 2030-05-29 16:00 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 11 |  | 13 |  | Standalone |  | 1 | 2.25 | 1408 | 1339.9
2030-05-29 16:00 | 2030-05-29 17:30 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 11 |  | 14 |  | Standalone |  | 1 | 2.25 | 1409.5 | 1338.4
2030-05-29 17:30 | 2030-05-29 19:00 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 11 |  | 15 |  | Standalone |  | 1 | 2.25 | 1411 | 1336.9
2030-05-29 19:00 | 2030-05-29 22:00 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 11 |  | 16 |  | Standalone |  | 1 | 3 | 1414 | 1333.9
2030-05-29 22:00 | 2030-05-30 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 11 |  | 17 |  | Standalone |  | 1 | 3 | 1416 | 1331.9
2030-05-30 | 2030-05-30 01:00 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 11 |  | 18 |  | Standalone |  | 1 | 1.5 | 1417 | 1330.9
2030-05-30 01:00 | 2030-05-30 06:12 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 11 |  | 19 |  | Standalone |  | 1 | 7.8 | 1422.2 | 1325.7
2030-05-30 06:12 | 2030-05-30 06:42 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 11 |  | 20 |  | Standalone |  | 1 | 0.75 | 1422.7 | 1325.2
2030-05-30 06:42 | 2030-05-30 07:42 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 11 | 21 | 21 |  | Standalone |  | 1 | 1.5 | 1423.7 | 1324.2
2030-05-30 07:42 | 2030-05-30 08:42 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 11 | 21 | 22 |  | Standalone |  | 1 | 1.5 | 1424.7 | 1323.2
2030-05-30 08:42 | 2030-05-30 12:42 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 11 | 21 | 23 |  | Standalone |  | 1 | 6 | 1428.7 | 1319.2
2030-05-30 12:42 | 2030-05-30 15:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 11 | 21 | 24 |  | Standalone |  | 1 | 3 | 1431.7 | 1316.2
2030-05-30 15:42 | 2030-05-30 16:42 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 11 | 21 | 25 |  | Standalone |  | 1 | 1 | 1432.7 | 1315.2
2030-05-30 16:42 | 2030-05-30 18:42 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 11 | 21 | 26 |  | Standalone |  | 1 | 2 | 1434.7 | 1313.2
2030-05-30 18:42 | 2030-05-30 19:42 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 11 | 21 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1435.7 | 1312.2
2030-05-30 19:42 | 2030-05-30 23:12 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 21 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1439.2 | 1308.7
2030-05-30 23:12 | 2030-05-30 23:42 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 11 | 21 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1439.7 | 1308.2
2030-05-30 23:42 | 2030-05-31 00:12 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 11 | 21 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1440.2 | 1307.7
2030-05-31 00:12 | 2030-05-31 02:27 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 21 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1442.45 | 1305.45
2030-05-31 02:27 | 2030-05-31 02:57 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 11 | 21 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1442.95 | 1304.95
2030-05-31 02:57 | 2030-05-31 03:27 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 11 | 21 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1443.45 | 1304.45
2030-05-31 03:27 | 2030-05-31 05:12 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 21 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1445.2 | 1302.7
2030-05-31 05:12 | 2030-05-31 06:42 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 11 | 21 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1446.7 | 1301.2
2030-05-31 06:42 | 2030-05-31 08:27 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 21 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1448.45 | 1299.45
2030-05-31 08:27 | 2030-05-31 09:57 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 11 | 21 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1449.95 | 1297.95
2030-05-31 09:57 | 2030-05-31 11:42 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 21 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1451.7 | 1296.2
2030-05-31 11:42 | 2030-05-31 13:12 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 11 | 21 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1453.2 | 1294.7
2030-05-31 13:12 | 2030-05-31 14:12 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 11 | 21 | 40 |  | Standalone |  | 1 | 1 | 1454.2 | 1293.7
2030-05-31 14:12 | 2030-05-31 15:12 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 11 | 21 | 41 |  | Standalone |  | 1 | 1 | 1455.2 | 1292.7
2030-05-31 15:12 | 2030-05-31 18:12 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 11 | 21 | 42 |  | Standalone |  | 1 | 3 | 1458.2 | 1289.7
2030-05-31 18:12 | 2030-05-31 21:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 11 | 21 | 43 |  | Standalone |  | 1 | 3 | 1461.2 | 1286.7
2030-05-31 21:12 | 2030-05-31 23:12 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 11 | 21 | 44 |  | Standalone |  | 1 | 3 | 1463.2 | 1284.7
2030-05-31 23:12 | 2030-06-01 00:12 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 11 | 22 | 21 |  | Standalone |  | 1 | 1.5 | 1464.2 | 1283.7
2030-06-01 00:12 | 2030-06-01 01:12 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 11 | 22 | 22 |  | Standalone |  | 1 | 1.5 | 1465.2 | 1282.7
2030-06-01 01:12 | 2030-06-01 05:12 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 11 | 22 | 23 |  | Standalone |  | 1 | 6 | 1469.2 | 1278.7
2030-06-01 05:12 | 2030-06-01 08:12 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 11 | 22 | 24 |  | Standalone |  | 1 | 3 | 1472.2 | 1275.7
2030-06-01 08:12 | 2030-06-01 09:12 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 11 | 22 | 25 |  | Standalone |  | 1 | 1 | 1473.2 | 1274.7
2030-06-01 09:12 | 2030-06-01 11:12 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 11 | 22 | 26 |  | Standalone |  | 1 | 2 | 1475.2 | 1272.7
2030-06-01 11:12 | 2030-06-01 12:12 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 11 | 22 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1476.2 | 1271.7
2030-06-01 12:12 | 2030-06-01 15:42 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 22 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1479.7 | 1268.2
2030-06-01 15:42 | 2030-06-01 16:12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 11 | 22 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1480.2 | 1267.7
2030-06-01 16:12 | 2030-06-01 16:42 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 11 | 22 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1480.7 | 1267.2
2030-06-01 16:42 | 2030-06-01 18:57 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 22 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1482.95 | 1264.95
2030-06-01 18:57 | 2030-06-01 19:27 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 11 | 22 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1483.45 | 1264.45
2030-06-01 19:27 | 2030-06-01 19:57 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 11 | 22 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1483.95 | 1263.95
2030-06-01 19:57 | 2030-06-01 21:42 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 22 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1485.7 | 1262.2
2030-06-01 21:42 | 2030-06-01 23:12 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 11 | 22 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1487.2 | 1260.7
2030-06-01 23:12 | 2030-06-02 00:57 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 22 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1488.95 | 1258.95
2030-06-02 00:57 | 2030-06-02 02:27 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 11 | 22 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1490.45 | 1257.45
2030-06-02 02:27 | 2030-06-02 04:12 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 11 | 22 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1492.2 | 1255.7
2030-06-02 04:12 | 2030-06-02 05:42 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 11 | 22 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1493.7 | 1254.2
2030-06-02 05:42 | 2030-06-02 06:42 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 11 | 22 | 40 |  | Standalone |  | 1 | 1 | 1494.7 | 1253.2
2030-06-02 06:42 | 2030-06-02 07:42 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 11 | 22 | 41 |  | Standalone |  | 1 | 1 | 1495.7 | 1252.2
2030-06-02 07:42 | 2030-06-02 10:42 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 11 | 22 | 42 |  | Standalone |  | 1 | 3 | 1498.7 | 1249.2
2030-06-02 10:42 | 2030-06-02 13:42 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 11 | 22 | 43 |  | Standalone |  | 1 | 3 | 1501.7 | 1246.2
2030-06-02 13:42 | 2030-06-02 15:42 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 11 | 22 | 44 |  | Standalone |  | 1 | 3 | 1503.7 | 1244.2
2030-06-02 15:42 | 2030-06-02 20:54 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 11 |  | 45 |  | Standalone |  | 1 | 7.8 | 1508.9 | 1239
2030-06-02 20:54 | 2030-06-02 21:54 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 12 |  | 1 |  | Standalone |  | 1 | 1.5 | 1509.9 | 1238
2030-06-02 21:54 | 2030-06-02 23:54 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 12 |  | 2 |  | Standalone |  | 1 | 3 | 1511.9 | 1236
2030-06-02 23:54 | 2030-06-03 02:54 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 12 |  | 3 |  | Standalone |  | 1 | 3 | 1514.9 | 1233
2030-06-03 02:54 | 2030-06-03 03:54 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 12 |  | 4 |  | Standalone |  | 1 | 1 | 1515.9 | 1232
2030-06-03 03:54 | 2030-06-03 06:09 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 12 |  | 5 |  | Standalone |  | 1 | 3.375 | 1518.15 | 1229.75
2030-06-03 06:09 | 2030-06-03 08:24 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 12 |  | 6 |  | Standalone |  | 1 | 3.375 | 1520.4 | 1227.5
2030-06-03 08:24 | 2030-06-03 09:54 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 12 |  | 7 |  | Standalone |  | 1 | 2.25 | 1521.9 | 1226
2030-06-03 09:54 | 2030-06-03 11:24 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 12 |  | 8 |  | Standalone |  | 1 | 2.25 | 1523.4 | 1224.5
2030-06-03 11:24 | 2030-06-03 12:54 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 12 |  | 9 |  | Standalone |  | 1 | 2.25 | 1524.9 | 1223
2030-06-03 12:54 | 2030-06-03 13:54 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 12 |  | 10 |  | Standalone |  | 1 | 1 | 1525.9 | 1222
2030-06-03 13:54 | 2030-06-03 16:09 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 12 |  | 11 |  | Standalone |  | 1 | 3.375 | 1528.15 | 1219.75
2030-06-03 16:09 | 2030-06-03 18:24 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 12 |  | 12 |  | Standalone |  | 1 | 3.375 | 1530.4 | 1217.5
2030-06-03 18:24 | 2030-06-03 19:54 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 12 |  | 13 |  | Standalone |  | 1 | 2.25 | 1531.9 | 1216
2030-06-03 19:54 | 2030-06-03 21:24 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 12 |  | 14 |  | Standalone |  | 1 | 2.25 | 1533.4 | 1214.5
2030-06-03 21:24 | 2030-06-03 22:54 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 12 |  | 15 |  | Standalone |  | 1 | 2.25 | 1534.9 | 1213
2030-06-03 22:54 | 2030-06-04 01:54 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 12 |  | 16 |  | Standalone |  | 1 | 3 | 1537.9 | 1210
2030-06-04 01:54 | 2030-06-04 03:54 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 12 |  | 17 |  | Standalone |  | 1 | 3 | 1539.9 | 1208
2030-06-04 03:54 | 2030-06-04 04:54 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 12 |  | 18 |  | Standalone |  | 1 | 1.5 | 1540.9 | 1207
2030-06-04 04:54 | 2030-06-04 10:06 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 12 |  | 19 |  | Standalone |  | 1 | 7.8 | 1546.1 | 1201.8
2030-06-04 10:06 | 2030-06-04 10:36 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 12 |  | 20 |  | Standalone |  | 1 | 0.75 | 1546.6 | 1201.3
2030-06-04 10:36 | 2030-06-04 11:36 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 12 | 23 | 21 |  | Standalone |  | 1 | 1.5 | 1547.6 | 1200.3
2030-06-04 11:36 | 2030-06-04 12:36 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 12 | 23 | 22 |  | Standalone |  | 1 | 1.5 | 1548.6 | 1199.3
2030-06-04 12:36 | 2030-06-04 16:36 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 12 | 23 | 23 |  | Standalone |  | 1 | 6 | 1552.6 | 1195.3
2030-06-04 16:36 | 2030-06-04 19:36 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 12 | 23 | 24 |  | Standalone |  | 1 | 3 | 1555.6 | 1192.3
2030-06-04 19:36 | 2030-06-04 20:36 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 12 | 23 | 25 |  | Standalone |  | 1 | 1 | 1556.6 | 1191.3
2030-06-04 20:36 | 2030-06-04 22:36 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 12 | 23 | 26 |  | Standalone |  | 1 | 2 | 1558.6 | 1189.3
2030-06-04 22:36 | 2030-06-04 23:36 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 12 | 23 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1559.6 | 1188.3
2030-06-04 23:36 | 2030-06-05 03:06 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 23 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1563.1 | 1184.8
2030-06-05 03:06 | 2030-06-05 03:36 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 12 | 23 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1563.6 | 1184.3
2030-06-05 03:36 | 2030-06-05 04:06 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 12 | 23 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1564.1 | 1183.8
2030-06-05 04:06 | 2030-06-05 06:21 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 23 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1566.35 | 1181.55
2030-06-05 06:21 | 2030-06-05 06:51 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 12 | 23 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1566.85 | 1181.05
2030-06-05 06:51 | 2030-06-05 07:21 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 12 | 23 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1567.35 | 1180.55
2030-06-05 07:21 | 2030-06-05 09:06 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 23 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1569.1 | 1178.8
2030-06-05 09:06 | 2030-06-05 10:36 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 12 | 23 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1570.6 | 1177.3
2030-06-05 10:36 | 2030-06-05 12:21 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 23 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1572.35 | 1175.55
2030-06-05 12:21 | 2030-06-05 13:51 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 12 | 23 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1573.85 | 1174.05
2030-06-05 13:51 | 2030-06-05 15:36 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 23 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1575.6 | 1172.3
2030-06-05 15:36 | 2030-06-05 17:06 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 12 | 23 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1577.1 | 1170.8
2030-06-05 17:06 | 2030-06-05 18:06 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 12 | 23 | 40 |  | Standalone |  | 1 | 1 | 1578.1 | 1169.8
2030-06-05 18:06 | 2030-06-05 19:06 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 12 | 23 | 41 |  | Standalone |  | 1 | 1 | 1579.1 | 1168.8
2030-06-05 19:06 | 2030-06-05 22:06 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 12 | 23 | 42 |  | Standalone |  | 1 | 3 | 1582.1 | 1165.8
2030-06-05 22:06 | 2030-06-06 01:06 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 12 | 23 | 43 |  | Standalone |  | 1 | 3 | 1585.1 | 1162.8
2030-06-06 01:06 | 2030-06-06 03:06 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 12 | 23 | 44 |  | Standalone |  | 1 | 3 | 1587.1 | 1160.8
2030-06-06 03:06 | 2030-06-06 04:06 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 12 | 24 | 21 |  | Standalone |  | 1 | 1.5 | 1588.1 | 1159.8
2030-06-06 04:06 | 2030-06-06 05:06 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 12 | 24 | 22 |  | Standalone |  | 1 | 1.5 | 1589.1 | 1158.8
2030-06-06 05:06 | 2030-06-06 09:06 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 12 | 24 | 23 |  | Standalone |  | 1 | 6 | 1593.1 | 1154.8
2030-06-06 09:06 | 2030-06-06 12:06 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 12 | 24 | 24 |  | Standalone |  | 1 | 3 | 1596.1 | 1151.8
2030-06-06 12:06 | 2030-06-06 13:06 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 12 | 24 | 25 |  | Standalone |  | 1 | 1 | 1597.1 | 1150.8
2030-06-06 13:06 | 2030-06-06 15:06 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 12 | 24 | 26 |  | Standalone |  | 1 | 2 | 1599.1 | 1148.8
2030-06-06 15:06 | 2030-06-06 16:06 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 12 | 24 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1600.1 | 1147.8
2030-06-06 16:06 | 2030-06-06 19:36 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 24 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1603.6 | 1144.3
2030-06-06 19:36 | 2030-06-06 20:06 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 12 | 24 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1604.1 | 1143.8
2030-06-06 20:06 | 2030-06-06 20:36 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 12 | 24 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1604.6 | 1143.3
2030-06-06 20:36 | 2030-06-06 22:51 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 24 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1606.85 | 1141.05
2030-06-06 22:51 | 2030-06-06 23:21 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 12 | 24 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1607.35 | 1140.55
2030-06-06 23:21 | 2030-06-06 23:51 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 12 | 24 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1607.85 | 1140.05
2030-06-06 23:51 | 2030-06-07 01:36 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 24 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1609.6 | 1138.3
2030-06-07 01:36 | 2030-06-07 03:06 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 12 | 24 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1611.1 | 1136.8
2030-06-07 03:06 | 2030-06-07 04:51 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 24 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1612.85 | 1135.05
2030-06-07 04:51 | 2030-06-07 06:21 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 12 | 24 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1614.35 | 1133.55
2030-06-07 06:21 | 2030-06-07 08:06 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 12 | 24 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1616.1 | 1131.8
2030-06-07 08:06 | 2030-06-07 09:36 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 12 | 24 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1617.6 | 1130.3
2030-06-07 09:36 | 2030-06-07 10:36 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 12 | 24 | 40 |  | Standalone |  | 1 | 1 | 1618.6 | 1129.3
2030-06-07 10:36 | 2030-06-07 11:36 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 12 | 24 | 41 |  | Standalone |  | 1 | 1 | 1619.6 | 1128.3
2030-06-07 11:36 | 2030-06-07 14:36 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 12 | 24 | 42 |  | Standalone |  | 1 | 3 | 1622.6 | 1125.3
2030-06-07 14:36 | 2030-06-07 17:36 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 12 | 24 | 43 |  | Standalone |  | 1 | 3 | 1625.6 | 1122.3
2030-06-07 17:36 | 2030-06-07 19:36 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 12 | 24 | 44 |  | Standalone |  | 1 | 3 | 1627.6 | 1120.3
2030-06-07 19:36 | 2030-06-08 00:48 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 12 |  | 45 |  | Standalone |  | 1 | 7.8 | 1632.8 | 1115.1
2030-06-08 00:48 | 2030-06-08 01:48 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 13 |  | 1 |  | Standalone |  | 1 | 1.5 | 1633.8 | 1114.1
2030-06-08 01:48 | 2030-06-08 03:48 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 13 |  | 2 |  | Standalone |  | 1 | 3 | 1635.8 | 1112.1
2030-06-08 03:48 | 2030-06-08 06:48 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 13 |  | 3 |  | Standalone |  | 1 | 3 | 1638.8 | 1109.1
2030-06-08 06:48 | 2030-06-08 07:48 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 13 |  | 4 |  | Standalone |  | 1 | 1 | 1639.8 | 1108.1
2030-06-08 07:48 | 2030-06-08 10:03 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 13 |  | 5 |  | Standalone |  | 1 | 3.375 | 1642.05 | 1105.85
2030-06-08 10:03 | 2030-06-08 12:18 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 13 |  | 6 |  | Standalone |  | 1 | 3.375 | 1644.3 | 1103.6
2030-06-08 12:18 | 2030-06-08 13:48 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 13 |  | 7 |  | Standalone |  | 1 | 2.25 | 1645.8 | 1102.1
2030-06-08 13:48 | 2030-06-08 15:18 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 13 |  | 8 |  | Standalone |  | 1 | 2.25 | 1647.3 | 1100.6
2030-06-08 15:18 | 2030-06-08 16:48 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 13 |  | 9 |  | Standalone |  | 1 | 2.25 | 1648.8 | 1099.1
2030-06-08 16:48 | 2030-06-08 17:48 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 13 |  | 10 |  | Standalone |  | 1 | 1 | 1649.8 | 1098.1
2030-06-08 17:48 | 2030-06-08 20:03 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 13 |  | 11 |  | Standalone |  | 1 | 3.375 | 1652.05 | 1095.85
2030-06-08 20:03 | 2030-06-08 22:18 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 13 |  | 12 |  | Standalone |  | 1 | 3.375 | 1654.3 | 1093.6
2030-06-08 22:18 | 2030-06-08 23:48 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 13 |  | 13 |  | Standalone |  | 1 | 2.25 | 1655.8 | 1092.1
2030-06-08 23:48 | 2030-06-09 01:18 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 13 |  | 14 |  | Standalone |  | 1 | 2.25 | 1657.3 | 1090.6
2030-06-09 01:18 | 2030-06-09 02:48 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 13 |  | 15 |  | Standalone |  | 1 | 2.25 | 1658.8 | 1089.1
2030-06-09 02:48 | 2030-06-09 05:48 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 13 |  | 16 |  | Standalone |  | 1 | 3 | 1661.8 | 1086.1
2030-06-09 05:48 | 2030-06-09 07:48 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 13 |  | 17 |  | Standalone |  | 1 | 3 | 1663.8 | 1084.1
2030-06-09 07:48 | 2030-06-09 08:48 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 13 |  | 18 |  | Standalone |  | 1 | 1.5 | 1664.8 | 1083.1
2030-06-09 08:48 | 2030-06-09 14:00 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 13 |  | 19 |  | Standalone |  | 1 | 7.8 | 1670 | 1077.9
2030-06-09 14:00 | 2030-06-09 14:30 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 13 |  | 20 |  | Standalone |  | 1 | 0.75 | 1670.5 | 1077.4
2030-06-09 14:30 | 2030-06-09 15:30 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 13 | 25 | 21 |  | Standalone |  | 1 | 1.5 | 1671.5 | 1076.4
2030-06-09 15:30 | 2030-06-09 16:30 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 13 | 25 | 22 |  | Standalone |  | 1 | 1.5 | 1672.5 | 1075.4
2030-06-09 16:30 | 2030-06-09 20:30 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 13 | 25 | 23 |  | Standalone |  | 1 | 6 | 1676.5 | 1071.4
2030-06-09 20:30 | 2030-06-09 23:30 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 13 | 25 | 24 |  | Standalone |  | 1 | 3 | 1679.5 | 1068.4
2030-06-09 23:30 | 2030-06-10 00:30 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 13 | 25 | 25 |  | Standalone |  | 1 | 1 | 1680.5 | 1067.4
2030-06-10 00:30 | 2030-06-10 02:30 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 13 | 25 | 26 |  | Standalone |  | 1 | 2 | 1682.5 | 1065.4
2030-06-10 02:30 | 2030-06-10 03:30 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 13 | 25 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1683.5 | 1064.4
2030-06-10 03:30 | 2030-06-10 07:00 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 25 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1687 | 1060.9
2030-06-10 07:00 | 2030-06-10 07:30 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 13 | 25 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1687.5 | 1060.4
2030-06-10 07:30 | 2030-06-10 08:00 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 13 | 25 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1688 | 1059.9
2030-06-10 08:00 | 2030-06-10 10:15 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 25 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1690.25 | 1057.65
2030-06-10 10:15 | 2030-06-10 10:45 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 13 | 25 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1690.75 | 1057.15
2030-06-10 10:45 | 2030-06-10 11:15 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 13 | 25 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1691.25 | 1056.65
2030-06-10 11:15 | 2030-06-10 13:00 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 25 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1693 | 1054.9
2030-06-10 13:00 | 2030-06-10 14:30 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 13 | 25 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1694.5 | 1053.4
2030-06-10 14:30 | 2030-06-10 16:15 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 25 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1696.25 | 1051.65
2030-06-10 16:15 | 2030-06-10 17:45 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 13 | 25 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1697.75 | 1050.15
2030-06-10 17:45 | 2030-06-10 19:30 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 25 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1699.5 | 1048.4
2030-06-10 19:30 | 2030-06-10 21:00 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 13 | 25 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1701 | 1046.9
2030-06-10 21:00 | 2030-06-10 22:00 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 13 | 25 | 40 |  | Standalone |  | 1 | 1 | 1702 | 1045.9
2030-06-10 22:00 | 2030-06-10 23:00 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 13 | 25 | 41 |  | Standalone |  | 1 | 1 | 1703 | 1044.9
2030-06-10 23:00 | 2030-06-11 02:00 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 13 | 25 | 42 |  | Standalone |  | 1 | 3 | 1706 | 1041.9
2030-06-11 02:00 | 2030-06-11 05:00 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 13 | 25 | 43 |  | Standalone |  | 1 | 3 | 1709 | 1038.9
2030-06-11 05:00 | 2030-06-11 07:00 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 13 | 25 | 44 |  | Standalone |  | 1 | 3 | 1711 | 1036.9
2030-06-11 07:00 | 2030-06-11 08:00 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 13 | 26 | 21 |  | Standalone |  | 1 | 1.5 | 1712 | 1035.9
2030-06-11 08:00 | 2030-06-11 09:00 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 13 | 26 | 22 |  | Standalone |  | 1 | 1.5 | 1713 | 1034.9
2030-06-11 09:00 | 2030-06-11 13:00 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 13 | 26 | 23 |  | Standalone |  | 1 | 6 | 1717 | 1030.9
2030-06-11 13:00 | 2030-06-11 16:00 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 13 | 26 | 24 |  | Standalone |  | 1 | 3 | 1720 | 1027.9
2030-06-11 16:00 | 2030-06-11 17:00 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 13 | 26 | 25 |  | Standalone |  | 1 | 1 | 1721 | 1026.9
2030-06-11 17:00 | 2030-06-11 19:00 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 13 | 26 | 26 |  | Standalone |  | 1 | 2 | 1723 | 1024.9
2030-06-11 19:00 | 2030-06-11 20:00 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 13 | 26 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1724 | 1023.9
2030-06-11 20:00 | 2030-06-11 23:30 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 26 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1727.5 | 1020.4
2030-06-11 23:30 | 2030-06-12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 13 | 26 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1728 | 1019.9
2030-06-12 | 2030-06-12 00:30 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 13 | 26 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1728.5 | 1019.4
2030-06-12 00:30 | 2030-06-12 02:45 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 26 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1730.75 | 1017.15
2030-06-12 02:45 | 2030-06-12 03:15 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 13 | 26 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1731.25 | 1016.65
2030-06-12 03:15 | 2030-06-12 03:45 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 13 | 26 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1731.75 | 1016.15
2030-06-12 03:45 | 2030-06-12 05:30 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 26 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1733.5 | 1014.4
2030-06-12 05:30 | 2030-06-12 07:00 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 13 | 26 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1735 | 1012.9
2030-06-12 07:00 | 2030-06-12 08:45 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 26 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1736.75 | 1011.15
2030-06-12 08:45 | 2030-06-12 10:15 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 13 | 26 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1738.25 | 1009.65
2030-06-12 10:15 | 2030-06-12 12:00 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 13 | 26 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1740 | 1007.9
2030-06-12 12:00 | 2030-06-12 13:30 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 13 | 26 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1741.5 | 1006.4
2030-06-12 13:30 | 2030-06-12 14:30 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 13 | 26 | 40 |  | Standalone |  | 1 | 1 | 1742.5 | 1005.4
2030-06-12 14:30 | 2030-06-12 15:30 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 13 | 26 | 41 |  | Standalone |  | 1 | 1 | 1743.5 | 1004.4
2030-06-12 15:30 | 2030-06-12 18:30 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 13 | 26 | 42 |  | Standalone |  | 1 | 3 | 1746.5 | 1001.4
2030-06-12 18:30 | 2030-06-12 21:30 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 13 | 26 | 43 |  | Standalone |  | 1 | 3 | 1749.5 | 998.4
2030-06-12 21:30 | 2030-06-12 23:30 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 13 | 26 | 44 |  | Standalone |  | 1 | 3 | 1751.5 | 996.4
2030-06-12 23:30 | 2030-06-13 04:42 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 13 |  | 45 |  | Standalone |  | 1 | 7.8 | 1756.7 | 991.2
2030-06-13 04:42 | 2030-06-13 05:42 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 14 |  | 1 |  | Standalone |  | 1 | 1.5 | 1757.7 | 990.2
2030-06-13 05:42 | 2030-06-13 07:42 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 14 |  | 2 |  | Standalone |  | 1 | 3 | 1759.7 | 988.2
2030-06-13 07:42 | 2030-06-13 10:42 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 14 |  | 3 |  | Standalone |  | 1 | 3 | 1762.7 | 985.2
2030-06-13 10:42 | 2030-06-13 11:42 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 14 |  | 4 |  | Standalone |  | 1 | 1 | 1763.7 | 984.2
2030-06-13 11:42 | 2030-06-13 13:57 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 14 |  | 5 |  | Standalone |  | 1 | 3.375 | 1765.95 | 981.95
2030-06-13 13:57 | 2030-06-13 16:12 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 14 |  | 6 |  | Standalone |  | 1 | 3.375 | 1768.2 | 979.7
2030-06-13 16:12 | 2030-06-13 17:42 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 14 |  | 7 |  | Standalone |  | 1 | 2.25 | 1769.7 | 978.2
2030-06-13 17:42 | 2030-06-13 19:12 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 14 |  | 8 |  | Standalone |  | 1 | 2.25 | 1771.2 | 976.7
2030-06-13 19:12 | 2030-06-13 20:42 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 14 |  | 9 |  | Standalone |  | 1 | 2.25 | 1772.7 | 975.2
2030-06-13 20:42 | 2030-06-13 21:42 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 14 |  | 10 |  | Standalone |  | 1 | 1 | 1773.7 | 974.2
2030-06-13 21:42 | 2030-06-13 23:57 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 14 |  | 11 |  | Standalone |  | 1 | 3.375 | 1775.95 | 971.95
2030-06-13 23:57 | 2030-06-14 02:12 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 14 |  | 12 |  | Standalone |  | 1 | 3.375 | 1778.2 | 969.7
2030-06-14 02:12 | 2030-06-14 03:42 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 14 |  | 13 |  | Standalone |  | 1 | 2.25 | 1779.7 | 968.2
2030-06-14 03:42 | 2030-06-14 05:12 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 14 |  | 14 |  | Standalone |  | 1 | 2.25 | 1781.2 | 966.7
2030-06-14 05:12 | 2030-06-14 06:42 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 14 |  | 15 |  | Standalone |  | 1 | 2.25 | 1782.7 | 965.2
2030-06-14 06:42 | 2030-06-14 09:42 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 14 |  | 16 |  | Standalone |  | 1 | 3 | 1785.7 | 962.2
2030-06-14 09:42 | 2030-06-14 11:42 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 14 |  | 17 |  | Standalone |  | 1 | 3 | 1787.7 | 960.2
2030-06-14 11:42 | 2030-06-14 12:42 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 14 |  | 18 |  | Standalone |  | 1 | 1.5 | 1788.7 | 959.2
2030-06-14 12:42 | 2030-06-14 17:54 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 14 |  | 19 |  | Standalone |  | 1 | 7.8 | 1793.9 | 954
2030-06-14 17:54 | 2030-06-14 18:24 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 14 |  | 20 |  | Standalone |  | 1 | 0.75 | 1794.4 | 953.5
2030-06-14 18:24 | 2030-06-14 19:24 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 14 | 27 | 21 |  | Standalone |  | 1 | 1.5 | 1795.4 | 952.5
2030-06-14 19:24 | 2030-06-14 20:24 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 14 | 27 | 22 |  | Standalone |  | 1 | 1.5 | 1796.4 | 951.5
2030-06-14 20:24 | 2030-06-15 00:24 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 14 | 27 | 23 |  | Standalone |  | 1 | 6 | 1800.4 | 947.5
2030-06-15 00:24 | 2030-06-15 03:24 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 14 | 27 | 24 |  | Standalone |  | 1 | 3 | 1803.4 | 944.5
2030-06-15 03:24 | 2030-06-15 04:24 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 14 | 27 | 25 |  | Standalone |  | 1 | 1 | 1804.4 | 943.5
2030-06-15 04:24 | 2030-06-15 06:24 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 14 | 27 | 26 |  | Standalone |  | 1 | 2 | 1806.4 | 941.5
2030-06-15 06:24 | 2030-06-15 07:24 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 14 | 27 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1807.4 | 940.5
2030-06-15 07:24 | 2030-06-15 10:54 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 27 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1810.9 | 937
2030-06-15 10:54 | 2030-06-15 11:24 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 14 | 27 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1811.4 | 936.5
2030-06-15 11:24 | 2030-06-15 11:54 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 14 | 27 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1811.9 | 936
2030-06-15 11:54 | 2030-06-15 14:09 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 27 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1814.15 | 933.75
2030-06-15 14:09 | 2030-06-15 14:39 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 14 | 27 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1814.65 | 933.25
2030-06-15 14:39 | 2030-06-15 15:09 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 14 | 27 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1815.15 | 932.75
2030-06-15 15:09 | 2030-06-15 16:54 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 27 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1816.9 | 931
2030-06-15 16:54 | 2030-06-15 18:24 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 14 | 27 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1818.4 | 929.5
2030-06-15 18:24 | 2030-06-15 20:09 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 27 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1820.15 | 927.75
2030-06-15 20:09 | 2030-06-15 21:39 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 14 | 27 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1821.65 | 926.25
2030-06-15 21:39 | 2030-06-15 23:24 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 27 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1823.4 | 924.5
2030-06-15 23:24 | 2030-06-16 00:54 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 14 | 27 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1824.9 | 923
2030-06-16 00:54 | 2030-06-16 01:54 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 14 | 27 | 40 |  | Standalone |  | 1 | 1 | 1825.9 | 922
2030-06-16 01:54 | 2030-06-16 02:54 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 14 | 27 | 41 |  | Standalone |  | 1 | 1 | 1826.9 | 921
2030-06-16 02:54 | 2030-06-16 05:54 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 14 | 27 | 42 |  | Standalone |  | 1 | 3 | 1829.9 | 918
2030-06-16 05:54 | 2030-06-16 08:54 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 14 | 27 | 43 |  | Standalone |  | 1 | 3 | 1832.9 | 915
2030-06-16 08:54 | 2030-06-16 10:54 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 14 | 27 | 44 |  | Standalone |  | 1 | 3 | 1834.9 | 913
2030-06-16 10:54 | 2030-06-16 11:54 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 14 | 28 | 21 |  | Standalone |  | 1 | 1.5 | 1835.9 | 912
2030-06-16 11:54 | 2030-06-16 12:54 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 14 | 28 | 22 |  | Standalone |  | 1 | 1.5 | 1836.9 | 911
2030-06-16 12:54 | 2030-06-16 16:54 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 14 | 28 | 23 |  | Standalone |  | 1 | 6 | 1840.9 | 907
2030-06-16 16:54 | 2030-06-16 19:54 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 14 | 28 | 24 |  | Standalone |  | 1 | 3 | 1843.9 | 904
2030-06-16 19:54 | 2030-06-16 20:54 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 14 | 28 | 25 |  | Standalone |  | 1 | 1 | 1844.9 | 903
2030-06-16 20:54 | 2030-06-16 22:54 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 14 | 28 | 26 |  | Standalone |  | 1 | 2 | 1846.9 | 901
2030-06-16 22:54 | 2030-06-16 23:54 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 14 | 28 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1847.9 | 900
2030-06-16 23:54 | 2030-06-17 03:24 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 28 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1851.4 | 896.5
2030-06-17 03:24 | 2030-06-17 03:54 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 14 | 28 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1851.9 | 896
2030-06-17 03:54 | 2030-06-17 04:24 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 14 | 28 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1852.4 | 895.5
2030-06-17 04:24 | 2030-06-17 06:39 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 28 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1854.65 | 893.25
2030-06-17 06:39 | 2030-06-17 07:09 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 14 | 28 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1855.15 | 892.75
2030-06-17 07:09 | 2030-06-17 07:39 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 14 | 28 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1855.65 | 892.25
2030-06-17 07:39 | 2030-06-17 09:24 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 28 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1857.4 | 890.5
2030-06-17 09:24 | 2030-06-17 10:54 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 14 | 28 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1858.9 | 889
2030-06-17 10:54 | 2030-06-17 12:39 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 28 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1860.65 | 887.25
2030-06-17 12:39 | 2030-06-17 14:09 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 14 | 28 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1862.15 | 885.75
2030-06-17 14:09 | 2030-06-17 15:54 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 14 | 28 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1863.9 | 884
2030-06-17 15:54 | 2030-06-17 17:24 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 14 | 28 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1865.4 | 882.5
2030-06-17 17:24 | 2030-06-17 18:24 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 14 | 28 | 40 |  | Standalone |  | 1 | 1 | 1866.4 | 881.5
2030-06-17 18:24 | 2030-06-17 19:24 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 14 | 28 | 41 |  | Standalone |  | 1 | 1 | 1867.4 | 880.5
2030-06-17 19:24 | 2030-06-17 22:24 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 14 | 28 | 42 |  | Standalone |  | 1 | 3 | 1870.4 | 877.5
2030-06-17 22:24 | 2030-06-18 01:24 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 14 | 28 | 43 |  | Standalone |  | 1 | 3 | 1873.4 | 874.5
2030-06-18 01:24 | 2030-06-18 03:24 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 14 | 28 | 44 |  | Standalone |  | 1 | 3 | 1875.4 | 872.5
2030-06-18 03:24 | 2030-06-18 08:36 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 14 |  | 45 |  | Standalone |  | 1 | 7.8 | 1880.6 | 867.3
2030-06-18 08:36 | 2030-06-18 09:36 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 15 |  | 1 |  | Standalone |  | 1 | 1.5 | 1881.6 | 866.3
2030-06-18 09:36 | 2030-06-18 11:36 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 15 |  | 2 |  | Standalone |  | 1 | 3 | 1883.6 | 864.3
2030-06-18 11:36 | 2030-06-18 14:36 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 15 |  | 3 |  | Standalone |  | 1 | 3 | 1886.6 | 861.3
2030-06-18 14:36 | 2030-06-18 15:36 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 15 |  | 4 |  | Standalone |  | 1 | 1 | 1887.6 | 860.3
2030-06-18 15:36 | 2030-06-18 17:51 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 15 |  | 5 |  | Standalone |  | 1 | 3.375 | 1889.85 | 858.05
2030-06-18 17:51 | 2030-06-18 20:06 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 15 |  | 6 |  | Standalone |  | 1 | 3.375 | 1892.1 | 855.8
2030-06-18 20:06 | 2030-06-18 21:36 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 15 |  | 7 |  | Standalone |  | 1 | 2.25 | 1893.6 | 854.3
2030-06-18 21:36 | 2030-06-18 23:06 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 15 |  | 8 |  | Standalone |  | 1 | 2.25 | 1895.1 | 852.8
2030-06-18 23:06 | 2030-06-19 00:36 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 15 |  | 9 |  | Standalone |  | 1 | 2.25 | 1896.6 | 851.3
2030-06-19 00:36 | 2030-06-19 01:36 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 15 |  | 10 |  | Standalone |  | 1 | 1 | 1897.6 | 850.3
2030-06-19 01:36 | 2030-06-19 03:51 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 15 |  | 11 |  | Standalone |  | 1 | 3.375 | 1899.85 | 848.05
2030-06-19 03:51 | 2030-06-19 06:06 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 15 |  | 12 |  | Standalone |  | 1 | 3.375 | 1902.1 | 845.8
2030-06-19 06:06 | 2030-06-19 07:36 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 15 |  | 13 |  | Standalone |  | 1 | 2.25 | 1903.6 | 844.3
2030-06-19 07:36 | 2030-06-19 09:06 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 15 |  | 14 |  | Standalone |  | 1 | 2.25 | 1905.1 | 842.8
2030-06-19 09:06 | 2030-06-19 10:36 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 15 |  | 15 |  | Standalone |  | 1 | 2.25 | 1906.6 | 841.3
2030-06-19 10:36 | 2030-06-19 13:36 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 15 |  | 16 |  | Standalone |  | 1 | 3 | 1909.6 | 838.3
2030-06-19 13:36 | 2030-06-19 15:36 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 15 |  | 17 |  | Standalone |  | 1 | 3 | 1911.6 | 836.3
2030-06-19 15:36 | 2030-06-19 16:36 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 15 |  | 18 |  | Standalone |  | 1 | 1.5 | 1912.6 | 835.3
2030-06-19 16:36 | 2030-06-19 21:48 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 15 |  | 19 |  | Standalone |  | 1 | 7.8 | 1917.8 | 830.1
2030-06-19 21:48 | 2030-06-19 22:18 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 15 |  | 20 |  | Standalone |  | 1 | 0.75 | 1918.3 | 829.6
2030-06-19 22:18 | 2030-06-19 23:18 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 15 | 29 | 21 |  | Standalone |  | 1 | 1.5 | 1919.3 | 828.6
2030-06-19 23:18 | 2030-06-20 00:18 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 15 | 29 | 22 |  | Standalone |  | 1 | 1.5 | 1920.3 | 827.6
2030-06-20 00:18 | 2030-06-20 04:18 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 15 | 29 | 23 |  | Standalone |  | 1 | 6 | 1924.3 | 823.6
2030-06-20 04:18 | 2030-06-20 07:18 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 15 | 29 | 24 |  | Standalone |  | 1 | 3 | 1927.3 | 820.6
2030-06-20 07:18 | 2030-06-20 08:18 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 15 | 29 | 25 |  | Standalone |  | 1 | 1 | 1928.3 | 819.6
2030-06-20 08:18 | 2030-06-20 10:18 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 15 | 29 | 26 |  | Standalone |  | 1 | 2 | 1930.3 | 817.6
2030-06-20 10:18 | 2030-06-20 11:18 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 15 | 29 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1931.3 | 816.6
2030-06-20 11:18 | 2030-06-20 14:48 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 29 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1934.8 | 813.1
2030-06-20 14:48 | 2030-06-20 15:18 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 15 | 29 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1935.3 | 812.6
2030-06-20 15:18 | 2030-06-20 15:48 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 15 | 29 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1935.8 | 812.1
2030-06-20 15:48 | 2030-06-20 18:03 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 29 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1938.05 | 809.85
2030-06-20 18:03 | 2030-06-20 18:33 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 15 | 29 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1938.55 | 809.35
2030-06-20 18:33 | 2030-06-20 19:03 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 15 | 29 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1939.05 | 808.85
2030-06-20 19:03 | 2030-06-20 20:48 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 29 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1940.8 | 807.1
2030-06-20 20:48 | 2030-06-20 22:18 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 15 | 29 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1942.3 | 805.6
2030-06-20 22:18 | 2030-06-21 00:03 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 29 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1944.05 | 803.85
2030-06-21 00:03 | 2030-06-21 01:33 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 15 | 29 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1945.55 | 802.35
2030-06-21 01:33 | 2030-06-21 03:18 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 29 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1947.3 | 800.6
2030-06-21 03:18 | 2030-06-21 04:48 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 15 | 29 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1948.8 | 799.1
2030-06-21 04:48 | 2030-06-21 05:48 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 15 | 29 | 40 |  | Standalone |  | 1 | 1 | 1949.8 | 798.1
2030-06-21 05:48 | 2030-06-21 06:48 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 15 | 29 | 41 |  | Standalone |  | 1 | 1 | 1950.8 | 797.1
2030-06-21 06:48 | 2030-06-21 09:48 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 15 | 29 | 42 |  | Standalone |  | 1 | 3 | 1953.8 | 794.1
2030-06-21 09:48 | 2030-06-21 12:48 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 15 | 29 | 43 |  | Standalone |  | 1 | 3 | 1956.8 | 791.1
2030-06-21 12:48 | 2030-06-21 14:48 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 15 | 29 | 44 |  | Standalone |  | 1 | 3 | 1958.8 | 789.1
2030-06-21 14:48 | 2030-06-21 15:48 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 15 | 30 | 21 |  | Standalone |  | 1 | 1.5 | 1959.8 | 788.1
2030-06-21 15:48 | 2030-06-21 16:48 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 15 | 30 | 22 |  | Standalone |  | 1 | 1.5 | 1960.8 | 787.1
2030-06-21 16:48 | 2030-06-21 20:48 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 15 | 30 | 23 |  | Standalone |  | 1 | 6 | 1964.8 | 783.1
2030-06-21 20:48 | 2030-06-21 23:48 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 15 | 30 | 24 |  | Standalone |  | 1 | 3 | 1967.8 | 780.1
2030-06-21 23:48 | 2030-06-22 00:48 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 15 | 30 | 25 |  | Standalone |  | 1 | 1 | 1968.8 | 779.1
2030-06-22 00:48 | 2030-06-22 02:48 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 15 | 30 | 26 |  | Standalone |  | 1 | 2 | 1970.8 | 777.1
2030-06-22 02:48 | 2030-06-22 03:48 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 15 | 30 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 1971.8 | 776.1
2030-06-22 03:48 | 2030-06-22 07:18 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 30 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 1975.3 | 772.6
2030-06-22 07:18 | 2030-06-22 07:48 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 15 | 30 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 1975.8 | 772.1
2030-06-22 07:48 | 2030-06-22 08:18 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 15 | 30 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 1976.3 | 771.6
2030-06-22 08:18 | 2030-06-22 10:33 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 30 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 1978.55 | 769.35
2030-06-22 10:33 | 2030-06-22 11:03 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 15 | 30 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 1979.05 | 768.85
2030-06-22 11:03 | 2030-06-22 11:33 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 15 | 30 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 1979.55 | 768.35
2030-06-22 11:33 | 2030-06-22 13:18 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 30 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 1981.3 | 766.6
2030-06-22 13:18 | 2030-06-22 14:48 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 15 | 30 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 1982.8 | 765.1
2030-06-22 14:48 | 2030-06-22 16:33 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 30 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 1984.55 | 763.35
2030-06-22 16:33 | 2030-06-22 18:03 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 15 | 30 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 1986.05 | 761.85
2030-06-22 18:03 | 2030-06-22 19:48 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 15 | 30 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 1987.8 | 760.1
2030-06-22 19:48 | 2030-06-22 21:18 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 15 | 30 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 1989.3 | 758.6
2030-06-22 21:18 | 2030-06-22 22:18 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 15 | 30 | 40 |  | Standalone |  | 1 | 1 | 1990.3 | 757.6
2030-06-22 22:18 | 2030-06-22 23:18 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 15 | 30 | 41 |  | Standalone |  | 1 | 1 | 1991.3 | 756.6
2030-06-22 23:18 | 2030-06-23 02:18 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 15 | 30 | 42 |  | Standalone |  | 1 | 3 | 1994.3 | 753.6
2030-06-23 02:18 | 2030-06-23 05:18 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 15 | 30 | 43 |  | Standalone |  | 1 | 3 | 1997.3 | 750.6
2030-06-23 05:18 | 2030-06-23 07:18 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 15 | 30 | 44 |  | Standalone |  | 1 | 3 | 1999.3 | 748.6
2030-06-23 07:18 | 2030-06-23 12:30 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 15 |  | 45 |  | Standalone |  | 1 | 7.8 | 2004.5 | 743.4
2030-06-23 12:30 | 2030-06-23 13:30 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 16 |  | 1 |  | Standalone |  | 1 | 1.5 | 2005.5 | 742.4
2030-06-23 13:30 | 2030-06-23 15:30 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 16 |  | 2 |  | Standalone |  | 1 | 3 | 2007.5 | 740.4
2030-06-23 15:30 | 2030-06-23 18:30 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 16 |  | 3 |  | Standalone |  | 1 | 3 | 2010.5 | 737.4
2030-06-23 18:30 | 2030-06-23 19:30 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 16 |  | 4 |  | Standalone |  | 1 | 1 | 2011.5 | 736.4
2030-06-23 19:30 | 2030-06-23 21:45 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 16 |  | 5 |  | Standalone |  | 1 | 3.375 | 2013.75 | 734.15
2030-06-23 21:45 | 2030-06-24 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 16 |  | 6 |  | Standalone |  | 1 | 3.375 | 2016 | 731.9
2030-06-24 | 2030-06-24 01:30 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 16 |  | 7 |  | Standalone |  | 1 | 2.25 | 2017.5 | 730.4
2030-06-24 01:30 | 2030-06-24 03:00 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 16 |  | 8 |  | Standalone |  | 1 | 2.25 | 2019 | 728.9
2030-06-24 03:00 | 2030-06-24 04:30 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 16 |  | 9 |  | Standalone |  | 1 | 2.25 | 2020.5 | 727.4
2030-06-24 04:30 | 2030-06-24 05:30 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 16 |  | 10 |  | Standalone |  | 1 | 1 | 2021.5 | 726.4
2030-06-24 05:30 | 2030-06-24 07:45 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 16 |  | 11 |  | Standalone |  | 1 | 3.375 | 2023.75 | 724.15
2030-06-24 07:45 | 2030-06-24 10:00 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 16 |  | 12 |  | Standalone |  | 1 | 3.375 | 2026 | 721.9
2030-06-24 10:00 | 2030-06-24 11:30 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 16 |  | 13 |  | Standalone |  | 1 | 2.25 | 2027.5 | 720.4
2030-06-24 11:30 | 2030-06-24 13:00 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 16 |  | 14 |  | Standalone |  | 1 | 2.25 | 2029 | 718.9
2030-06-24 13:00 | 2030-06-24 14:30 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 16 |  | 15 |  | Standalone |  | 1 | 2.25 | 2030.5 | 717.4
2030-06-24 14:30 | 2030-06-24 17:30 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 16 |  | 16 |  | Standalone |  | 1 | 3 | 2033.5 | 714.4
2030-06-24 17:30 | 2030-06-24 19:30 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 16 |  | 17 |  | Standalone |  | 1 | 3 | 2035.5 | 712.4
2030-06-24 19:30 | 2030-06-24 20:30 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 16 |  | 18 |  | Standalone |  | 1 | 1.5 | 2036.5 | 711.4
2030-06-24 20:30 | 2030-06-25 01:42 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 16 |  | 19 |  | Standalone |  | 1 | 7.8 | 2041.7 | 706.2
2030-06-25 01:42 | 2030-06-25 02:12 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 16 |  | 20 |  | Standalone |  | 1 | 0.75 | 2042.2 | 705.7
2030-06-25 02:12 | 2030-06-25 03:12 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 16 | 31 | 21 |  | Standalone |  | 1 | 1.5 | 2043.2 | 704.7
2030-06-25 03:12 | 2030-06-25 04:12 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 16 | 31 | 22 |  | Standalone |  | 1 | 1.5 | 2044.2 | 703.7
2030-06-25 04:12 | 2030-06-25 08:12 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 16 | 31 | 23 |  | Standalone |  | 1 | 6 | 2048.2 | 699.7
2030-06-25 08:12 | 2030-06-25 11:12 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 16 | 31 | 24 |  | Standalone |  | 1 | 3 | 2051.2 | 696.7
2030-06-25 11:12 | 2030-06-25 12:12 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 16 | 31 | 25 |  | Standalone |  | 1 | 1 | 2052.2 | 695.7
2030-06-25 12:12 | 2030-06-25 14:12 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 16 | 31 | 26 |  | Standalone |  | 1 | 2 | 2054.2 | 693.7
2030-06-25 14:12 | 2030-06-25 15:12 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 16 | 31 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2055.2 | 692.7
2030-06-25 15:12 | 2030-06-25 18:42 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 31 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2058.7 | 689.2
2030-06-25 18:42 | 2030-06-25 19:12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 16 | 31 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2059.2 | 688.7
2030-06-25 19:12 | 2030-06-25 19:42 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 16 | 31 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2059.7 | 688.2
2030-06-25 19:42 | 2030-06-25 21:57 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 31 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2061.95 | 685.95
2030-06-25 21:57 | 2030-06-25 22:27 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 16 | 31 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2062.45 | 685.45
2030-06-25 22:27 | 2030-06-25 22:57 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 16 | 31 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2062.95 | 684.95
2030-06-25 22:57 | 2030-06-26 00:42 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 31 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2064.7 | 683.2
2030-06-26 00:42 | 2030-06-26 02:12 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 16 | 31 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2066.2 | 681.7
2030-06-26 02:12 | 2030-06-26 03:57 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 31 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2067.95 | 679.95
2030-06-26 03:57 | 2030-06-26 05:27 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 16 | 31 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2069.45 | 678.45
2030-06-26 05:27 | 2030-06-26 07:12 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 31 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2071.2 | 676.7
2030-06-26 07:12 | 2030-06-26 08:42 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 16 | 31 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2072.7 | 675.2
2030-06-26 08:42 | 2030-06-26 09:42 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 16 | 31 | 40 |  | Standalone |  | 1 | 1 | 2073.7 | 674.2
2030-06-26 09:42 | 2030-06-26 10:42 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 16 | 31 | 41 |  | Standalone |  | 1 | 1 | 2074.7 | 673.2
2030-06-26 10:42 | 2030-06-26 13:42 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 16 | 31 | 42 |  | Standalone |  | 1 | 3 | 2077.7 | 670.2
2030-06-26 13:42 | 2030-06-26 16:42 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 16 | 31 | 43 |  | Standalone |  | 1 | 3 | 2080.7 | 667.2
2030-06-26 16:42 | 2030-06-26 18:42 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 16 | 31 | 44 |  | Standalone |  | 1 | 3 | 2082.7 | 665.2
2030-06-26 18:42 | 2030-06-26 19:42 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 16 | 32 | 21 |  | Standalone |  | 1 | 1.5 | 2083.7 | 664.2
2030-06-26 19:42 | 2030-06-26 20:42 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 16 | 32 | 22 |  | Standalone |  | 1 | 1.5 | 2084.7 | 663.2
2030-06-26 20:42 | 2030-06-27 00:42 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 16 | 32 | 23 |  | Standalone |  | 1 | 6 | 2088.7 | 659.2
2030-06-27 00:42 | 2030-06-27 03:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 16 | 32 | 24 |  | Standalone |  | 1 | 3 | 2091.7 | 656.2
2030-06-27 03:42 | 2030-06-27 04:42 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 16 | 32 | 25 |  | Standalone |  | 1 | 1 | 2092.7 | 655.2
2030-06-27 04:42 | 2030-06-27 06:42 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 16 | 32 | 26 |  | Standalone |  | 1 | 2 | 2094.7 | 653.2
2030-06-27 06:42 | 2030-06-27 07:42 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 16 | 32 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2095.7 | 652.2
2030-06-27 07:42 | 2030-06-27 11:12 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 32 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2099.2 | 648.7
2030-06-27 11:12 | 2030-06-27 11:42 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 16 | 32 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2099.7 | 648.2
2030-06-27 11:42 | 2030-06-27 12:12 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 16 | 32 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2100.2 | 647.7
2030-06-27 12:12 | 2030-06-27 14:27 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 32 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2102.45 | 645.45
2030-06-27 14:27 | 2030-06-27 14:57 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 16 | 32 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2102.95 | 644.95
2030-06-27 14:57 | 2030-06-27 15:27 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 16 | 32 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2103.45 | 644.45
2030-06-27 15:27 | 2030-06-27 17:12 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 32 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2105.2 | 642.7
2030-06-27 17:12 | 2030-06-27 18:42 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 16 | 32 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2106.7 | 641.2
2030-06-27 18:42 | 2030-06-27 20:27 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 32 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2108.45 | 639.45
2030-06-27 20:27 | 2030-06-27 21:57 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 16 | 32 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2109.95 | 637.95
2030-06-27 21:57 | 2030-06-27 23:42 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 16 | 32 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2111.7 | 636.2
2030-06-27 23:42 | 2030-06-28 01:12 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 16 | 32 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2113.2 | 634.7
2030-06-28 01:12 | 2030-06-28 02:12 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 16 | 32 | 40 |  | Standalone |  | 1 | 1 | 2114.2 | 633.7
2030-06-28 02:12 | 2030-06-28 03:12 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 16 | 32 | 41 |  | Standalone |  | 1 | 1 | 2115.2 | 632.7
2030-06-28 03:12 | 2030-06-28 06:12 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 16 | 32 | 42 |  | Standalone |  | 1 | 3 | 2118.2 | 629.7
2030-06-28 06:12 | 2030-06-28 09:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 16 | 32 | 43 |  | Standalone |  | 1 | 3 | 2121.2 | 626.7
2030-06-28 09:12 | 2030-06-28 11:12 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 16 | 32 | 44 |  | Standalone |  | 1 | 3 | 2123.2 | 624.7
2030-06-28 11:12 | 2030-06-28 16:24 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 16 |  | 45 |  | Standalone |  | 1 | 7.8 | 2128.4 | 619.5
2030-06-28 16:24 | 2030-06-28 17:24 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 17 |  | 1 |  | Standalone |  | 1 | 1.5 | 2129.4 | 618.5
2030-06-28 17:24 | 2030-06-28 19:24 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 17 |  | 2 |  | Standalone |  | 1 | 3 | 2131.4 | 616.5
2030-06-28 19:24 | 2030-06-28 22:24 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 17 |  | 3 |  | Standalone |  | 1 | 3 | 2134.4 | 613.5
2030-06-28 22:24 | 2030-06-28 23:24 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 17 |  | 4 |  | Standalone |  | 1 | 1 | 2135.4 | 612.5
2030-06-28 23:24 | 2030-06-29 01:39 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 17 |  | 5 |  | Standalone |  | 1 | 3.375 | 2137.65 | 610.25
2030-06-29 01:39 | 2030-06-29 03:54 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 17 |  | 6 |  | Standalone |  | 1 | 3.375 | 2139.9 | 608
2030-06-29 03:54 | 2030-06-29 05:24 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 17 |  | 7 |  | Standalone |  | 1 | 2.25 | 2141.4 | 606.5
2030-06-29 05:24 | 2030-06-29 06:54 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 17 |  | 8 |  | Standalone |  | 1 | 2.25 | 2142.9 | 605
2030-06-29 06:54 | 2030-06-29 08:24 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 17 |  | 9 |  | Standalone |  | 1 | 2.25 | 2144.4 | 603.5
2030-06-29 08:24 | 2030-06-29 09:24 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 17 |  | 10 |  | Standalone |  | 1 | 1 | 2145.4 | 602.5
2030-06-29 09:24 | 2030-06-29 11:39 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 17 |  | 11 |  | Standalone |  | 1 | 3.375 | 2147.65 | 600.25
2030-06-29 11:39 | 2030-06-29 13:54 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 17 |  | 12 |  | Standalone |  | 1 | 3.375 | 2149.9 | 598
2030-06-29 13:54 | 2030-06-29 15:24 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 17 |  | 13 |  | Standalone |  | 1 | 2.25 | 2151.4 | 596.5
2030-06-29 15:24 | 2030-06-29 16:54 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 17 |  | 14 |  | Standalone |  | 1 | 2.25 | 2152.9 | 595
2030-06-29 16:54 | 2030-06-29 18:24 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 17 |  | 15 |  | Standalone |  | 1 | 2.25 | 2154.4 | 593.5
2030-06-29 18:24 | 2030-06-29 21:24 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 17 |  | 16 |  | Standalone |  | 1 | 3 | 2157.4 | 590.5
2030-06-29 21:24 | 2030-06-29 23:24 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 17 |  | 17 |  | Standalone |  | 1 | 3 | 2159.4 | 588.5
2030-06-29 23:24 | 2030-06-30 00:24 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 17 |  | 18 |  | Standalone |  | 1 | 1.5 | 2160.4 | 587.5
2030-06-30 00:24 | 2030-06-30 05:36 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 17 |  | 19 |  | Standalone |  | 1 | 7.8 | 2165.6 | 582.3
2030-06-30 05:36 | 2030-06-30 06:06 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 17 |  | 20 |  | Standalone |  | 1 | 0.75 | 2166.1 | 581.8
2030-06-30 06:06 | 2030-06-30 07:06 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 17 | 33 | 21 |  | Standalone |  | 1 | 1.5 | 2167.1 | 580.8
2030-06-30 07:06 | 2030-06-30 08:06 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 17 | 33 | 22 |  | Standalone |  | 1 | 1.5 | 2168.1 | 579.8
2030-06-30 08:06 | 2030-06-30 12:06 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 17 | 33 | 23 |  | Standalone |  | 1 | 6 | 2172.1 | 575.8
2030-06-30 12:06 | 2030-06-30 15:06 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 17 | 33 | 24 |  | Standalone |  | 1 | 3 | 2175.1 | 572.8
2030-06-30 15:06 | 2030-06-30 16:06 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 17 | 33 | 25 |  | Standalone |  | 1 | 1 | 2176.1 | 571.8
2030-06-30 16:06 | 2030-06-30 18:06 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 17 | 33 | 26 |  | Standalone |  | 1 | 2 | 2178.1 | 569.8
2030-06-30 18:06 | 2030-06-30 19:06 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 17 | 33 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2179.1 | 568.8
2030-06-30 19:06 | 2030-06-30 22:36 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 33 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2182.6 | 565.3
2030-06-30 22:36 | 2030-06-30 23:06 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 17 | 33 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2183.1 | 564.8
2030-06-30 23:06 | 2030-06-30 23:36 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 17 | 33 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2183.6 | 564.3
2030-06-30 23:36 | 2030-07-01 01:51 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 33 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2185.85 | 562.05
2030-07-01 01:51 | 2030-07-01 02:21 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 17 | 33 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2186.35 | 561.55
2030-07-01 02:21 | 2030-07-01 02:51 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 17 | 33 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2186.85 | 561.05
2030-07-01 02:51 | 2030-07-01 04:36 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 33 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2188.6 | 559.3
2030-07-01 04:36 | 2030-07-01 06:06 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 17 | 33 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2190.1 | 557.8
2030-07-01 06:06 | 2030-07-01 07:51 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 33 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2191.85 | 556.05
2030-07-01 07:51 | 2030-07-01 09:21 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 17 | 33 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2193.35 | 554.55
2030-07-01 09:21 | 2030-07-01 11:06 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 33 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2195.1 | 552.8
2030-07-01 11:06 | 2030-07-01 12:36 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 17 | 33 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2196.6 | 551.3
2030-07-01 12:36 | 2030-07-01 13:36 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 17 | 33 | 40 |  | Standalone |  | 1 | 1 | 2197.6 | 550.3
2030-07-01 13:36 | 2030-07-01 14:36 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 17 | 33 | 41 |  | Standalone |  | 1 | 1 | 2198.6 | 549.3
2030-07-01 14:36 | 2030-07-01 17:36 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 17 | 33 | 42 |  | Standalone |  | 1 | 3 | 2201.6 | 546.3
2030-07-01 17:36 | 2030-07-01 20:36 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 17 | 33 | 43 |  | Standalone |  | 1 | 3 | 2204.6 | 543.3
2030-07-01 20:36 | 2030-07-01 22:36 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 17 | 33 | 44 |  | Standalone |  | 1 | 3 | 2206.6 | 541.3
2030-07-01 22:36 | 2030-07-01 23:36 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 17 | 34 | 21 |  | Standalone |  | 1 | 1.5 | 2207.6 | 540.3
2030-07-01 23:36 | 2030-07-02 00:36 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 17 | 34 | 22 |  | Standalone |  | 1 | 1.5 | 2208.6 | 539.3
2030-07-02 00:36 | 2030-07-02 04:36 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 17 | 34 | 23 |  | Standalone |  | 1 | 6 | 2212.6 | 535.3
2030-07-02 04:36 | 2030-07-02 07:36 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 17 | 34 | 24 |  | Standalone |  | 1 | 3 | 2215.6 | 532.3
2030-07-02 07:36 | 2030-07-02 08:36 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 17 | 34 | 25 |  | Standalone |  | 1 | 1 | 2216.6 | 531.3
2030-07-02 08:36 | 2030-07-02 10:36 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 17 | 34 | 26 |  | Standalone |  | 1 | 2 | 2218.6 | 529.3
2030-07-02 10:36 | 2030-07-02 11:36 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 17 | 34 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2219.6 | 528.3
2030-07-02 11:36 | 2030-07-02 15:06 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 34 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2223.1 | 524.8
2030-07-02 15:06 | 2030-07-02 15:36 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 17 | 34 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2223.6 | 524.3
2030-07-02 15:36 | 2030-07-02 16:06 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 17 | 34 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2224.1 | 523.8
2030-07-02 16:06 | 2030-07-02 18:21 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 34 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2226.35 | 521.55
2030-07-02 18:21 | 2030-07-02 18:51 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 17 | 34 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2226.85 | 521.05
2030-07-02 18:51 | 2030-07-02 19:21 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 17 | 34 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2227.35 | 520.55
2030-07-02 19:21 | 2030-07-02 21:06 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 34 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2229.1 | 518.8
2030-07-02 21:06 | 2030-07-02 22:36 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 17 | 34 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2230.6 | 517.3
2030-07-02 22:36 | 2030-07-03 00:21 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 34 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2232.35 | 515.55
2030-07-03 00:21 | 2030-07-03 01:51 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 17 | 34 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2233.85 | 514.05
2030-07-03 01:51 | 2030-07-03 03:36 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 17 | 34 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2235.6 | 512.3
2030-07-03 03:36 | 2030-07-03 05:06 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 17 | 34 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2237.1 | 510.8
2030-07-03 05:06 | 2030-07-03 06:06 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 17 | 34 | 40 |  | Standalone |  | 1 | 1 | 2238.1 | 509.8
2030-07-03 06:06 | 2030-07-03 07:06 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 17 | 34 | 41 |  | Standalone |  | 1 | 1 | 2239.1 | 508.8
2030-07-03 07:06 | 2030-07-03 10:06 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 17 | 34 | 42 |  | Standalone |  | 1 | 3 | 2242.1 | 505.8
2030-07-03 10:06 | 2030-07-03 13:06 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 17 | 34 | 43 |  | Standalone |  | 1 | 3 | 2245.1 | 502.8
2030-07-03 13:06 | 2030-07-03 15:06 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 17 | 34 | 44 |  | Standalone |  | 1 | 3 | 2247.1 | 500.8
2030-07-03 15:06 | 2030-07-03 20:18 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 17 |  | 45 |  | Standalone |  | 1 | 7.8 | 2252.3 | 495.6
2030-07-03 20:18 | 2030-07-03 21:18 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 18 |  | 1 |  | Standalone |  | 1 | 1.5 | 2253.3 | 494.6
2030-07-03 21:18 | 2030-07-03 23:18 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 18 |  | 2 |  | Standalone |  | 1 | 3 | 2255.3 | 492.6
2030-07-03 23:18 | 2030-07-04 02:18 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 18 |  | 3 |  | Standalone |  | 1 | 3 | 2258.3 | 489.6
2030-07-04 02:18 | 2030-07-04 03:18 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 18 |  | 4 |  | Standalone |  | 1 | 1 | 2259.3 | 488.6
2030-07-04 03:18 | 2030-07-04 05:33 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 18 |  | 5 |  | Standalone |  | 1 | 3.375 | 2261.55 | 486.35
2030-07-04 05:33 | 2030-07-04 07:48 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 18 |  | 6 |  | Standalone |  | 1 | 3.375 | 2263.8 | 484.1
2030-07-04 07:48 | 2030-07-04 09:18 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 18 |  | 7 |  | Standalone |  | 1 | 2.25 | 2265.3 | 482.6
2030-07-04 09:18 | 2030-07-04 10:48 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 18 |  | 8 |  | Standalone |  | 1 | 2.25 | 2266.8 | 481.1
2030-07-04 10:48 | 2030-07-04 12:18 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 18 |  | 9 |  | Standalone |  | 1 | 2.25 | 2268.3 | 479.6
2030-07-04 12:18 | 2030-07-04 13:18 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 18 |  | 10 |  | Standalone |  | 1 | 1 | 2269.3 | 478.6
2030-07-04 13:18 | 2030-07-04 15:33 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 18 |  | 11 |  | Standalone |  | 1 | 3.375 | 2271.55 | 476.35
2030-07-04 15:33 | 2030-07-04 17:48 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 18 |  | 12 |  | Standalone |  | 1 | 3.375 | 2273.8 | 474.1
2030-07-04 17:48 | 2030-07-04 19:18 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 18 |  | 13 |  | Standalone |  | 1 | 2.25 | 2275.3 | 472.6
2030-07-04 19:18 | 2030-07-04 20:48 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 18 |  | 14 |  | Standalone |  | 1 | 2.25 | 2276.8 | 471.1
2030-07-04 20:48 | 2030-07-04 22:18 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 18 |  | 15 |  | Standalone |  | 1 | 2.25 | 2278.3 | 469.6
2030-07-04 22:18 | 2030-07-05 01:18 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 18 |  | 16 |  | Standalone |  | 1 | 3 | 2281.3 | 466.6
2030-07-05 01:18 | 2030-07-05 03:18 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 18 |  | 17 |  | Standalone |  | 1 | 3 | 2283.3 | 464.6
2030-07-05 03:18 | 2030-07-05 04:18 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 18 |  | 18 |  | Standalone |  | 1 | 1.5 | 2284.3 | 463.6
2030-07-05 04:18 | 2030-07-05 09:30 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 18 |  | 19 |  | Standalone |  | 1 | 7.8 | 2289.5 | 458.4
2030-07-05 09:30 | 2030-07-05 10:00 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 18 |  | 20 |  | Standalone |  | 1 | 0.75 | 2290 | 457.9
2030-07-05 10:00 | 2030-07-05 11:00 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 18 | 35 | 21 |  | Standalone |  | 1 | 1.5 | 2291 | 456.9
2030-07-05 11:00 | 2030-07-05 12:00 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 18 | 35 | 22 |  | Standalone |  | 1 | 1.5 | 2292 | 455.9
2030-07-05 12:00 | 2030-07-05 16:00 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 18 | 35 | 23 |  | Standalone |  | 1 | 6 | 2296 | 451.9
2030-07-05 16:00 | 2030-07-05 19:00 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 18 | 35 | 24 |  | Standalone |  | 1 | 3 | 2299 | 448.9
2030-07-05 19:00 | 2030-07-05 20:00 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 18 | 35 | 25 |  | Standalone |  | 1 | 1 | 2300 | 447.9
2030-07-05 20:00 | 2030-07-05 22:00 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 18 | 35 | 26 |  | Standalone |  | 1 | 2 | 2302 | 445.9
2030-07-05 22:00 | 2030-07-05 23:00 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 18 | 35 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2303 | 444.9
2030-07-05 23:00 | 2030-07-06 02:30 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 35 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2306.5 | 441.4
2030-07-06 02:30 | 2030-07-06 03:00 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 18 | 35 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2307 | 440.9
2030-07-06 03:00 | 2030-07-06 03:30 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 18 | 35 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2307.5 | 440.4
2030-07-06 03:30 | 2030-07-06 05:45 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 35 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2309.75 | 438.15
2030-07-06 05:45 | 2030-07-06 06:15 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 18 | 35 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2310.25 | 437.65
2030-07-06 06:15 | 2030-07-06 06:45 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 18 | 35 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2310.75 | 437.15
2030-07-06 06:45 | 2030-07-06 08:30 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 35 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2312.5 | 435.4
2030-07-06 08:30 | 2030-07-06 10:00 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 18 | 35 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2314 | 433.9
2030-07-06 10:00 | 2030-07-06 11:45 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 35 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2315.75 | 432.15
2030-07-06 11:45 | 2030-07-06 13:15 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 18 | 35 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2317.25 | 430.65
2030-07-06 13:15 | 2030-07-06 15:00 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 35 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2319 | 428.9
2030-07-06 15:00 | 2030-07-06 16:30 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 18 | 35 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2320.5 | 427.4
2030-07-06 16:30 | 2030-07-06 17:30 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 18 | 35 | 40 |  | Standalone |  | 1 | 1 | 2321.5 | 426.4
2030-07-06 17:30 | 2030-07-06 18:30 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 18 | 35 | 41 |  | Standalone |  | 1 | 1 | 2322.5 | 425.4
2030-07-06 18:30 | 2030-07-06 21:30 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 18 | 35 | 42 |  | Standalone |  | 1 | 3 | 2325.5 | 422.4
2030-07-06 21:30 | 2030-07-07 00:30 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 18 | 35 | 43 |  | Standalone |  | 1 | 3 | 2328.5 | 419.4
2030-07-07 00:30 | 2030-07-07 02:30 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 18 | 35 | 44 |  | Standalone |  | 1 | 3 | 2330.5 | 417.4
2030-07-07 02:30 | 2030-07-07 03:30 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 18 | 36 | 21 |  | Standalone |  | 1 | 1.5 | 2331.5 | 416.4
2030-07-07 03:30 | 2030-07-07 04:30 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 18 | 36 | 22 |  | Standalone |  | 1 | 1.5 | 2332.5 | 415.4
2030-07-07 04:30 | 2030-07-07 08:30 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 18 | 36 | 23 |  | Standalone |  | 1 | 6 | 2336.5 | 411.4
2030-07-07 08:30 | 2030-07-07 11:30 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 18 | 36 | 24 |  | Standalone |  | 1 | 3 | 2339.5 | 408.4
2030-07-07 11:30 | 2030-07-07 12:30 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 18 | 36 | 25 |  | Standalone |  | 1 | 1 | 2340.5 | 407.4
2030-07-07 12:30 | 2030-07-07 14:30 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 18 | 36 | 26 |  | Standalone |  | 1 | 2 | 2342.5 | 405.4
2030-07-07 14:30 | 2030-07-07 15:30 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 18 | 36 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2343.5 | 404.4
2030-07-07 15:30 | 2030-07-07 19:00 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 36 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2347 | 400.9
2030-07-07 19:00 | 2030-07-07 19:30 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 18 | 36 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2347.5 | 400.4
2030-07-07 19:30 | 2030-07-07 20:00 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 18 | 36 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2348 | 399.9
2030-07-07 20:00 | 2030-07-07 22:15 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 36 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2350.25 | 397.65
2030-07-07 22:15 | 2030-07-07 22:45 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 18 | 36 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2350.75 | 397.15
2030-07-07 22:45 | 2030-07-07 23:15 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 18 | 36 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2351.25 | 396.65
2030-07-07 23:15 | 2030-07-08 01:00 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 36 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2353 | 394.9
2030-07-08 01:00 | 2030-07-08 02:30 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 18 | 36 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2354.5 | 393.4
2030-07-08 02:30 | 2030-07-08 04:15 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 36 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2356.25 | 391.65
2030-07-08 04:15 | 2030-07-08 05:45 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 18 | 36 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2357.75 | 390.15
2030-07-08 05:45 | 2030-07-08 07:30 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 18 | 36 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2359.5 | 388.4
2030-07-08 07:30 | 2030-07-08 09:00 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 18 | 36 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2361 | 386.9
2030-07-08 09:00 | 2030-07-08 10:00 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 18 | 36 | 40 |  | Standalone |  | 1 | 1 | 2362 | 385.9
2030-07-08 10:00 | 2030-07-08 11:00 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 18 | 36 | 41 |  | Standalone |  | 1 | 1 | 2363 | 384.9
2030-07-08 11:00 | 2030-07-08 14:00 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 18 | 36 | 42 |  | Standalone |  | 1 | 3 | 2366 | 381.9
2030-07-08 14:00 | 2030-07-08 17:00 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 18 | 36 | 43 |  | Standalone |  | 1 | 3 | 2369 | 378.9
2030-07-08 17:00 | 2030-07-08 19:00 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 18 | 36 | 44 |  | Standalone |  | 1 | 3 | 2371 | 376.9
2030-07-08 19:00 | 2030-07-09 00:12 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 18 |  | 45 |  | Standalone |  | 1 | 7.8 | 2376.2 | 371.7
2030-07-09 00:12 | 2030-07-09 01:12 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 19 |  | 1 |  | Standalone |  | 1 | 1.5 | 2377.2 | 370.7
2030-07-09 01:12 | 2030-07-09 03:12 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 19 |  | 2 |  | Standalone |  | 1 | 3 | 2379.2 | 368.7
2030-07-09 03:12 | 2030-07-09 06:12 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 19 |  | 3 |  | Standalone |  | 1 | 3 | 2382.2 | 365.7
2030-07-09 06:12 | 2030-07-09 07:12 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 19 |  | 4 |  | Standalone |  | 1 | 1 | 2383.2 | 364.7
2030-07-09 07:12 | 2030-07-09 09:27 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 19 |  | 5 |  | Standalone |  | 1 | 3.375 | 2385.45 | 362.45
2030-07-09 09:27 | 2030-07-09 11:42 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 19 |  | 6 |  | Standalone |  | 1 | 3.375 | 2387.7 | 360.2
2030-07-09 11:42 | 2030-07-09 13:12 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 19 |  | 7 |  | Standalone |  | 1 | 2.25 | 2389.2 | 358.7
2030-07-09 13:12 | 2030-07-09 14:42 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 19 |  | 8 |  | Standalone |  | 1 | 2.25 | 2390.7 | 357.2
2030-07-09 14:42 | 2030-07-09 16:12 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 19 |  | 9 |  | Standalone |  | 1 | 2.25 | 2392.2 | 355.7
2030-07-09 16:12 | 2030-07-09 17:12 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 19 |  | 10 |  | Standalone |  | 1 | 1 | 2393.2 | 354.7
2030-07-09 17:12 | 2030-07-09 19:27 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 19 |  | 11 |  | Standalone |  | 1 | 3.375 | 2395.45 | 352.45
2030-07-09 19:27 | 2030-07-09 21:42 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 19 |  | 12 |  | Standalone |  | 1 | 3.375 | 2397.7 | 350.2
2030-07-09 21:42 | 2030-07-09 23:12 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 19 |  | 13 |  | Standalone |  | 1 | 2.25 | 2399.2 | 348.7
2030-07-09 23:12 | 2030-07-10 00:42 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 19 |  | 14 |  | Standalone |  | 1 | 2.25 | 2400.7 | 347.2
2030-07-10 00:42 | 2030-07-10 02:12 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 19 |  | 15 |  | Standalone |  | 1 | 2.25 | 2402.2 | 345.7
2030-07-10 02:12 | 2030-07-10 05:12 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 19 |  | 16 |  | Standalone |  | 1 | 3 | 2405.2 | 342.7
2030-07-10 05:12 | 2030-07-10 07:12 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 19 |  | 17 |  | Standalone |  | 1 | 3 | 2407.2 | 340.7
2030-07-10 07:12 | 2030-07-10 08:12 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 19 |  | 18 |  | Standalone |  | 1 | 1.5 | 2408.2 | 339.7
2030-07-10 08:12 | 2030-07-10 13:24 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 19 |  | 19 |  | Standalone |  | 1 | 7.8 | 2413.4 | 334.5
2030-07-10 13:24 | 2030-07-10 13:54 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 19 |  | 20 |  | Standalone |  | 1 | 0.75 | 2413.9 | 334
2030-07-10 13:54 | 2030-07-10 14:54 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 19 | 37 | 21 |  | Standalone |  | 1 | 1.5 | 2414.9 | 333
2030-07-10 14:54 | 2030-07-10 15:54 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 19 | 37 | 22 |  | Standalone |  | 1 | 1.5 | 2415.9 | 332
2030-07-10 15:54 | 2030-07-10 19:54 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 19 | 37 | 23 |  | Standalone |  | 1 | 6 | 2419.9 | 328
2030-07-10 19:54 | 2030-07-10 22:54 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 19 | 37 | 24 |  | Standalone |  | 1 | 3 | 2422.9 | 325
2030-07-10 22:54 | 2030-07-10 23:54 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 19 | 37 | 25 |  | Standalone |  | 1 | 1 | 2423.9 | 324
2030-07-10 23:54 | 2030-07-11 01:54 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 19 | 37 | 26 |  | Standalone |  | 1 | 2 | 2425.9 | 322
2030-07-11 01:54 | 2030-07-11 02:54 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 19 | 37 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2426.9 | 321
2030-07-11 02:54 | 2030-07-11 06:24 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 37 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2430.4 | 317.5
2030-07-11 06:24 | 2030-07-11 06:54 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 19 | 37 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2430.9 | 317
2030-07-11 06:54 | 2030-07-11 07:24 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 19 | 37 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2431.4 | 316.5
2030-07-11 07:24 | 2030-07-11 09:39 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 37 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2433.65 | 314.25
2030-07-11 09:39 | 2030-07-11 10:09 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 19 | 37 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2434.15 | 313.75
2030-07-11 10:09 | 2030-07-11 10:39 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 19 | 37 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2434.65 | 313.25
2030-07-11 10:39 | 2030-07-11 12:24 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 37 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2436.4 | 311.5
2030-07-11 12:24 | 2030-07-11 13:54 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 19 | 37 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2437.9 | 310
2030-07-11 13:54 | 2030-07-11 15:39 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 37 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2439.65 | 308.25
2030-07-11 15:39 | 2030-07-11 17:09 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 19 | 37 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2441.15 | 306.75
2030-07-11 17:09 | 2030-07-11 18:54 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 37 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2442.9 | 305
2030-07-11 18:54 | 2030-07-11 20:24 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 19 | 37 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2444.4 | 303.5
2030-07-11 20:24 | 2030-07-11 21:24 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 19 | 37 | 40 |  | Standalone |  | 1 | 1 | 2445.4 | 302.5
2030-07-11 21:24 | 2030-07-11 22:24 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 19 | 37 | 41 |  | Standalone |  | 1 | 1 | 2446.4 | 301.5
2030-07-11 22:24 | 2030-07-12 01:24 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 19 | 37 | 42 |  | Standalone |  | 1 | 3 | 2449.4 | 298.5
2030-07-12 01:24 | 2030-07-12 04:24 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 19 | 37 | 43 |  | Standalone |  | 1 | 3 | 2452.4 | 295.5
2030-07-12 04:24 | 2030-07-12 06:24 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 19 | 37 | 44 |  | Standalone |  | 1 | 3 | 2454.4 | 293.5
2030-07-12 06:24 | 2030-07-12 07:24 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 19 | 38 | 21 |  | Standalone |  | 1 | 1.5 | 2455.4 | 292.5
2030-07-12 07:24 | 2030-07-12 08:24 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 19 | 38 | 22 |  | Standalone |  | 1 | 1.5 | 2456.4 | 291.5
2030-07-12 08:24 | 2030-07-12 12:24 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 19 | 38 | 23 |  | Standalone |  | 1 | 6 | 2460.4 | 287.5
2030-07-12 12:24 | 2030-07-12 15:24 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 19 | 38 | 24 |  | Standalone |  | 1 | 3 | 2463.4 | 284.5
2030-07-12 15:24 | 2030-07-12 16:24 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 19 | 38 | 25 |  | Standalone |  | 1 | 1 | 2464.4 | 283.5
2030-07-12 16:24 | 2030-07-12 18:24 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 19 | 38 | 26 |  | Standalone |  | 1 | 2 | 2466.4 | 281.5
2030-07-12 18:24 | 2030-07-12 19:24 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 19 | 38 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2467.4 | 280.5
2030-07-12 19:24 | 2030-07-12 22:54 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 38 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2470.9 | 277
2030-07-12 22:54 | 2030-07-12 23:24 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 19 | 38 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2471.4 | 276.5
2030-07-12 23:24 | 2030-07-12 23:54 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 19 | 38 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2471.9 | 276
2030-07-12 23:54 | 2030-07-13 02:09 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 38 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2474.15 | 273.75
2030-07-13 02:09 | 2030-07-13 02:39 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 19 | 38 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2474.65 | 273.25
2030-07-13 02:39 | 2030-07-13 03:09 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 19 | 38 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2475.15 | 272.75
2030-07-13 03:09 | 2030-07-13 04:54 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 38 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2476.9 | 271
2030-07-13 04:54 | 2030-07-13 06:24 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 19 | 38 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2478.4 | 269.5
2030-07-13 06:24 | 2030-07-13 08:09 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 38 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2480.15 | 267.75
2030-07-13 08:09 | 2030-07-13 09:39 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 19 | 38 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2481.65 | 266.25
2030-07-13 09:39 | 2030-07-13 11:24 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 19 | 38 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2483.4 | 264.5
2030-07-13 11:24 | 2030-07-13 12:54 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 19 | 38 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2484.9 | 263
2030-07-13 12:54 | 2030-07-13 13:54 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 19 | 38 | 40 |  | Standalone |  | 1 | 1 | 2485.9 | 262
2030-07-13 13:54 | 2030-07-13 14:54 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 19 | 38 | 41 |  | Standalone |  | 1 | 1 | 2486.9 | 261
2030-07-13 14:54 | 2030-07-13 17:54 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 19 | 38 | 42 |  | Standalone |  | 1 | 3 | 2489.9 | 258
2030-07-13 17:54 | 2030-07-13 20:54 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 19 | 38 | 43 |  | Standalone |  | 1 | 3 | 2492.9 | 255
2030-07-13 20:54 | 2030-07-13 22:54 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 19 | 38 | 44 |  | Standalone |  | 1 | 3 | 2494.9 | 253
2030-07-13 22:54 | 2030-07-14 04:06 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 19 |  | 45 |  | Standalone |  | 1 | 7.8 | 2500.1 | 247.8
2030-07-14 04:06 | 2030-07-14 05:06 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 20 |  | 1 |  | Standalone |  | 1 | 1.5 | 2501.1 | 246.8
2030-07-14 05:06 | 2030-07-14 07:06 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 20 |  | 2 |  | Standalone |  | 1 | 3 | 2503.1 | 244.8
2030-07-14 07:06 | 2030-07-14 10:06 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 20 |  | 3 |  | Standalone |  | 1 | 3 | 2506.1 | 241.8
2030-07-14 10:06 | 2030-07-14 11:06 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 20 |  | 4 |  | Standalone |  | 1 | 1 | 2507.1 | 240.8
2030-07-14 11:06 | 2030-07-14 13:21 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 20 |  | 5 |  | Standalone |  | 1 | 3.375 | 2509.35 | 238.55
2030-07-14 13:21 | 2030-07-14 15:36 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 20 |  | 6 |  | Standalone |  | 1 | 3.375 | 2511.6 | 236.3
2030-07-14 15:36 | 2030-07-14 17:06 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 20 |  | 7 |  | Standalone |  | 1 | 2.25 | 2513.1 | 234.8
2030-07-14 17:06 | 2030-07-14 18:36 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 20 |  | 8 |  | Standalone |  | 1 | 2.25 | 2514.6 | 233.3
2030-07-14 18:36 | 2030-07-14 20:06 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 20 |  | 9 |  | Standalone |  | 1 | 2.25 | 2516.1 | 231.8
2030-07-14 20:06 | 2030-07-14 21:06 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 20 |  | 10 |  | Standalone |  | 1 | 1 | 2517.1 | 230.8
2030-07-14 21:06 | 2030-07-14 23:21 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 20 |  | 11 |  | Standalone |  | 1 | 3.375 | 2519.35 | 228.55
2030-07-14 23:21 | 2030-07-15 01:36 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 20 |  | 12 |  | Standalone |  | 1 | 3.375 | 2521.6 | 226.3
2030-07-15 01:36 | 2030-07-15 03:06 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 20 |  | 13 |  | Standalone |  | 1 | 2.25 | 2523.1 | 224.8
2030-07-15 03:06 | 2030-07-15 04:36 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 20 |  | 14 |  | Standalone |  | 1 | 2.25 | 2524.6 | 223.3
2030-07-15 04:36 | 2030-07-15 06:06 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 20 |  | 15 |  | Standalone |  | 1 | 2.25 | 2526.1 | 221.8
2030-07-15 06:06 | 2030-07-15 09:06 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 20 |  | 16 |  | Standalone |  | 1 | 3 | 2529.1 | 218.8
2030-07-15 09:06 | 2030-07-15 11:06 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 20 |  | 17 |  | Standalone |  | 1 | 3 | 2531.1 | 216.8
2030-07-15 11:06 | 2030-07-15 12:06 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 20 |  | 18 |  | Standalone |  | 1 | 1.5 | 2532.1 | 215.8
2030-07-15 12:06 | 2030-07-15 17:18 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 20 |  | 19 |  | Standalone |  | 1 | 7.8 | 2537.3 | 210.6
2030-07-15 17:18 | 2030-07-15 17:48 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 20 |  | 20 |  | Standalone |  | 1 | 0.75 | 2537.8 | 210.1
2030-07-15 17:48 | 2030-07-15 18:48 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 20 | 39 | 21 |  | Standalone |  | 1 | 1.5 | 2538.8 | 209.1
2030-07-15 18:48 | 2030-07-15 19:48 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 20 | 39 | 22 |  | Standalone |  | 1 | 1.5 | 2539.8 | 208.1
2030-07-15 19:48 | 2030-07-15 23:48 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 20 | 39 | 23 |  | Standalone |  | 1 | 6 | 2543.8 | 204.1
2030-07-15 23:48 | 2030-07-16 02:48 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 20 | 39 | 24 |  | Standalone |  | 1 | 3 | 2546.8 | 201.1
2030-07-16 02:48 | 2030-07-16 03:48 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 20 | 39 | 25 |  | Standalone |  | 1 | 1 | 2547.8 | 200.1
2030-07-16 03:48 | 2030-07-16 05:48 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 20 | 39 | 26 |  | Standalone |  | 1 | 2 | 2549.8 | 198.1
2030-07-16 05:48 | 2030-07-16 06:48 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 20 | 39 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2550.8 | 197.1
2030-07-16 06:48 | 2030-07-16 10:18 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 39 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2554.3 | 193.6
2030-07-16 10:18 | 2030-07-16 10:48 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 20 | 39 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2554.8 | 193.1
2030-07-16 10:48 | 2030-07-16 11:18 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 20 | 39 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2555.3 | 192.6
2030-07-16 11:18 | 2030-07-16 13:33 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 39 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2557.55 | 190.35
2030-07-16 13:33 | 2030-07-16 14:03 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 20 | 39 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2558.05 | 189.85
2030-07-16 14:03 | 2030-07-16 14:33 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 20 | 39 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2558.55 | 189.35
2030-07-16 14:33 | 2030-07-16 16:18 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 39 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2560.3 | 187.6
2030-07-16 16:18 | 2030-07-16 17:48 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 20 | 39 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2561.8 | 186.1
2030-07-16 17:48 | 2030-07-16 19:33 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 39 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2563.55 | 184.35
2030-07-16 19:33 | 2030-07-16 21:03 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 20 | 39 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2565.05 | 182.85
2030-07-16 21:03 | 2030-07-16 22:48 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 39 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2566.8 | 181.1
2030-07-16 22:48 | 2030-07-17 00:18 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 20 | 39 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2568.3 | 179.6
2030-07-17 00:18 | 2030-07-17 01:18 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 20 | 39 | 40 |  | Standalone |  | 1 | 1 | 2569.3 | 178.6
2030-07-17 01:18 | 2030-07-17 02:18 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 20 | 39 | 41 |  | Standalone |  | 1 | 1 | 2570.3 | 177.6
2030-07-17 02:18 | 2030-07-17 05:18 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 20 | 39 | 42 |  | Standalone |  | 1 | 3 | 2573.3 | 174.6
2030-07-17 05:18 | 2030-07-17 08:18 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 20 | 39 | 43 |  | Standalone |  | 1 | 3 | 2576.3 | 171.6
2030-07-17 08:18 | 2030-07-17 10:18 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 20 | 39 | 44 |  | Standalone |  | 1 | 3 | 2578.3 | 169.6
2030-07-17 10:18 | 2030-07-17 11:18 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 20 | 40 | 21 |  | Standalone |  | 1 | 1.5 | 2579.3 | 168.6
2030-07-17 11:18 | 2030-07-17 12:18 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 20 | 40 | 22 |  | Standalone |  | 1 | 1.5 | 2580.3 | 167.6
2030-07-17 12:18 | 2030-07-17 16:18 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 20 | 40 | 23 |  | Standalone |  | 1 | 6 | 2584.3 | 163.6
2030-07-17 16:18 | 2030-07-17 19:18 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 20 | 40 | 24 |  | Standalone |  | 1 | 3 | 2587.3 | 160.6
2030-07-17 19:18 | 2030-07-17 20:18 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 20 | 40 | 25 |  | Standalone |  | 1 | 1 | 2588.3 | 159.6
2030-07-17 20:18 | 2030-07-17 22:18 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 20 | 40 | 26 |  | Standalone |  | 1 | 2 | 2590.3 | 157.6
2030-07-17 22:18 | 2030-07-17 23:18 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 20 | 40 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2591.3 | 156.6
2030-07-17 23:18 | 2030-07-18 02:48 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 40 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2594.8 | 153.1
2030-07-18 02:48 | 2030-07-18 03:18 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 20 | 40 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2595.3 | 152.6
2030-07-18 03:18 | 2030-07-18 03:48 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 20 | 40 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2595.8 | 152.1
2030-07-18 03:48 | 2030-07-18 06:03 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 40 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2598.05 | 149.85
2030-07-18 06:03 | 2030-07-18 06:33 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 20 | 40 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2598.55 | 149.35
2030-07-18 06:33 | 2030-07-18 07:03 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 20 | 40 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2599.05 | 148.85
2030-07-18 07:03 | 2030-07-18 08:48 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 40 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2600.8 | 147.1
2030-07-18 08:48 | 2030-07-18 10:18 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 20 | 40 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2602.3 | 145.6
2030-07-18 10:18 | 2030-07-18 12:03 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 40 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2604.05 | 143.85
2030-07-18 12:03 | 2030-07-18 13:33 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 20 | 40 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2605.55 | 142.35
2030-07-18 13:33 | 2030-07-18 15:18 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 20 | 40 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2607.3 | 140.6
2030-07-18 15:18 | 2030-07-18 16:48 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 20 | 40 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2608.8 | 139.1
2030-07-18 16:48 | 2030-07-18 17:48 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 20 | 40 | 40 |  | Standalone |  | 1 | 1 | 2609.8 | 138.1
2030-07-18 17:48 | 2030-07-18 18:48 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 20 | 40 | 41 |  | Standalone |  | 1 | 1 | 2610.8 | 137.1
2030-07-18 18:48 | 2030-07-18 21:48 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 20 | 40 | 42 |  | Standalone |  | 1 | 3 | 2613.8 | 134.1
2030-07-18 21:48 | 2030-07-19 00:48 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 20 | 40 | 43 |  | Standalone |  | 1 | 3 | 2616.8 | 131.1
2030-07-19 00:48 | 2030-07-19 02:48 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 20 | 40 | 44 |  | Standalone |  | 1 | 3 | 2618.8 | 129.1
2030-07-19 02:48 | 2030-07-19 08:00 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 20 |  | 45 |  | Standalone |  | 1 | 7.8 | 2624 | 123.9
2030-07-19 08:00 | 2030-07-19 09:00 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 21 |  | 1 |  | Standalone |  | 1 | 1.5 | 2625 | 122.9
2030-07-19 09:00 | 2030-07-19 11:00 | 2 | Preload and jacking up at port | OFFSHORE | Working |  |  |  | 21 |  | 2 |  | Standalone |  | 1 | 3 | 2627 | 120.9
2030-07-19 11:00 | 2030-07-19 14:00 | 3 | Release crane, gangway etc and prep for lifting | OFFSHORE | Working |  |  |  | 21 |  | 3 |  | Standalone |  | 1 | 3 | 2630 | 117.9
2030-07-19 14:00 | 2030-07-19 15:00 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 21 |  | 4 |  | Standalone |  | 1 | 1 | 2631 | 116.9
2030-07-19 15:00 | 2030-07-19 17:15 | 2.25 | Loadout Nacelle #1 | OFFSHORE | Working |  |  |  | 21 |  | 5 |  | Standalone |  | 1 | 3.375 | 2633.25 | 114.65
2030-07-19 17:15 | 2030-07-19 19:30 | 2.25 | Loadout Tower #1 | OFFSHORE | Working |  |  |  | 21 |  | 6 |  | Standalone |  | 1 | 3.375 | 2635.5 | 112.4
2030-07-19 19:30 | 2030-07-19 21:00 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 21 |  | 7 |  | Standalone |  | 1 | 2.25 | 2637 | 110.9
2030-07-19 21:00 | 2030-07-19 22:30 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 21 |  | 8 |  | Standalone |  | 1 | 2.25 | 2638.5 | 109.4
2030-07-19 22:30 | 2030-07-20 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 21 |  | 9 |  | Standalone |  | 1 | 2.25 | 2640 | 107.9
2030-07-20 | 2030-07-20 01:00 | 1 | Load in/out WTG supplier equipment | OFFSHORE | Working |  |  |  | 21 |  | 10 |  | Standalone |  | 1 | 1 | 2641 | 106.9
2030-07-20 01:00 | 2030-07-20 03:15 | 2.25 | Loadout Nacelle #2 | OFFSHORE | Working |  |  |  | 21 |  | 11 |  | Standalone |  | 1 | 3.375 | 2643.25 | 104.65
2030-07-20 03:15 | 2030-07-20 05:30 | 2.25 | Loadout Tower #2 | OFFSHORE | Working |  |  |  | 21 |  | 12 |  | Standalone |  | 1 | 3.375 | 2645.5 | 102.4
2030-07-20 05:30 | 2030-07-20 07:00 | 1.5 | Loadout Blade 1 | OFFSHORE | Working |  |  |  | 21 |  | 13 |  | Standalone |  | 1 | 2.25 | 2647 | 100.9
2030-07-20 07:00 | 2030-07-20 08:30 | 1.5 | Loadout Blade 2 | OFFSHORE | Working |  |  |  | 21 |  | 14 |  | Standalone |  | 1 | 2.25 | 2648.5 | 99.4
2030-07-20 08:30 | 2030-07-20 10:00 | 1.5 | Loadout Blade 3 | OFFSHORE | Working |  |  |  | 21 |  | 15 |  | Standalone |  | 1 | 2.25 | 2650 | 97.9
2030-07-20 10:00 | 2030-07-20 13:00 | 3 | Secure of crane, gangway (at port)) | OFFSHORE | Working |  |  |  | 21 |  | 16 |  | Standalone |  | 1 | 3 | 2653 | 94.9
2030-07-20 13:00 | 2030-07-20 15:00 | 2 | Jacking down at port | OFFSHORE | Working |  |  |  | 21 |  | 17 |  | Standalone |  | 1 | 3 | 2655 | 92.9
2030-07-20 15:00 | 2030-07-20 16:00 | 1 | Port maneuvering | OFFSHORE | Working |  |  |  | 21 |  | 18 |  | Standalone |  | 1 | 1.5 | 2656 | 91.9
2030-07-20 16:00 | 2030-07-20 21:12 | 5.2 | Transit from port to site | OFFSHORE | Working |  |  |  | 21 |  | 19 |  | Standalone |  | 1 | 7.8 | 2661.2 | 86.7
2030-07-20 21:12 | 2030-07-20 21:42 | 0.5 | DP field check | OFFSHORE | Working |  |  |  | 21 |  | 20 |  | Standalone |  | 1 | 0.75 | 2661.7 | 86.2
2030-07-20 21:42 | 2030-07-20 22:42 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 21 | 41 | 21 |  | Standalone |  | 1 | 1.5 | 2662.7 | 85.2
2030-07-20 22:42 | 2030-07-20 23:42 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 21 | 41 | 22 |  | Standalone |  | 1 | 1.5 | 2663.7 | 84.2
2030-07-20 23:42 | 2030-07-21 03:42 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 21 | 41 | 23 |  | Standalone |  | 1 | 6 | 2667.7 | 80.2
2030-07-21 03:42 | 2030-07-21 06:42 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 21 | 41 | 24 |  | Standalone |  | 1 | 3 | 2670.7 | 77.2
2030-07-21 06:42 | 2030-07-21 07:42 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 21 | 41 | 25 |  | Standalone |  | 1 | 1 | 2671.7 | 76.2
2030-07-21 07:42 | 2030-07-21 09:42 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 21 | 41 | 26 |  | Standalone |  | 1 | 2 | 2673.7 | 74.2
2030-07-21 09:42 | 2030-07-21 10:42 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 21 | 41 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2674.7 | 73.2
2030-07-21 10:42 | 2030-07-21 14:12 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 41 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2678.2 | 69.7
2030-07-21 14:12 | 2030-07-21 14:42 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 21 | 41 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2678.7 | 69.2
2030-07-21 14:42 | 2030-07-21 15:12 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 21 | 41 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2679.2 | 68.7
2030-07-21 15:12 | 2030-07-21 17:27 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 41 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2681.45 | 66.45
2030-07-21 17:27 | 2030-07-21 17:57 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 21 | 41 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2681.95 | 65.95
2030-07-21 17:57 | 2030-07-21 18:27 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 21 | 41 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2682.45 | 65.45
2030-07-21 18:27 | 2030-07-21 20:12 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 41 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2684.2 | 63.7
2030-07-21 20:12 | 2030-07-21 21:42 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 21 | 41 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2685.7 | 62.2
2030-07-21 21:42 | 2030-07-21 23:27 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 41 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2687.45 | 60.45
2030-07-21 23:27 | 2030-07-22 00:57 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 21 | 41 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2688.95 | 58.95
2030-07-22 00:57 | 2030-07-22 02:42 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 41 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2690.7 | 57.2
2030-07-22 02:42 | 2030-07-22 04:12 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 21 | 41 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2692.2 | 55.7
2030-07-22 04:12 | 2030-07-22 05:12 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 21 | 41 | 40 |  | Standalone |  | 1 | 1 | 2693.2 | 54.7
2030-07-22 05:12 | 2030-07-22 06:12 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 21 | 41 | 41 |  | Standalone |  | 1 | 1 | 2694.2 | 53.7
2030-07-22 06:12 | 2030-07-22 09:12 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 21 | 41 | 42 |  | Standalone |  | 1 | 3 | 2697.2 | 50.7
2030-07-22 09:12 | 2030-07-22 12:12 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 21 | 41 | 43 |  | Standalone |  | 1 | 3 | 2700.2 | 47.7
2030-07-22 12:12 | 2030-07-22 14:12 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 21 | 41 | 44 |  | Standalone |  | 1 | 3 | 2702.2 | 45.7
2030-07-22 14:12 | 2030-07-22 15:12 | 1 | Transit to next foundation | OFFSHORE | Working |  |  |  | 21 | 42 | 21 |  | Standalone |  | 1 | 1.5 | 2703.2 | 44.7
2030-07-22 15:12 | 2030-07-22 16:12 | 1 | Positioning at WTG location | OFFSHORE | Working |  |  |  | 21 | 42 | 22 |  | Standalone |  | 1 | 1.5 | 2704.2 | 43.7
2030-07-22 16:12 | 2030-07-22 20:12 | 4 | Preload and jacking up at site | OFFSHORE | Working |  |  |  | 21 | 42 | 23 |  | Standalone |  | 1 | 6 | 2708.2 | 39.7
2030-07-22 20:12 | 2030-07-22 23:12 | 3 | Release crane, gangway and prep for lifting | OFFSHORE | Working |  |  |  | 21 | 42 | 24 |  | Standalone |  | 1 | 3 | 2711.2 | 36.7
2030-07-22 23:12 | 2030-07-23 00:12 | 1 | Remove TP cover and Preparation of TP | OFFSHORE | Working |  |  |  | 21 | 42 | 25 |  | Standalone |  | 1 | 1 | 2712.2 | 35.7
2030-07-23 00:12 | 2030-07-23 02:12 | 2 | Tower preparation, removal of seafastening bolts | OFFSHORE | Working |  |  |  | 21 | 42 | 26 |  | Standalone |  | 1 | 2 | 2714.2 | 33.7
2030-07-23 02:12 | 2030-07-23 03:12 | 1 | Tower rigging-up (attached lifting equipment) | OFFSHORE | Working |  |  |  | 21 | 42 | 27 | G1 | Start | MOST_STRINGENT | 1 | 1.5 | 2715.2 | 32.7
2030-07-23 03:12 | 2030-07-23 06:42 | 3.5 | Tower Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 42 | 28 | G1 | Continue | MOST_STRINGENT | 1 | 5.25 | 2718.7 | 29.2
2030-07-23 06:42 | 2030-07-23 07:12 | 0.5 | Tower derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 21 | 42 | 29 | G1 | End | MOST_STRINGENT | 1 | 0.75 | 2719.2 | 28.7
2030-07-23 07:12 | 2030-07-23 07:42 | 0.5 | Nacelle preparation and rigging | OFFSHORE | Working |  |  |  | 21 | 42 | 30 | G2 | Start | MOST_STRINGENT | 1 | 0.75 | 2719.7 | 28.2
2030-07-23 07:42 | 2030-07-23 09:57 | 2.25 | Nacelle Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 42 | 31 | G2 | Continue | MOST_STRINGENT | 1 | 3.375 | 2721.95 | 25.95
2030-07-23 09:57 | 2030-07-23 10:27 | 0.5 | Nacelle derigging (remove lifting equipment) | OFFSHORE | Working |  |  |  | 21 | 42 | 32 | G2 | End | MOST_STRINGENT | 1 | 0.75 | 2722.45 | 25.45
2030-07-23 10:27 | 2030-07-23 10:57 | 0.5 | Blade yoke rigging and attachement to Blade #1 | OFFSHORE | Working |  |  |  | 21 | 42 | 33 | G3 | Start | MOST_STRINGENT | 1 | 0.75 | 2722.95 | 24.95
2030-07-23 10:57 | 2030-07-23 12:42 | 1.75 | Blade #1 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 42 | 34 | G3 | Continue | MOST_STRINGENT | 1 | 2.625 | 2724.7 | 23.2
2030-07-23 12:42 | 2030-07-23 14:12 | 1.5 | Blade #1 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 21 | 42 | 35 | G3 | End | MOST_STRINGENT | 1 | 2.25 | 2726.2 | 21.7
2030-07-23 14:12 | 2030-07-23 15:57 | 1.75 | Blade #2 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 42 | 36 | G4 | Start | MOST_STRINGENT | 1 | 2.625 | 2727.95 | 19.95
2030-07-23 15:57 | 2030-07-23 17:27 | 1.5 | Balde #2 completion work, re-locate blade yoke to next blade | OFFSHORE | Working |  |  |  | 21 | 42 | 37 | G4 | End | MOST_STRINGENT | 1 | 2.25 | 2729.45 | 18.45
2030-07-23 17:27 | 2030-07-23 19:12 | 1.75 | Blade #3 Lifting (safe-to-safe) | OFFSHORE | Working |  |  |  | 21 | 42 | 38 | G5 | Start | MOST_STRINGENT | 1 | 2.625 | 2731.2 | 16.7
2030-07-23 19:12 | 2030-07-23 20:42 | 1.5 | Blade #3 completion work, blade yoke de-rigging | OFFSHORE | Working |  |  |  | 21 | 42 | 39 | G5 | End | MOST_STRINGENT | 1 | 2.25 | 2732.7 | 15.2
2030-07-23 20:42 | 2030-07-23 21:42 | 1 | Handling HSBM and lifting tools | OFFSHORE | Working |  |  |  | 21 | 42 | 40 |  | Standalone |  | 1 | 1 | 2733.7 | 14.2
2030-07-23 21:42 | 2030-07-23 22:42 | 1 | Lifting HSBM and lifting tools from Nacelle | OFFSHORE | Working |  |  |  | 21 | 42 | 41 |  | Standalone |  | 1 | 1 | 2734.7 | 13.2
2030-07-23 22:42 | 2030-07-24 01:42 | 3 | Turbine general completion works | OFFSHORE | Working |  |  |  | 21 | 42 | 42 |  | Standalone |  | 1 | 3 | 2737.7 | 10.2
2030-07-24 01:42 | 2030-07-24 04:42 | 3 | Secure of crane, gangway etc. Preparation for jacking down and sailing | OFFSHORE | Working |  |  |  | 21 | 42 | 43 |  | Standalone |  | 1 | 3 | 2740.7 | 7.2
2030-07-24 04:42 | 2030-07-24 06:42 | 2 | Jacking down at site | OFFSHORE | Working |  |  |  | 21 | 42 | 44 |  | Standalone |  | 1 | 3 | 2742.7 | 5.2
2030-07-24 06:42 | 2030-07-24 11:54 | 5.2 | Transit from site to port | OFFSHORE | Working |  |  |  | 21 |  | 45 |  | Standalone |  | 1 | 7.8 | 2747.9 | 1.3642e-12

## OUT_overall
OUT_overall
Overall campaign duration and position-completion profiles across the hindcast simulations.
Campaign duration summary
Scenario | Hindcast year | Duration [days] | Duration [hours] | Nominal start | Nominal finish
P0 (no weather) |  | 114.4958 | 2747.9 | 2030-04-01 | 2030-07-24 11:54
Best hindcast year | 2016 | 154.9479 | 3718.75 | 2016-04-01 | 2016-09-02 22:45
P50 |  | 169.1979 | 4060.75 | 2030-04-01 | 2030-09-17 04:45
P75 |  | 179.0312 | 4296.75 | 2030-04-01 | 2030-09-27 00:45
P90 |  | 190.8635 | 4580.725 | 2030-04-01 | 2030-10-08 20:44
Worst hindcast year | 2015 | 208.6042 | 5006.5 | 2015-04-01 | 2015-10-26 14:30
Position completion profile
Position | P0 [days] | Best [days] | P50 [days] | P75 [days] | P90 [days] | Worst [days]
1 | 4.2271 | 4.2708 | 7.724 | 10.3594 | 12.8354 | 15.6667
2 | 6.4667 | 6.5312 | 11.6302 | 16.5547 | 17.8604 | 26.1042
3 | 10.9104 | 13.4375 | 19.0156 | 23.4661 | 25.3542 | 30.5938
4 | 13.15 | 16.3021 | 22.9896 | 26.5156 | 28.7333 | 33.5104
5 | 17.5938 | 21.1771 | 29.401 | 32.651 | 36.6698 | 40.6979
6 | 19.8333 | 24.8021 | 32.6927 | 35.2708 | 39.1688 | 51.5625
7 | 24.2771 | 29.6562 | 39.1615 | 41.7135 | 46.5094 | 56.1979
8 | 26.5167 | 32.1354 | 41.625 | 44.8568 | 49.8698 | 58.4583
9 | 29.9917 | 35.9479 | 46.9948 | 50.0677 | 55.9531 | 61.9375
10 | 31.6792 | 37.6354 | 49.0938 | 52.3307 | 57.6406 | 63.8854
11 | 35.1542 | 41.1146 | 53.2552 | 56.3516 | 62.1573 | 69.2812
12 | 36.8417 | 43.0208 | 55.7552 | 60.3854 | 64.3792 | 72.75
13 | 40.3167 | 46.5 | 60.8542 | 65.5078 | 68.5573 | 77.3125
14 | 42.0042 | 48.1875 | 63.2292 | 67.7083 | 70.326 | 79
15 | 45.4792 | 51.7604 | 68.6771 | 73.3359 | 75.8062 | 82.8438
16 | 47.1667 | 53.6667 | 71.3854 | 75.5859 | 78.5167 | 84.5312
17 | 50.6417 | 62.9688 | 75.6615 | 81.2865 | 82.9729 | 88.1146
18 | 52.3292 | 64.8542 | 78.9479 | 84.7135 | 86.7479 | 89.8021
19 | 55.8042 | 71.2604 | 83.9583 | 89.5286 | 92.8 | 96.7604
20 | 57.4917 | 73.7292 | 87.0729 | 91.5365 | 94.9396 | 98.4479
21 | 60.9667 | 81.5 | 90.7188 | 95.2812 | 98.9719 | 103.4062
22 | 62.6542 | 83.1875 | 93.4062 | 97.388 | 100.6594 | 105.2083
23 | 66.1292 | 87.8333 | 98.4688 | 103.5833 | 106.2177 | 112.6667
24 | 67.8167 | 89.8854 | 101.5625 | 105.2708 | 109.6719 | 115.3125
25 | 71.2917 | 93.625 | 106.2135 | 109.7396 | 113.8438 | 120.7708
26 | 72.9792 | 95.3125 | 108.9635 | 112.2839 | 115.7531 | 122.4583
27 | 76.4542 | 100.6875 | 113.4219 | 118.5208 | 121.0656 | 125.9375
28 | 78.1417 | 102.6042 | 116.8021 | 121.0208 | 124.401 | 127.625
29 | 81.6167 | 106.9792 | 121.901 | 125.2135 | 130.649 | 138.3958
30 | 83.3042 | 108.6667 | 123.8385 | 129.401 | 134.1781 | 140.0833
31 | 86.7792 | 115.7917 | 128.9115 | 134.9375 | 138.4563 | 148.9167
32 | 88.4667 | 117.5417 | 131.6302 | 137.3958 | 140.2188 | 152.0104
33 | 91.9417 | 121.6667 | 135.5312 | 142.0312 | 144.1083 | 155.4896
34 | 93.6292 | 124.2708 | 137.9531 | 144.9922 | 148.0979 | 157.1771
35 | 97.1042 | 127.75 | 144.3698 | 149.2656 | 152.2271 | 167.9688
36 | 98.7917 | 129.4375 | 146.5625 | 151.0182 | 154.0146 | 170.4688
37 | 102.2667 | 134.9375 | 151.6198 | 155.9922 | 158.8906 | 174.3542
38 | 103.9542 | 137.6771 | 154.4427 | 158.5625 | 163.4719 | 176.0417
39 | 107.4292 | 142.9167 | 159.0104 | 163.5859 | 172.6573 | 184.3542
40 | 109.1167 | 146.4167 | 161.25 | 165.5026 | 175.2302 | 186.3125
41 | 112.5917 | 150.375 | 166.7188 | 175.375 | 186.3385 | 202.9792
42 | 114.2792 | 154.7292 | 168.9792 | 178.8125 | 190.6448 | 208.3854

## OUT_overall MS
OUT_overall MS
Milestone completion dates by position and hindcast year. Blank cells indicate incomplete positions.
Position | 1979 | 1980 | 1981 | 1982 | 1983 | 1984 | 1985 | 1986 | 1987 | 1988 | 1989 | 1990 | 1991 | 1992 | 1993 | 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
1 | 1979-04-13 01:30 | 1980-04-08 13:30 | 1981-04-06 10:45 | 1982-04-12 13:15 | 1983-04-06 17:15 | 1984-04-08 23:30 | 1985-04-09 17:15 | 1986-04-09 05:00 | 1987-04-07 23:30 | 1988-04-12 01:30 | 1989-04-14 00:15 | 1990-04-07 07:45 | 1991-04-10 08:00 | 1992-04-06 17:00 | 1993-04-15 23:00 | 1994-04-05 20:45 | 1995-04-08 21:15 | 1996-04-16 16:00 | 1997-04-05 06:30 | 1998-04-07 08:45 | 1999-04-10 14:15 | 2000-04-09 21:15 | 2001-04-07 19:15 | 2002-04-05 06:30 | 2003-04-09 19:00 | 2004-04-07 04:45 | 2005-04-07 18:15 | 2006-04-06 11:00 | 2007-04-15 09:45 | 2008-04-07 05:00 | 2009-04-13 10:15 | 2010-04-11 03:00 | 2011-04-08 10:15 | 2012-04-09 01:30 | 2013-04-09 01:15 | 2014-04-08 11:15 | 2015-04-06 10:00 | 2016-04-05 06:30 | 2017-04-07 11:15 | 2018-04-08 03:15 | 2019-04-07 14:15 | 2020-04-16 12:00 | 2021-04-13 07:00 | 2022-04-12 14:45 | 2023-04-10 06:30
2 | 1979-04-18 21:15 | 1980-04-13 04:00 | 1981-04-09 22:00 | 1982-04-17 13:30 | 1983-04-08 23:30 | 1984-04-15 18:00 | 1985-04-18 12:30 | 1986-04-12 16:00 | 1987-04-10 05:45 | 1988-04-17 13:15 | 1989-04-17 17:15 | 1990-04-10 14:15 | 1991-04-12 14:15 | 1992-04-10 09:00 | 1993-04-18 19:15 | 1994-04-08 03:00 | 1995-04-12 13:00 | 1996-04-22 17:00 | 1997-04-08 04:45 | 1998-04-09 15:00 | 1999-04-15 01:00 | 2000-04-13 17:15 | 2001-04-13 17:30 | 2002-04-07 19:15 | 2003-04-12 01:15 | 2004-04-11 11:15 | 2005-04-10 09:30 | 2006-04-09 12:15 | 2007-04-17 16:00 | 2008-04-11 09:30 | 2009-04-16 06:00 | 2010-04-19 07:00 | 2011-04-12 18:30 | 2012-04-11 07:45 | 2013-04-14 20:15 | 2014-04-12 04:45 | 2015-04-15 12:45 | 2016-04-07 12:45 | 2017-04-09 17:30 | 2018-04-10 09:30 | 2019-04-10 04:30 | 2020-04-18 18:15 | 2021-04-27 02:30 | 2022-04-21 12:15 | 2023-04-13 11:45
3 | 1979-04-25 10:00 | 1980-04-20 12:00 | 1981-04-16 03:45 | 1982-04-24 13:15 | 1983-04-15 05:15 | 1984-04-24 15:00 | 1985-04-23 09:30 | 1986-04-18 22:15 | 1987-04-21 13:45 | 1988-04-25 10:15 | 1989-04-22 19:00 | 1990-04-18 05:00 | 1991-04-18 02:30 | 1992-04-19 15:00 | 1993-04-23 07:00 | 1994-04-17 10:30 | 1995-04-17 01:45 | 1996-04-27 13:00 | 1997-04-16 16:00 | 1998-04-14 11:00 | 1999-04-21 08:30 | 2000-04-19 23:45 | 2001-04-20 01:00 | 2002-04-16 19:30 | 2003-04-17 10:15 | 2004-04-17 23:45 | 2005-04-17 20:30 | 2006-04-21 09:30 | 2007-04-24 10:30 | 2008-04-20 08:30 | 2009-04-24 14:30 | 2010-04-26 08:30 | 2011-04-17 22:30 | 2012-04-15 19:30 | 2013-04-20 12:00 | 2014-04-18 18:45 | 2015-04-27 07:30 | 2016-04-14 10:30 | 2017-04-17 06:30 | 2018-04-17 22:00 | 2019-04-18 02:30 | 2020-04-30 15:15 | 2021-05-01 14:15 | 2022-04-26 08:30 | 2023-04-17 23:30
4 | 1979-04-28 17:15 | 1980-04-27 11:00 | 1981-04-18 18:15 | 1982-04-27 04:00 | 1983-04-19 14:15 | 1984-04-27 20:30 | 1985-04-26 01:45 | 1986-04-24 03:30 | 1987-04-23 20:00 | 1988-04-27 16:30 | 1989-04-26 22:00 | 1990-04-20 11:15 | 1991-04-25 06:30 | 1992-04-22 23:30 | 1993-04-26 22:15 | 1994-04-19 16:45 | 1995-04-20 08:00 | 1996-04-29 19:15 | 1997-04-19 18:00 | 1998-04-17 12:15 | 1999-04-24 18:00 | 2000-04-22 14:30 | 2001-04-24 05:00 | 2002-04-21 06:15 | 2003-04-19 16:30 | 2004-04-20 10:15 | 2005-04-20 02:45 | 2006-04-23 15:45 | 2007-04-30 10:30 | 2008-04-26 03:30 | 2009-04-30 17:15 | 2010-04-28 14:45 | 2011-04-22 09:15 | 2012-04-19 07:15 | 2013-04-24 13:15 | 2014-04-22 09:00 | 2015-04-29 13:45 | 2016-04-17 07:15 | 2017-04-19 12:45 | 2018-04-20 12:15 | 2019-04-20 08:45 | 2020-05-02 21:30 | 2021-05-04 12:15 | 2022-04-29 03:15 | 2023-04-21 19:00
5 | 1979-05-07 19:00 | 1980-05-03 06:45 | 1981-04-26 03:00 | 1982-05-03 14:30 | 1983-04-24 17:15 | 1984-05-09 04:45 | 1985-05-02 08:30 | 1986-04-28 18:00 | 1987-04-30 10:15 | 1988-05-02 08:30 | 1989-05-01 09:45 | 1990-04-28 21:15 | 1991-05-03 19:00 | 1992-04-27 11:15 | 1993-05-01 23:45 | 1994-04-24 04:30 | 1995-04-27 15:30 | 1996-05-04 07:15 | 1997-04-28 17:15 | 1998-04-22 04:15 | 1999-05-06 00:15 | 2000-04-29 17:45 | 2001-04-30 18:30 | 2002-04-29 19:00 | 2003-04-28 18:30 | 2004-04-26 13:45 | 2005-04-25 08:30 | 2006-04-28 19:15 | 2007-05-04 23:00 | 2008-05-01 23:15 | 2009-05-09 14:15 | 2010-05-03 12:00 | 2011-04-28 04:00 | 2012-04-24 10:45 | 2013-04-30 09:00 | 2014-05-01 10:15 | 2015-05-04 04:15 | 2016-04-23 13:00 | 2017-04-26 04:00 | 2018-04-27 07:00 | 2019-04-24 22:00 | 2020-05-07 09:15 | 2021-05-09 22:00 | 2022-05-11 16:45 | 2023-04-29 11:15
6 | 1979-05-10 08:15 | 1980-05-05 13:00 | 1981-04-28 09:15 | 1982-05-05 20:45 | 1983-04-27 01:00 | 1984-05-11 11:00 | 1985-05-04 14:45 | 1986-05-02 00:45 | 1987-05-05 20:15 | 1988-05-04 14:45 | 1989-05-03 16:00 | 1990-05-01 03:30 | 1991-05-06 01:15 | 1992-04-30 15:30 | 1993-05-05 16:45 | 1994-04-26 10:45 | 1995-04-29 21:45 | 1996-05-07 05:45 | 1997-04-30 23:30 | 1998-04-26 02:00 | 1999-05-08 06:30 | 2000-05-02 | 2001-05-03 17:15 | 2002-05-02 21:15 | 2003-05-02 17:15 | 2004-04-30 00:45 | 2005-04-28 09:15 | 2006-05-01 01:30 | 2007-05-07 05:15 | 2008-05-04 05:30 | 2009-05-11 22:00 | 2010-05-05 18:15 | 2011-04-30 10:15 | 2012-04-28 07:45 | 2013-05-07 09:15 | 2014-05-04 17:30 | 2015-05-06 22:15 | 2016-04-25 19:15 | 2017-04-30 21:15 | 2018-04-29 13:15 | 2019-04-28 22:30 | 2020-05-09 18:15 | 2021-05-12 15:30 | 2022-05-22 13:30 | 2023-05-03 16:15
7 | 1979-05-21 19:15 | 1980-05-12 22:15 | 1981-05-04 23:00 | 1982-05-10 08:30 | 1983-05-04 23:15 | 1984-05-15 22:45 | 1985-05-10 05:15 | 1986-05-08 18:30 | 1987-05-12 17:00 | 1988-05-10 11:00 | 1989-05-10 03:00 | 1990-05-06 18:45 | 1991-05-12 00:15 | 1992-05-05 23:45 | 1993-05-10 04:45 | 1994-04-30 22:30 | 1995-05-08 01:30 | 1996-05-19 20:15 | 1997-05-05 11:15 | 1998-04-30 15:45 | 1999-05-14 17:15 | 2000-05-09 18:15 | 2001-05-08 14:30 | 2002-05-07 09:00 | 2003-05-09 22:00 | 2004-05-05 04:00 | 2005-05-08 06:30 | 2006-05-08 03:15 | 2007-05-12 13:15 | 2008-05-17 07:30 | 2009-05-17 14:15 | 2010-05-10 06:00 | 2011-05-06 11:15 | 2012-05-07 03:30 | 2013-05-12 07:45 | 2014-05-10 18:15 | 2015-05-12 01:15 | 2016-05-01 15:15 | 2017-05-05 15:00 | 2018-05-05 11:15 | 2019-05-12 17:30 | 2020-05-15 11:15 | 2021-05-18 00:30 | 2022-05-27 04:45 | 2023-05-12 22:15
8 | 1979-05-26 01:45 | 1980-05-15 04:30 | 1981-05-07 10:15 | 1982-05-12 14:45 | 1983-05-07 10:15 | 1984-05-23 15:00 | 1985-05-12 11:30 | 1986-05-11 00:45 | 1987-05-16 17:00 | 1988-05-14 17:15 | 1989-05-12 09:15 | 1990-05-09 01:00 | 1991-05-15 17:15 | 1992-05-08 06:00 | 1993-05-12 11:00 | 1994-05-06 01:00 | 1995-05-10 07:45 | 1996-05-24 12:30 | 1997-05-07 17:30 | 1998-05-03 03:15 | 1999-05-16 23:30 | 2000-05-14 07:00 | 2001-05-16 06:30 | 2002-05-09 21:15 | 2003-05-12 15:15 | 2004-05-09 19:30 | 2005-05-11 06:30 | 2006-05-10 09:30 | 2007-05-15 10:15 | 2008-05-20 07:45 | 2009-05-19 20:30 | 2010-05-13 20:15 | 2011-05-08 17:30 | 2012-05-09 17:00 | 2013-05-14 14:00 | 2014-05-13 10:30 | 2015-05-15 03:15 | 2016-05-04 02:15 | 2017-05-09 06:45 | 2018-05-07 17:30 | 2019-05-14 23:45 | 2020-05-17 17:30 | 2021-05-21 02:30 | 2022-05-29 11:00 | 2023-05-15 07:15
9 | 1979-06-01 03:15 | 1980-05-27 23:15 | 1981-05-10 21:45 | 1982-05-18 00:15 | 1983-05-10 21:45 | 1984-05-28 09:45 | 1985-05-15 23:00 | 1986-05-16 11:15 | 1987-05-20 04:45 | 1988-05-18 07:45 | 1989-05-17 09:45 | 1990-05-12 17:30 | 1991-05-19 10:15 | 1992-05-15 05:00 | 1993-05-16 22:30 | 1994-05-09 12:30 | 1995-05-14 13:00 | 1996-05-28 | 1997-05-12 05:30 | 1998-05-06 22:45 | 1999-05-22 21:45 | 2000-05-20 23:30 | 2001-05-20 03:15 | 2002-05-14 04:30 | 2003-05-16 02:45 | 2004-05-14 09:15 | 2005-05-16 10:00 | 2006-05-21 08:00 | 2007-05-18 21:45 | 2008-05-23 22:45 | 2009-05-23 08:00 | 2010-05-17 23:30 | 2011-05-12 20:15 | 2012-05-15 02:30 | 2013-05-20 01:15 | 2014-05-18 06:45 | 2015-05-18 15:45 | 2016-05-08 01:45 | 2017-05-13 00:15 | 2018-05-14 01:30 | 2019-05-19 23:15 | 2020-05-21 10:45 | 2021-05-24 14:00 | 2022-06-01 22:30 | 2023-05-19 11:15
10 | 1979-06-02 19:45 | 1980-05-29 15:45 | 1981-05-14 17:15 | 1982-05-19 16:45 | 1983-05-13 20:30 | 1984-05-30 02:15 | 1985-05-20 06:00 | 1986-05-18 07:30 | 1987-05-21 21:15 | 1988-05-20 06:15 | 1989-05-20 05:15 | 1990-05-14 10:00 | 1991-05-21 02:45 | 1992-05-16 21:30 | 1993-05-18 15:00 | 1994-05-11 06:15 | 1995-05-17 02:15 | 1996-05-29 16:30 | 1997-05-13 22:00 | 1998-05-08 15:15 | 1999-05-24 21:15 | 2000-05-23 07:30 | 2001-05-21 19:45 | 2002-05-16 12:30 | 2003-05-18 11:30 | 2004-05-16 01:45 | 2005-05-18 02:30 | 2006-05-23 00:30 | 2007-05-20 15:30 | 2008-05-25 15:15 | 2009-05-25 13:15 | 2010-05-19 16:00 | 2011-05-15 06:15 | 2012-05-16 19:00 | 2013-05-23 09:15 | 2014-05-19 23:15 | 2015-05-22 11:30 | 2016-05-10 00:15 | 2017-05-14 16:45 | 2018-05-15 18:00 | 2019-05-23 01:30 | 2020-05-25 06:15 | 2021-05-26 06:30 | 2022-06-03 21:15 | 2023-05-21 03:45
11 | 1979-06-06 07:15 | 1980-06-02 03:15 | 1981-05-23 15:30 | 1982-05-25 07:45 | 1983-05-20 00:30 | 1984-06-03 19:30 | 1985-05-26 18:45 | 1986-05-24 09:15 | 1987-05-25 12:15 | 1988-05-26 08:30 | 1989-05-23 19:45 | 1990-05-20 11:15 | 1991-05-26 11:30 | 1992-05-23 02:30 | 1993-05-22 02:30 | 1994-05-15 09:15 | 1995-05-20 21:15 | 1996-06-02 04:00 | 1997-05-18 05:15 | 1998-05-12 02:45 | 1999-05-30 08:45 | 2000-05-28 12:00 | 2001-05-25 07:15 | 2002-05-20 | 2003-05-23 07:45 | 2004-05-21 08:30 | 2005-05-22 22:15 | 2006-05-26 23:15 | 2007-05-24 03:00 | 2008-05-31 15:00 | 2009-06-02 23:30 | 2010-05-24 02:15 | 2011-05-20 | 2012-05-20 10:00 | 2013-05-26 20:45 | 2014-05-23 13:00 | 2015-05-26 06:30 | 2016-05-14 12:30 | 2017-05-22 13:30 | 2018-05-19 08:45 | 2019-05-26 13:00 | 2020-05-29 03:45 | 2021-05-31 00:15 | 2022-06-09 06:45 | 2023-05-26 13:15
12 | 1979-06-08 08:15 | 1980-06-04 14:30 | 1981-05-25 08:00 | 1982-05-27 00:15 | 1983-05-21 17:00 | 1984-06-05 16:00 | 1985-05-31 05:30 | 1986-05-28 09:15 | 1987-05-27 04:45 | 1988-05-31 20:30 | 1989-05-26 04:00 | 1990-05-22 11:15 | 1991-05-28 04:00 | 1992-05-24 19:00 | 1993-05-23 19:00 | 1994-05-17 07:15 | 1995-05-23 17:30 | 1996-06-03 20:30 | 1997-05-19 23:15 | 1998-05-14 00:30 | 1999-06-01 01:15 | 2000-05-30 04:30 | 2001-05-26 23:45 | 2002-05-21 16:30 | 2003-05-25 00:15 | 2004-05-23 01:00 | 2005-05-25 21:00 | 2006-05-28 15:45 | 2007-05-26 12:30 | 2008-06-02 07:30 | 2009-06-07 04:00 | 2010-05-25 21:15 | 2011-05-21 19:30 | 2012-05-24 08:15 | 2013-05-29 03:15 | 2014-05-25 14:30 | 2015-06-01 01:15 | 2016-05-17 18:00 | 2017-05-24 06:00 | 2018-05-24 14:00 | 2019-05-29 17:00 | 2020-05-30 20:15 | 2021-06-01 16:45 | 2022-06-12 18:00 | 2023-05-28 05:45
13 | 1979-06-11 20:15 | 1980-06-08 03:45 | 1981-05-28 20:30 | 1982-05-31 10:30 | 1983-05-26 | 1984-06-09 03:30 | 1985-06-08 05:30 | 1986-05-31 22:45 | 1987-05-31 20:00 | 1988-06-06 18:30 | 1989-05-31 05:15 | 1990-05-30 08:00 | 1991-05-31 21:00 | 1992-05-29 09:30 | 1993-05-27 17:30 | 1994-05-22 19:15 | 1995-05-27 05:00 | 1996-06-08 16:45 | 1997-05-28 07:30 | 1998-05-17 12:00 | 1999-06-07 17:00 | 2000-06-03 00:15 | 2001-06-03 01:15 | 2002-05-27 09:15 | 2003-06-05 18:45 | 2004-05-26 12:30 | 2005-05-31 08:30 | 2006-06-01 07:00 | 2007-05-30 04:30 | 2008-06-06 23:30 | 2009-06-10 21:15 | 2010-05-29 12:30 | 2011-06-01 02:00 | 2012-05-28 03:15 | 2013-06-01 14:45 | 2014-05-29 02:00 | 2015-06-04 12:45 | 2016-05-23 19:30 | 2017-05-31 19:45 | 2018-05-28 08:15 | 2019-06-03 11:30 | 2020-06-03 12:15 | 2021-06-05 10:00 | 2022-06-17 07:30
14 | 1979-06-14 00:30 | 1980-06-09 20:15 | 1981-05-30 13:00 | 1982-06-06 08:15 | 1983-05-27 23:00 | 1984-06-11 03:30 | 1985-06-10 04:30 | 1986-06-03 02:30 | 1987-06-02 12:30 | 1988-06-08 11:00 | 1989-06-01 21:45 | 1990-06-02 20:00 | 1991-06-02 13:30 | 1992-05-31 09:15 | 1993-05-30 20:30 | 1994-05-24 11:45 | 1995-05-28 21:30 | 1996-06-10 09:15 | 1997-05-30 05:15 | 1998-05-19 04:30 | 1999-06-09 12:15 | 2000-06-04 16:45 | 2001-06-06 02:15 | 2002-05-29 01:45 | 2003-06-07 11:15 | 2004-05-28 05:00 | 2005-06-02 01:00 | 2006-06-04 | 2007-05-31 21:00 | 2008-06-08 16:00 | 2009-06-12 13:45 | 2010-06-08 10:15 | 2011-06-02 18:30 | 2012-06-01 19:00 | 2013-06-03 08:30 | 2014-05-30 18:30 | 2015-06-06 05:15 | 2016-05-25 12:00 | 2017-06-03 09:00 | 2018-05-30 05:30 | 2019-06-05 04:00 | 2020-06-05 04:45 | 2021-06-07 03:30 | 2022-06-19
15 | 1979-06-17 12:00 | 1980-06-13 07:45 | 1981-06-09 11:30 | 1982-06-09 19:45 | 1983-06-08 09:15 | 1984-06-17 03:15 | 1985-06-15 07:30 | 1986-06-08 17:00 | 1987-06-06 | 1988-06-15 17:15 | 1989-06-05 09:15 | 1990-06-06 12:45 | 1991-06-06 02:45 | 1992-06-04 09:45 | 1993-06-04 21:15 | 1994-05-28 23:15 | 1995-06-01 09:00 | 1996-06-13 20:45 | 1997-06-03 04:30 | 1998-05-22 18:15 | 1999-06-13 05:30 | 2000-06-13 09:00 | 2001-06-09 13:45 | 2002-06-02 12:00 | 2003-06-14 21:30 | 2004-05-31 16:30 | 2005-06-07 12:15 | 2006-06-15 20:15 | 2007-06-05 15:45 | 2008-06-15 15:30 | 2009-06-16 02:45 | 2010-06-12 03:30 | 2011-06-06 06:00 | 2012-06-09 12:00 | 2013-06-07 03:30 | 2014-06-03 23:30 | 2015-06-09 21:15 | 2016-05-30 08:15 | 2017-06-06 20:30 | 2018-06-04 00:30 | 2019-06-08 15:30 | 2020-06-10 04:30 | 2021-06-11 01:00 | 2022-06-22 20:15
16 | 1979-06-19 13:00 | 1980-06-15 00:15 | 1981-06-16 17:00 | 1982-06-11 12:15 | 1983-06-10 01:45 | 1984-06-18 19:45 | 1985-06-17 11:30 | 1986-06-11 19:00 | 1987-06-07 20:30 | 1988-06-17 14:30 | 1989-06-07 01:45 | 1990-06-09 15:15 | 1991-06-07 19:15 | 1992-06-06 02:15 | 1993-06-07 04:00 | 1994-05-31 02:15 | 1995-06-03 07:30 | 1996-06-15 13:15 | 1997-06-04 21:00 | 1998-05-24 16:00 | 1999-06-15 06:00 | 2000-06-15 16:30 | 2001-06-11 06:15 | 2002-06-04 08:30 | 2003-06-19 01:00 | 2004-06-03 05:15 | 2005-06-09 09:15 | 2006-06-17 16:15 | 2007-06-07 08:15 | 2008-06-19 03:15 | 2009-06-17 19:15 | 2010-06-13 20:00 | 2011-06-08 15:15 | 2012-06-12 19:00 | 2013-06-08 22:15 | 2014-06-05 16:00 | 2015-06-11 19:15 | 2016-06-01 00:45 | 2017-06-08 13:00 | 2018-06-05 21:00 | 2019-06-11 21:15 | 2020-06-11 21:00 | 2021-06-12 18:00 | 2022-06-24 12:45
17 | 1979-06-23 00:30 | 1980-06-18 11:45 | 1981-06-23 00:15 | 1982-06-15 | 1983-06-13 13:15 | 1984-06-22 10:00 | 1985-06-23 12:00 | 1986-06-17 21:15 | 1987-06-14 08:45 | 1988-06-21 23:30 | 1989-06-14 08:30 | 1990-06-13 02:45 | 1991-06-11 06:45 | 1992-06-11 05:15 | 1993-06-11 05:30 | 1994-06-05 07:45 | 1995-06-07 20:30 | 1996-06-19 09:15 | 1997-06-13 01:45 | 1998-06-02 23:15 | 1999-06-19 21:15 | 2000-06-19 04:00 | 2001-06-17 02:00 | 2002-06-09 01:15 | 2003-06-22 18:45 | 2004-06-14 09:15 | 2005-06-13 18:00 | 2006-06-21 03:45 | 2007-06-12 05:00 | 2008-06-22 14:45 | 2009-06-24 12:30 | 2010-06-22 21:15 | 2011-06-13 08:15 | 2012-06-16 23:30 | 2013-06-15 00:15 | 2014-06-16 02:15 | 2015-06-15 16:45 | 2016-06-06 19:45 | 2017-06-12 00:30 | 2018-06-10 04:15 | 2019-06-16 08:15 | 2020-06-15 15:00 | 2021-06-21 16:15 | 2022-06-28 02:45
18 | 1979-06-24 17:00 | 1980-06-20 04:15 | 1981-06-25 02:15 | 1982-06-23 11:30 | 1983-06-16 07:15 | 1984-06-25 13:00 | 1985-06-28 15:30 | 1986-06-19 13:45 | 1987-06-19 09:00 | 1988-06-26 23:30 | 1989-06-19 19:00 | 1990-06-14 19:15 | 1991-06-12 23:15 | 1992-06-12 21:45 | 1993-06-14 21:15 | 1994-06-08 16:00 | 1995-06-10 16:00 | 1996-06-24 17:30 | 1997-06-15 05:30 | 1998-06-04 20:30 | 1999-06-25 22:15 | 2000-06-20 21:15 | 2001-06-18 18:30 | 2002-06-11 09:00 | 2003-06-29 05:15 | 2004-06-16 01:45 | 2005-06-16 03:00 | 2006-06-22 20:15 | 2007-06-16 02:15 | 2008-06-24 19:00 | 2009-06-26 05:00 | 2010-06-27 05:30 | 2011-06-15 00:45 | 2012-06-19 03:00 | 2013-06-17 09:00 | 2014-06-19 19:30 | 2015-06-17 09:15 | 2016-06-08 12:15 | 2017-06-15 20:00 | 2018-06-12 06:15 | 2019-06-18 18:30 | 2020-06-17 07:30 | 2021-06-23 11:15 | 2022-06-29 19:15
19 | 1979-06-29 21:30 | 1980-06-23 15:45 | 1981-06-28 18:15 | 1982-07-03 | 1983-06-23 04:45 | 1984-06-30 06:00 | 1985-07-05 05:30 | 1986-06-23 01:15 | 1987-06-25 11:30 | 1988-07-01 03:15 | 1989-06-25 09:15 | 1990-06-20 15:00 | 1991-06-16 15:45 | 1992-06-16 16:15 | 1993-06-18 18:15 | 1994-06-15 23:30 | 1995-06-19 17:30 | 1996-06-28 14:15 | 1997-06-20 02:45 | 1998-06-11 06:15 | 1999-06-29 09:45 | 2000-06-24 08:45 | 2001-06-22 08:00 | 2002-06-15 12:45 | 2003-07-02 16:45 | 2004-06-19 13:15 | 2005-06-27 14:15 | 2006-06-26 07:45 | 2007-06-20 16:30 | 2008-07-02 06:45 | 2009-07-02 20:15 | 2010-06-30 17:00 | 2011-06-18 12:15 | 2012-06-27 01:30 | 2013-06-21 15:00 | 2014-06-24 18:45 | 2015-06-21 10:45 | 2016-06-17 23:30 | 2017-06-22 18:15 | 2018-06-22 06:00 | 2019-06-24 06:15 | 2020-06-22 13:30 | 2021-07-03 11:45 | 2022-07-06 18:15
20 | 1979-07-01 15:30 | 1980-06-25 08:15 | 1981-06-30 17:15 | 1982-07-05 06:00 | 1983-06-24 21:15 | 1984-07-02 00:30 | 1985-07-06 22:00 | 1986-06-27 23:30 | 1987-06-27 18:00 | 1988-07-02 19:45 | 1989-06-27 10:00 | 1990-06-24 17:00 | 1991-06-18 22:00 | 1992-06-18 12:15 | 1993-06-20 16:15 | 1994-06-19 09:00 | 1995-06-28 09:30 | 1996-06-30 17:30 | 1997-06-21 19:15 | 1998-06-13 17:30 | 1999-07-01 02:15 | 2000-06-26 01:15 | 2001-06-25 07:00 | 2002-06-18 00:30 | 2003-07-04 09:15 | 2004-06-21 19:15 | 2005-06-29 06:45 | 2006-06-28 00:15 | 2007-06-22 09:00 | 2008-07-03 23:15 | 2009-07-05 08:30 | 2010-07-02 09:30 | 2011-06-20 04:45 | 2012-07-01 12:00 | 2013-06-28 23:30 | 2014-06-26 17:30 | 2015-06-23 10:00 | 2016-06-19 16:00 | 2017-06-24 10:45 | 2018-06-24 09:30 | 2019-06-25 22:45 | 2020-06-24 21:15 | 2021-07-05 04:15 | 2022-07-08 10:45
21 | 1979-07-06 00:30 | 1980-06-30 02:00 | 1981-07-05 05:00 | 1982-07-09 02:30 | 1983-06-29 17:30 | 1984-07-05 12:00 | 1985-07-12 02:45 | 1986-07-01 15:45 | 1987-07-01 05:30 | 1988-07-06 07:15 | 1989-07-02 22:45 | 1990-06-28 06:00 | 1991-06-26 21:15 | 1992-06-21 23:45 | 1993-06-24 10:45 | 1994-06-24 00:30 | 1995-07-01 21:00 | 1996-07-04 05:00 | 1997-06-26 08:15 | 1998-06-24 15:30 | 1999-07-04 14:45 | 2000-06-29 12:45 | 2001-06-28 19:00 | 2002-06-21 12:00 | 2003-07-08 06:45 | 2004-06-28 04:00 | 2005-07-03 | 2006-07-01 11:45 | 2007-06-28 20:15 | 2008-07-07 17:00 | 2009-07-08 20:00 | 2010-07-13 09:45 | 2011-06-26 17:00 | 2012-07-04 23:30 | 2013-07-02 11:00 | 2014-06-30 05:00 | 2015-06-28 19:15 | 2016-06-23 03:30 | 2017-06-29 17:45 | 2018-06-27 21:00 | 2019-06-29 22:45 | 2020-06-29 17:30 | 2021-07-09 00:45 | 2022-07-11 22:15
22 | 1979-07-08 20:00 | 1980-07-01 23:30 | 1981-07-08 18:00 | 1982-07-10 19:00 | 1983-07-03 11:15 | 1984-07-07 04:30 | 1985-07-13 21:15 | 1986-07-03 08:15 | 1987-07-02 22:00 | 1988-07-07 23:45 | 1989-07-04 15:15 | 1990-07-03 15:15 | 1991-06-28 13:45 | 1992-06-24 01:30 | 1993-06-26 03:15 | 1994-06-25 20:15 | 1995-07-05 08:15 | 1996-07-05 21:30 | 1997-06-30 09:00 | 1998-06-26 08:30 | 1999-07-06 10:30 | 2000-07-01 05:15 | 2001-07-01 | 2002-06-23 04:30 | 2003-07-09 23:15 | 2004-07-05 16:15 | 2005-07-04 16:30 | 2006-07-03 04:15 | 2007-06-30 12:45 | 2008-07-09 23:15 | 2009-07-10 12:30 | 2010-07-15 05:00 | 2011-06-30 07:30 | 2012-07-06 16:00 | 2013-07-04 03:30 | 2014-07-01 21:30 | 2015-07-02 17:30 | 2016-06-24 20:00 | 2017-07-01 10:15 | 2018-06-29 13:30 | 2019-07-01 18:00 | 2020-07-01 15:15 | 2021-07-10 17:15 | 2022-07-14 12:00
23 | 1979-07-14 03:15 | 1980-07-07 06:30 | 1981-07-12 05:30 | 1982-07-14 06:30 | 1983-07-11 03:45 | 1984-07-12 08:00 | 1985-07-17 08:45 | 1986-07-07 12:45 | 1987-07-06 21:15 | 1988-07-11 14:15 | 1989-07-08 02:45 | 1990-07-07 02:45 | 1991-07-02 22:15 | 1992-07-02 16:30 | 1993-06-30 14:15 | 1994-06-29 07:45 | 1995-07-08 19:45 | 1996-07-09 09:00 | 1997-07-07 17:15 | 1998-06-29 20:00 | 1999-07-14 03:00 | 2000-07-05 07:00 | 2001-07-06 13:00 | 2002-06-27 20:00 | 2003-07-13 10:45 | 2004-07-11 18:15 | 2005-07-09 21:15 | 2006-07-07 08:15 | 2007-07-04 00:15 | 2008-07-13 23:45 | 2009-07-14 02:30 | 2010-07-21 13:00 | 2011-07-03 19:00 | 2012-07-10 19:30 | 2013-07-09 16:15 | 2014-07-05 15:45 | 2015-07-22 16:00 | 2016-06-28 07:30 | 2017-07-04 21:45 | 2018-07-07 21:15 | 2019-07-17 01:15 | 2020-07-05 16:45 | 2021-07-14 04:45 | 2022-07-21 17:30
24 | 1979-07-20 16:15 | 1980-07-08 23:00 | 1981-07-13 22:00 | 1982-07-15 23:00 | 1983-07-12 20:15 | 1984-07-15 02:30 | 1985-07-19 15:15 | 1986-07-09 05:15 | 1987-07-08 13:45 | 1988-07-13 06:45 | 1989-07-09 21:00 | 1990-07-08 19:15 | 1991-07-07 09:15 | 1992-07-09 18:15 | 1993-07-02 07:30 | 1994-07-01 00:15 | 1995-07-11 13:15 | 1996-07-11 01:30 | 1997-07-11 21:15 | 1998-07-01 12:30 | 1999-07-15 19:30 | 2000-07-10 04:00 | 2001-07-10 22:30 | 2002-06-29 21:15 | 2003-07-15 03:15 | 2004-07-13 10:45 | 2005-07-11 13:45 | 2006-07-09 00:45 | 2007-07-05 23:30 | 2008-07-15 16:15 | 2009-07-16 11:00 | 2010-07-25 07:30 | 2011-07-05 11:30 | 2012-07-13 20:15 | 2013-07-11 21:00 | 2014-07-10 20:00 | 2015-07-24 20:15 | 2016-06-30 03:30 | 2017-07-06 14:15 | 2018-07-12 20:30 | 2019-07-19 16:30 | 2020-07-07 21:15 | 2021-07-15 21:15 | 2022-07-23 10:00
25 | 1979-07-24 03:45 | 1980-07-15 08:30 | 1981-07-17 09:30 | 1982-07-19 21:00 | 1983-07-19 20:00 | 1984-07-18 23:45 | 1985-07-23 02:45 | 1986-07-15 18:30 | 1987-07-12 01:15 | 1988-07-16 18:15 | 1989-07-13 09:30 | 1990-07-13 17:30 | 1991-07-11 01:45 | 1992-07-14 18:00 | 1993-07-05 19:00 | 1994-07-04 23:00 | 1995-07-15 05:45 | 1996-07-14 21:15 | 1997-07-16 03:30 | 1998-07-05 | 1999-07-21 11:45 | 2000-07-15 23:00 | 2001-07-15 11:45 | 2002-07-06 22:00 | 2003-07-18 21:15 | 2004-07-16 22:15 | 2005-07-15 05:45 | 2006-07-18 11:30 | 2007-07-09 12:15 | 2008-07-22 09:45 | 2009-07-20 18:00 | 2010-07-30 18:30 | 2011-07-08 23:00 | 2012-07-19 17:00 | 2013-07-17 12:45 | 2014-07-16 06:45 | 2015-07-29 13:15 | 2016-07-03 15:00 | 2017-07-10 04:45 | 2018-07-16 08:00 | 2019-07-25 01:45 | 2020-07-12 23:15 | 2021-07-19 08:45 | 2022-07-26 21:30
26 | 1979-07-25 20:15 | 1980-07-17 01:00 | 1981-07-20 14:15 | 1982-07-21 13:30 | 1983-07-21 12:30 | 1984-07-21 17:15 | 1985-07-24 19:15 | 1986-07-17 23:15 | 1987-07-17 22:00 | 1988-07-18 10:45 | 1989-07-15 02:00 | 1990-07-15 10:00 | 1991-07-15 20:00 | 1992-07-17 00:30 | 1993-07-07 11:30 | 1994-07-07 09:30 | 1995-07-16 22:15 | 1996-07-16 13:45 | 1997-07-18 09:00 | 1998-07-06 16:30 | 1999-07-23 04:15 | 2000-07-19 17:15 | 2001-07-17 12:15 | 2002-07-08 19:00 | 2003-07-22 06:00 | 2004-07-18 14:45 | 2005-07-22 09:15 | 2006-07-20 04:00 | 2007-07-11 04:45 | 2008-07-24 02:15 | 2009-07-22 16:15 | 2010-08-01 11:00 | 2011-07-10 15:30 | 2012-07-21 09:30 | 2013-07-19 07:30 | 2014-07-20 17:00 | 2015-07-31 05:45 | 2016-07-05 07:30 | 2017-07-11 21:15 | 2018-07-19 11:30 | 2019-07-26 18:15 | 2020-07-14 15:45 | 2021-07-25 13:00 | 2022-07-28 14:00
27 | 1979-07-31 06:00 | 1980-07-24 16:00 | 1981-07-27 05:30 | 1982-07-27 07:45 | 1983-07-25 | 1984-07-25 18:30 | 1985-07-28 17:45 | 1986-07-21 16:15 | 1987-07-21 09:30 | 1988-07-25 15:45 | 1989-07-19 19:00 | 1990-07-19 05:45 | 1991-07-20 21:00 | 1992-07-20 12:00 | 1993-07-10 23:00 | 1994-07-14 16:00 | 1995-07-20 09:45 | 1996-07-21 21:30 | 1997-07-22 04:00 | 1998-07-10 16:30 | 1999-07-29 17:30 | 2000-07-23 04:45 | 2001-07-20 23:45 | 2002-07-13 18:30 | 2003-07-28 10:00 | 2004-07-22 02:15 | 2005-07-25 21:00 | 2006-07-23 15:30 | 2007-07-20 12:15 | 2008-07-31 19:15 | 2009-07-28 10:45 | 2010-08-04 22:30 | 2011-07-14 03:00 | 2012-07-29 11:30 | 2013-07-23 04:00 | 2014-07-29 14:30 | 2015-08-03 17:15 | 2016-07-15 14:15 | 2017-07-15 08:45 | 2018-07-24 17:00 | 2019-07-30 07:45 | 2020-07-19 00:45 | 2021-07-30 15:15 | 2022-08-01 09:15
28 | 1979-08-03 13:00 | 1980-07-26 09:00 | 1981-07-28 22:00 | 1982-08-03 15:15 | 1983-07-27 08:30 | 1984-07-27 20:30 | 1985-07-30 18:00 | 1986-07-23 08:45 | 1987-07-24 13:15 | 1988-07-28 09:00 | 1989-07-21 19:30 | 1990-07-21 00:30 | 1991-07-22 13:30 | 1992-07-24 21:00 | 1993-07-13 12:00 | 1994-07-16 08:30 | 1995-07-22 02:15 | 1996-07-27 21:00 | 1997-07-25 08:15 | 1998-07-12 14:30 | 1999-07-31 20:00 | 2000-07-24 21:15 | 2001-07-22 17:00 | 2002-07-15 11:00 | 2003-07-30 06:15 | 2004-07-23 18:45 | 2005-07-27 23:00 | 2006-07-27 05:30 | 2007-07-22 04:45 | 2008-08-03 01:00 | 2009-07-30 03:15 | 2010-08-06 15:00 | 2011-07-17 02:00 | 2012-08-05 07:00 | 2013-07-25 07:30 | 2014-08-01 | 2015-08-05 09:45 | 2016-07-17 14:15 | 2017-07-17 22:00 | 2018-07-28 16:00 | 2019-08-01 19:00 | 2020-07-20 17:15 | 2021-08-02 06:15 | 2022-08-03 01:45
29 | 1979-08-07 04:45 | 1980-07-31 20:15 | 1981-08-01 19:00 | 1982-08-07 02:45 | 1983-07-30 20:00 | 1984-07-31 23:00 | 1985-08-03 17:45 | 1986-07-26 20:15 | 1987-08-02 04:30 | 1988-08-02 06:15 | 1989-07-27 13:15 | 1990-07-25 18:00 | 1991-07-28 07:15 | 1992-07-28 09:00 | 1993-07-16 23:30 | 1994-07-19 20:00 | 1995-07-26 12:00 | 1996-08-03 20:30 | 1997-07-30 22:30 | 1998-07-25 22:15 | 1999-08-10 13:15 | 2000-08-01 08:15 | 2001-07-26 04:45 | 2002-07-22 19:45 | 2003-08-02 17:45 | 2004-07-27 06:15 | 2005-08-02 22:00 | 2006-07-30 17:00 | 2007-07-25 16:15 | 2008-08-07 12:00 | 2009-08-03 07:15 | 2010-08-11 16:30 | 2011-07-23 12:45 | 2012-08-12 21:15 | 2013-07-29 07:00 | 2014-08-07 13:00 | 2015-08-17 09:30 | 2016-07-21 01:45 | 2017-07-22 07:30 | 2018-08-01 11:00 | 2019-08-05 07:00 | 2020-07-24 04:45 | 2021-08-10 15:00 | 2022-08-06 13:15
30 | 1979-08-08 21:15 | 1980-08-02 12:45 | 1981-08-03 19:30 | 1982-08-11 04:00 | 1983-08-01 12:30 | 1984-08-02 15:30 | 1985-08-05 10:15 | 1986-07-28 12:45 | 1987-08-03 21:00 | 1988-08-04 10:30 | 1989-08-04 17:00 | 1990-07-27 12:30 | 1991-08-01 10:30 | 1992-07-30 01:30 | 1993-07-18 16:00 | 1994-07-21 12:30 | 1995-07-28 04:30 | 1996-08-05 21:00 | 1997-08-01 20:00 | 1998-07-27 14:45 | 1999-08-14 19:30 | 2000-08-03 00:45 | 2001-07-28 07:30 | 2002-07-24 16:00 | 2003-08-04 10:15 | 2004-07-29 04:00 | 2005-08-08 00:15 | 2006-08-01 09:30 | 2007-07-27 08:45 | 2008-08-09 23:30 | 2009-08-13 12:15 | 2010-08-13 09:00 | 2011-07-25 05:15 | 2012-08-14 13:45 | 2013-07-30 23:30 | 2014-08-09 17:00 | 2015-08-19 02:00 | 2016-07-22 18:15 | 2017-07-24 | 2018-08-03 12:15 | 2019-08-12 17:15 | 2020-07-25 21:15 | 2021-08-12 14:15 | 2022-08-08 05:45
31 | 1979-08-16 12:00 | 1980-08-07 22:15 | 1981-08-11 16:00 | 1982-08-15 15:15 | 1983-08-05 | 1984-08-06 07:30 | 1985-08-08 21:45 | 1986-08-01 00:15 | 1987-08-09 02:15 | 1988-08-08 15:00 | 1989-08-08 04:30 | 1990-07-31 22:00 | 1991-08-04 22:00 | 1992-08-02 13:00 | 1993-07-25 20:30 | 1994-07-25 19:00 | 1995-08-03 21:15 | 1996-08-11 06:45 | 1997-08-05 15:45 | 1998-07-31 14:15 | 1999-08-18 13:45 | 2000-08-06 12:15 | 2001-08-02 00:30 | 2002-07-30 07:30 | 2003-08-11 05:00 | 2004-08-02 08:00 | 2005-08-14 09:00 | 2006-08-07 21:30 | 2007-07-30 20:15 | 2008-08-13 11:00 | 2009-08-16 23:45 | 2010-08-16 20:30 | 2011-07-28 16:45 | 2012-08-21 02:30 | 2013-08-04 22:00 | 2014-08-16 09:00 | 2015-08-27 22:00 | 2016-07-26 05:45 | 2017-07-28 07:00 | 2018-08-13 19:00 | 2019-08-20 18:15 | 2020-07-29 09:45 | 2021-08-17 15:45 | 2022-08-13 09:00
32 | 1979-08-18 22:15 | 1980-08-10 18:00 | 1981-08-15 05:30 | 1982-08-17 15:30 | 1983-08-06 16:30 | 1984-08-09 03:15 | 1985-08-10 14:15 | 1986-08-05 18:00 | 1987-08-10 18:45 | 1988-08-10 07:30 | 1989-08-09 21:00 | 1990-08-02 21:15 | 1991-08-06 14:30 | 1992-08-04 05:30 | 1993-07-27 13:00 | 1994-07-27 20:30 | 1995-08-05 13:45 | 1996-08-15 23:00 | 1997-08-11 14:15 | 1998-08-02 06:45 | 1999-08-20 06:15 | 2000-08-10 16:00 | 2001-08-04 02:15 | 2002-08-01 11:00 | 2003-08-13 02:15 | 2004-08-04 19:30 | 2005-08-16 01:30 | 2006-08-11 04:30 | 2007-08-01 12:45 | 2008-08-15 03:30 | 2009-08-18 16:15 | 2010-08-18 13:00 | 2011-08-03 01:00 | 2012-08-25 12:00 | 2013-08-06 17:30 | 2014-08-18 01:30 | 2015-08-31 00:15 | 2016-07-27 22:15 | 2017-08-03 19:00 | 2018-08-17 09:30 | 2019-08-22 10:45 | 2020-07-31 02:15 | 2021-08-19 08:15 | 2022-08-15 01:30
33 | 1979-08-22 09:45 | 1980-08-14 05:30 | 1981-08-19 14:00 | 1982-08-21 06:00 | 1983-08-10 04:00 | 1984-08-13 00:15 | 1985-08-15 15:00 | 1986-08-09 08:00 | 1987-08-19 23:00 | 1988-08-14 06:00 | 1989-08-13 11:45 | 1990-08-09 05:45 | 1991-08-11 16:45 | 1992-08-11 05:00 | 1993-08-01 14:00 | 1994-08-06 13:00 | 1995-08-09 01:15 | 1996-08-19 16:45 | 1997-08-16 02:00 | 1998-08-07 08:30 | 1999-08-26 05:30 | 2000-08-16 14:15 | 2001-08-07 13:45 | 2002-08-10 11:15 | 2003-08-17 13:00 | 2004-08-08 12:30 | 2005-08-23 02:15 | 2006-08-14 19:30 | 2007-08-07 04:00 | 2008-08-18 19:45 | 2009-08-22 03:45 | 2010-08-22 06:30 | 2011-08-09 12:30 | 2012-08-31 | 2013-08-10 05:00 | 2014-08-23 02:45 | 2015-09-03 11:45 | 2016-07-31 16:00 | 2017-08-07 18:30 | 2018-08-20 23:00 | 2019-08-27 20:45 | 2020-08-05 15:00 | 2021-08-22 19:45 | 2022-08-18 13:00
34 | 1979-08-27 08:30 | 1980-08-15 22:00 | 1981-08-21 06:30 | 1982-08-23 03:30 | 1983-08-18 21:00 | 1984-08-14 19:30 | 1985-08-17 07:30 | 1986-08-11 08:00 | 1987-08-25 04:30 | 1988-08-16 14:15 | 1989-08-15 04:15 | 1990-08-11 05:15 | 1991-08-13 09:15 | 1992-08-13 03:30 | 1993-08-03 06:30 | 1994-08-12 06:15 | 1995-08-10 17:45 | 1996-08-21 23:00 | 1997-08-20 19:00 | 1998-08-09 01:00 | 1999-08-27 22:00 | 2000-08-18 06:45 | 2001-08-09 06:15 | 2002-08-12 03:45 | 2003-08-19 05:30 | 2004-08-10 09:15 | 2005-08-24 18:45 | 2006-08-16 12:00 | 2007-08-13 12:30 | 2008-08-20 12:15 | 2009-08-24 02:15 | 2010-08-23 23:00 | 2011-08-11 05:00 | 2012-09-03 00:30 | 2013-08-11 21:30 | 2014-08-24 19:15 | 2015-09-05 04:15 | 2016-08-03 17:00 | 2017-08-11 21:15 | 2018-08-26 12:00 | 2019-08-29 13:15 | 2020-08-07 07:30 | 2021-08-24 19:15 | 2022-08-20 17:00
35 | 1979-08-30 20:00 | 1980-08-20 19:00 | 1981-08-25 12:45 | 1982-08-28 19:00 | 1983-08-22 12:30 | 1984-08-23 15:30 | 1985-08-21 11:00 | 1986-08-15 | 1987-08-28 16:00 | 1988-08-23 12:30 | 1989-08-18 15:45 | 1990-08-14 16:45 | 1991-08-16 21:30 | 1992-08-18 05:00 | 1993-08-06 18:00 | 1994-08-17 08:30 | 1995-08-14 18:30 | 1996-08-25 23:00 | 1997-08-27 23:30 | 1998-08-14 03:30 | 1999-08-31 09:30 | 2000-08-24 11:00 | 2001-08-12 17:45 | 2002-08-16 | 2003-08-23 14:00 | 2004-08-17 08:30 | 2005-08-28 06:15 | 2006-08-20 10:00 | 2007-08-23 05:15 | 2008-08-25 22:30 | 2009-08-27 13:45 | 2010-08-28 19:00 | 2011-08-14 16:30 | 2012-09-06 12:00 | 2013-08-19 20:30 | 2014-08-28 06:45 | 2015-09-15 23:15 | 2016-08-08 01:30 | 2017-08-15 08:45 | 2018-09-03 22:00 | 2019-09-02 05:15 | 2020-08-11 11:00 | 2021-08-28 06:45 | 2022-08-25 16:00
36 | 1979-09-01 12:30 | 1980-08-22 11:30 | 1981-08-27 05:15 | 1982-08-30 11:30 | 1983-08-24 11:15 | 1984-08-25 08:00 | 1985-08-26 08:00 | 1986-08-17 16:00 | 1987-09-01 01:00 | 1988-08-25 05:00 | 1989-08-20 08:15 | 1990-08-16 16:00 | 1991-08-19 09:30 | 1992-08-21 22:30 | 1993-08-08 10:30 | 1994-08-19 01:00 | 1995-08-16 11:00 | 1996-08-27 15:30 | 1997-09-01 20:30 | 1998-08-15 20:00 | 1999-09-02 02:00 | 2000-08-26 19:30 | 2001-08-14 10:15 | 2002-08-24 16:30 | 2003-08-26 17:00 | 2004-08-19 21:00 | 2005-08-29 22:45 | 2006-08-22 09:15 | 2007-08-24 21:45 | 2008-08-27 15:00 | 2009-08-29 06:15 | 2010-08-30 20:30 | 2011-08-16 09:00 | 2012-09-08 04:30 | 2013-08-25 19:00 | 2014-08-30 04:00 | 2015-09-18 11:15 | 2016-08-09 20:00 | 2017-08-17 01:15 | 2018-09-05 14:30 | 2019-09-03 21:45 | 2020-08-13 06:30 | 2021-08-29 23:15 | 2022-08-28 06:30
37 | 1979-09-05 | 1980-08-25 23:00 | 1981-08-31 10:00 | 1982-09-04 20:00 | 1983-08-28 23:00 | 1984-09-02 14:00 | 1985-08-29 21:30 | 1986-08-25 17:00 | 1987-09-05 01:30 | 1988-08-28 16:30 | 1989-08-23 22:45 | 1990-08-28 05:00 | 1991-08-31 08:00 | 1992-08-25 10:00 | 1993-08-14 15:00 | 1994-08-25 20:00 | 1995-08-19 22:30 | 1996-08-31 21:15 | 1997-09-07 02:15 | 1998-08-19 07:30 | 1999-09-05 13:30 | 2000-09-02 19:00 | 2001-08-19 13:00 | 2002-08-28 04:00 | 2003-08-30 04:30 | 2004-08-23 08:30 | 2005-09-04 08:15 | 2006-08-25 20:45 | 2007-08-28 09:15 | 2008-08-31 05:00 | 2009-09-03 16:00 | 2010-09-03 21:00 | 2011-08-19 20:30 | 2012-09-11 16:00 | 2013-08-31 01:15 | 2014-09-02 20:30 | 2015-09-22 08:30 | 2016-08-13 22:30 | 2017-08-20 12:45 | 2018-09-11 22:15 | 2019-09-11 05:30 | 2020-08-16 18:00 | 2021-09-02 10:45 | 2022-09-06 10:00
38 | 1979-09-06 16:30 | 1980-08-30 07:30 | 1981-09-04 08:30 | 1982-09-07 04:30 | 1983-08-30 15:30 | 1984-09-04 11:30 | 1985-08-31 14:00 | 1986-08-31 07:30 | 1987-09-12 15:00 | 1988-08-30 09:00 | 1989-08-26 09:00 | 1990-08-31 17:00 | 1991-09-02 07:30 | 1992-08-27 05:00 | 1993-08-16 16:15 | 1994-08-29 10:00 | 1995-08-21 15:00 | 1996-09-02 13:45 | 1997-09-08 18:45 | 1998-08-21 03:30 | 1999-09-08 01:30 | 2000-09-04 11:30 | 2001-08-22 20:00 | 2002-09-02 17:00 | 2003-09-03 09:00 | 2004-08-27 15:30 | 2005-09-08 04:00 | 2006-08-27 13:15 | 2007-08-30 01:45 | 2008-09-01 21:30 | 2009-09-06 12:30 | 2010-09-05 14:00 | 2011-08-21 13:00 | 2012-09-13 11:00 | 2013-09-06 12:15 | 2014-09-04 13:00 | 2015-09-24 01:00 | 2016-08-16 18:00 | 2017-08-24 23:00 | 2018-09-13 14:45 | 2019-09-13 11:15 | 2020-08-18 10:30 | 2021-09-04 03:15 | 2022-09-08 02:30
39 | 1979-09-10 08:15 | 1980-09-03 12:00 | 1981-09-09 01:30 | 1982-09-13 16:15 | 1983-09-03 03:00 | 1984-09-08 22:30 | 1985-09-04 19:00 | 1986-09-06 20:00 | 1987-09-21 20:45 | 1988-09-04 16:15 | 1989-08-30 16:30 | 1990-09-04 04:30 | 1991-09-08 02:00 | 1992-09-07 04:00 | 1993-08-24 05:00 | 1994-09-03 10:30 | 1995-08-25 23:30 | 1996-09-06 09:15 | 1997-09-12 06:15 | 1998-08-24 15:00 | 1999-09-11 13:00 | 2000-09-15 22:00 | 2001-08-26 09:00 | 2002-09-09 11:30 | 2003-09-06 20:30 | 2004-09-03 18:00 | 2005-09-15 00:15 | 2006-08-31 00:45 | 2007-09-02 13:15 | 2008-09-05 09:00 | 2009-09-11 04:30 | 2010-09-09 01:30 | 2011-08-25 05:00 | 2012-09-20 08:15 | 2013-09-11 17:15 | 2014-09-08 13:00 | 2015-10-01 23:00 | 2016-08-24 01:00 | 2017-08-28 12:00 | 2018-09-20 19:00 | 2019-10-02 08:30 | 2020-08-21 22:00 | 2021-09-07 15:00 | 2022-09-28 05:30
40 | 1979-09-12 21:15 | 1980-09-05 04:30 | 1981-09-10 18:00 | 1982-09-16 18:00 | 1983-09-04 19:30 | 1984-09-10 15:00 | 1985-09-08 17:00 | 1986-09-10 04:30 | 1987-09-23 13:15 | 1988-09-06 15:15 | 1989-09-01 09:00 | 1990-09-06 04:00 | 1991-09-10 17:30 | 1992-09-08 20:30 | 1993-08-25 21:30 | 1994-09-05 16:00 | 1995-08-28 21:30 | 1996-09-08 01:45 | 1997-09-25 11:15 | 1998-08-26 07:30 | 1999-09-13 19:00 | 2000-09-18 01:15 | 2001-08-28 07:15 | 2002-09-11 04:00 | 2003-09-08 13:00 | 2004-09-05 10:30 | 2005-09-16 16:45 | 2006-09-01 17:15 | 2007-09-04 14:15 | 2008-09-07 01:30 | 2009-09-12 21:00 | 2010-09-11 20:30 | 2011-08-30 05:00 | 2012-09-22 06:15 | 2013-09-13 09:45 | 2014-09-10 05:30 | 2015-10-04 07:30 | 2016-08-25 17:30 | 2017-09-04 04:00 | 2018-09-22 11:30 | 2019-10-04 01:00 | 2020-08-25 10:00 | 2021-09-09 15:30 | 2022-09-29 22:00
41 | 1979-09-16 08:45 | 1980-09-12 17:00 | 1981-09-23 12:00 | 1982-09-26 11:00 | 1983-09-10 04:00 | 1984-09-15 06:00 | 1985-09-12 09:00 | 1986-09-13 16:00 | 1987-10-03 05:30 | 1988-09-10 02:45 | 1989-09-04 20:30 | 1990-09-14 19:00 | 1991-09-25 | 1992-09-12 08:00 | 1993-08-29 09:00 | 1994-09-10 05:30 | 1995-09-03 21:30 | 1996-09-12 10:15 | 1997-10-04 16:45 | 1998-08-31 04:15 | 1999-09-24 08:00 | 2000-09-21 12:45 | 2001-09-02 07:00 | 2002-09-14 15:30 | 2003-09-16 02:30 | 2004-09-13 07:00 | 2005-09-21 05:30 | 2006-09-05 04:45 | 2007-09-10 11:30 | 2008-09-15 23:15 | 2009-09-18 01:00 | 2010-09-15 08:00 | 2011-09-06 23:30 | 2012-10-20 23:30 | 2013-09-23 08:00 | 2014-09-13 17:00 | 2015-10-07 19:30 | 2016-08-31 12:00 | 2017-09-07 22:00 | 2018-10-14 12:00 | 2019-10-11 07:15 | 2020-09-04 07:00 | 2021-09-18 20:00 | 2022-10-03 12:00
42 | 1979-09-18 01:15 | 1980-09-14 18:30 | 1981-09-25 13:30 | 1982-09-30 01:30 | 1983-09-11 20:30 | 1984-09-16 22:30 | 1985-09-14 01:30 | 1986-09-20 21:00 | 1987-10-05 08:15 | 1988-09-11 19:15 | 1989-09-06 13:00 | 1990-09-16 17:00 | 1991-10-03 10:30 | 1992-09-15 04:00 | 1993-09-04 11:00 | 1994-09-18 | 1995-09-05 14:00 | 1996-09-14 11:00 | 1997-10-09 12:15 | 1998-09-03 09:15 | 1999-09-26 22:30 | 2000-09-23 06:15 | 2001-09-04 12:15 | 2002-09-16 11:30 | 2003-09-17 19:00 | 2004-09-14 23:30 | 2005-09-26 18:30 | 2006-09-08 05:00 | 2007-09-14 18:00 | 2008-09-18 03:30 | 2009-09-20 08:15 | 2010-09-17 00:30 | 2011-09-08 16:00 | 2012-10-22 16:00 | 2013-09-27 19:00 | 2014-09-16 11:30 | 2015-10-26 09:15 | 2016-09-02 17:30 | 2017-09-09 14:30 | 2018-10-22 03:30 | 2019-10-22 01:00 | 2020-09-09 14:00 | 2021-09-21 23:30 | 2022-10-06 15:00

## OUT_overall monthly
OUT_overall monthly
Additive representative hindcast-year schedules for P50, P75 and P90. Each scenario reconciles independently to its complete representative campaign duration.
A. Statistical planning and representative-year selection | [8 empty] | B. Additive representative-year reconciliation | [9 empty] | Scenario | Workable time [h] | Downtime [h]
Scenario | Statistical duration [h] | Statistical duration [d] | Representative year | Representative duration [h] | Representative duration [d] | Representative - target [h] | Interpretation |  | Scenario | Exact P0 [h] | Timestep adjustment [h] | Representative downtime [h] | Reconciled duration [h] | Reported representative duration [h] | Variance [h] | Downtime [%] | Status | Reconciliation | P50 | 2756 | 1303.75
P50 | 4060.75 | 169.1979 | 1984 | 4059.75 | 169.1562 | -1 | Closest complete historical simulation to the statistical target |  | P50 | 2747.9 | 8.1 | 1303.75 | 4059.75 | 4059.75 | -1.3642e-12 | 32.11% | RECONCILED | P0 + timestep adjustment + representative downtime | P75 | 2756 | 1539.75
P75 | 4296.75 | 179.0312 | 2005 | 4295.75 | 178.9896 | -1 | Closest complete historical simulation to the statistical target |  | P75 | 2747.9 | 8.1 | 1539.75 | 4295.75 | 4295.75 | -1.819e-12 | 35.84% | RECONCILED | P0 + timestep adjustment + representative downtime | P90 | 2756 | 1845.5
P90 | 4580.725 | 190.8635 | 1997 | 4601.5 | 191.7292 | 20.775 | Closest complete historical simulation to the statistical target |  | P90 | 2747.9 | 8.1 | 1845.5 | 4601.5 | 4601.5 | -1.819e-12 | 40.11% | RECONCILED | P0 + timestep adjustment + representative downtime
C. Representative-year monthly schedules - additive
| P50 - representative year 1984 | [5 empty] | P75 - representative year 2005 | [5 empty] | P90 - representative year 1997
Month | Positions | Cumulative | Working [h] | Downtime [h] | Campaign [h] | DT [%] | Positions | Cumulative | Working [h] | Downtime [h] | Campaign [h] | DT [%] | Positions | Cumulative | Working [h] | Downtime [h] | Campaign [h] | DT [%]
Jan | 0 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
Feb | 0 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
Mar | 0 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
Apr | 4 | 4 | 337 | 383 | 720 | 53.19% | 6 | 6 | 500.5 | 219.5 | 720 | 30.49% | 6 | 6 | 481.25 | 238.75 | 720 | 33.16%
May | 6 | 10 | 472.5 | 271.5 | 744 | 36.49% | 7 | 13 | 489.25 | 254.75 | 744 | 34.24% | 8 | 14 | 576 | 168 | 744 | 22.58%
Jun | 9 | 19 | 552.75 | 167.25 | 720 | 23.23% | 7 | 20 | 438.25 | 281.75 | 720 | 39.13% | 8 | 22 | 468.5 | 251.5 | 720 | 34.93%
Jul | 10 | 29 | 605 | 139 | 744 | 18.68% | 8 | 28 | 504.25 | 239.75 | 744 | 32.22% | 7 | 29 | 466 | 278 | 744 | 37.37%
Aug | 7 | 36 | 493 | 251 | 744 | 33.74% | 8 | 36 | 473 | 271 | 744 | 36.42% | 6 | 35 | 366.5 | 377.5 | 744 | 50.74%
Sep | 6 | 42 | 295.75 | 92 | 387.75 | 23.73% | 6 | 42 | 350.75 | 273 | 623.75 | 43.77% | 5 | 40 | 298.25 | 421.75 | 720 | 58.58%
Oct |  | 42 | [5 empty] | 42 |  |  |  |  | 2 | 42 | 99.5 | 110 | 209.5 | 52.51%
Nov |  | 42 | [5 empty] | 42 | [5 empty] | 42
Dec |  | 42 | [5 empty] | 42 | [5 empty] | 42
Total | 42 | 42 | 2756 | 1303.75 | 4059.75 | 32.11% | 42 | 42 | 2756 | 1539.75 | 4295.75 | 35.84% | 42 | 42 | 2756 | 1845.5 | 4601.5 | 40.11%
Interpretation: every P50/P75/P90 block is one complete representative hindcast-year simulation. Monthly working hours and downtime hours are additive and reconcile to the representative duration. Independent monthly percentile statistics are provided separately in OUT_specific month.

## OUT_specific month
OUT_specific month
Monthly statistical profile. Mean, P50, P75 and P90 are calculated independently for each calendar month across successful simulations. These monthly percentile values are non-additive and must not be summed to reconcile total campaign duration.
Month | Cumulative positions - Mean | Cumulative positions - P50 | Cumulative positions - P75 | Cumulative positions - P90 | Downtime hours - Mean | Downtime hours - P50 | Downtime hours - P75 | Downtime hours - P90 | Workable hours - Mean | Workable hours - P50 | Workable hours - P75 | Workable hours - P90
Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apr | 4.8636 | 5 | 4 | 4 | 284.9375 | 284.5 | 347 | 386.325 | 435.0625 | 435.5 | 373 | 333.675
May | 12.5455 | 13 | 12 | 10 | 213.1705 | 220.125 | 256.4375 | 285.3 | 530.8295 | 523.875 | 487.5625 | 458.7
Jun | 20.4318 | 20.5 | 19 | 18 | 228.3239 | 232.75 | 283.8125 | 345.9 | 491.6761 | 487.25 | 436.1875 | 374.1
Jul | 28.9091 | 29 | 28 | 27 | 216.75 | 205.25 | 267.4375 | 321.7 | 527.25 | 538.75 | 476.5625 | 422.3
Aug | 37.1818 | 37 | 36 | 35 | 235.1875 | 228.375 | 305.75 | 367.375 | 508.8125 | 515.625 | 438.25 | 376.625
Sep | 42 | 42 | 42 | 40 | 183.1951 | 144.2518 | 315.907 | 456.4 | 295.7652 | 244.4982 | 308.843 | 263.6
Oct | 42 | 42 | 42 | 42 |  |  |  | 154.0079 |  |  |  | 34.7171
Nov | 42 | 42 | 42 | 42
Dec | 42 | 42 | 42 | 42

## OUT_overall annual
OUT_overall annual
One row per hindcast start year, including success, duration, P0 reconciliation and data coverage.
Hindcast start year | Successful | Campaign start | Campaign finish | Duration [days] | Duration [hours] | Exact P0 [hours] | Working time [hours] | Timestep adjustment [hours] | Downtime [hours] | Completed positions | Data coverage limited | Message
1979 | TRUE | 1979-04-01 | 1979-09-18 06:30 | 170.2708 | 4086.5 | 2747.9 | 2756 | 8.1 | 1330.5 | 42 | FALSE | Completed
1980 | TRUE | 1980-04-01 | 1980-09-14 23:45 | 166.9896 | 4007.75 | 2747.9 | 2756 | 8.1 | 1251.75 | 42 | FALSE | Completed
1981 | TRUE | 1981-04-01 | 1981-09-25 18:45 | 177.7812 | 4266.75 | 2747.9 | 2756 | 8.1 | 1510.75 | 42 | FALSE | Completed
1982 | TRUE | 1982-04-01 | 1982-09-30 06:45 | 182.2812 | 4374.75 | 2747.9 | 2756 | 8.1 | 1618.75 | 42 | FALSE | Completed
1983 | TRUE | 1983-04-01 | 1983-09-12 01:45 | 164.0729 | 3937.75 | 2747.9 | 2756 | 8.1 | 1181.75 | 42 | FALSE | Completed
1984 | TRUE | 1984-04-01 | 1984-09-17 03:45 | 169.1562 | 4059.75 | 2747.9 | 2756 | 8.1 | 1303.75 | 42 | FALSE | Completed
1985 | TRUE | 1985-04-01 | 1985-09-14 06:45 | 166.2812 | 3990.75 | 2747.9 | 2756 | 8.1 | 1234.75 | 42 | FALSE | Completed
1986 | TRUE | 1986-04-01 | 1986-09-21 02:15 | 173.0938 | 4154.25 | 2747.9 | 2756 | 8.1 | 1398.25 | 42 | FALSE | Completed
1987 | TRUE | 1987-04-01 | 1987-10-05 13:30 | 187.5625 | 4501.5 | 2747.9 | 2756 | 8.1 | 1745.5 | 42 | FALSE | Completed
1988 | TRUE | 1988-04-01 | 1988-09-12 00:30 | 164.0208 | 3936.5 | 2747.9 | 2756 | 8.1 | 1180.5 | 42 | FALSE | Completed
1989 | TRUE | 1989-04-01 | 1989-09-06 18:15 | 158.7604 | 3810.25 | 2747.9 | 2756 | 8.1 | 1054.25 | 42 | FALSE | Completed
1990 | TRUE | 1990-04-01 | 1990-09-16 22:15 | 168.9271 | 4054.25 | 2747.9 | 2756 | 8.1 | 1298.25 | 42 | FALSE | Completed
1991 | TRUE | 1991-04-01 | 1991-10-03 15:45 | 185.6562 | 4455.75 | 2747.9 | 2756 | 8.1 | 1699.75 | 42 | FALSE | Completed
1992 | TRUE | 1992-04-01 | 1992-09-15 09:15 | 167.3854 | 4017.25 | 2747.9 | 2756 | 8.1 | 1261.25 | 42 | FALSE | Completed
1993 | TRUE | 1993-04-01 | 1993-09-04 16:15 | 156.6771 | 3760.25 | 2747.9 | 2756 | 8.1 | 1004.25 | 42 | FALSE | Completed
1994 | TRUE | 1994-04-01 | 1994-09-18 05:15 | 170.2188 | 4085.25 | 2747.9 | 2756 | 8.1 | 1329.25 | 42 | FALSE | Completed
1995 | TRUE | 1995-04-01 | 1995-09-05 19:15 | 157.8021 | 3787.25 | 2747.9 | 2756 | 8.1 | 1031.25 | 42 | FALSE | Completed
1996 | TRUE | 1996-04-01 | 1996-09-14 16:15 | 166.6771 | 4000.25 | 2747.9 | 2756 | 8.1 | 1244.25 | 42 | FALSE | Completed
1997 | TRUE | 1997-04-01 | 1997-10-09 17:30 | 191.7292 | 4601.5 | 2747.9 | 2756 | 8.1 | 1845.5 | 42 | FALSE | Completed
1998 | TRUE | 1998-04-01 | 1998-09-03 14:30 | 155.6042 | 3734.5 | 2747.9 | 2756 | 8.1 | 978.5 | 42 | FALSE | Completed
1999 | TRUE | 1999-04-01 | 1999-09-27 03:45 | 179.1562 | 4299.75 | 2747.9 | 2756 | 8.1 | 1543.75 | 42 | FALSE | Completed
2000 | TRUE | 2000-04-01 | 2000-09-23 11:30 | 175.4792 | 4211.5 | 2747.9 | 2756 | 8.1 | 1455.5 | 42 | FALSE | Completed
2001 | TRUE | 2001-04-01 | 2001-09-04 17:30 | 156.7292 | 3761.5 | 2747.9 | 2756 | 8.1 | 1005.5 | 42 | FALSE | Completed
2002 | TRUE | 2002-04-01 | 2002-09-16 16:45 | 168.6979 | 4048.75 | 2747.9 | 2756 | 8.1 | 1292.75 | 42 | FALSE | Completed
2003 | TRUE | 2003-04-01 | 2003-09-18 00:15 | 170.0104 | 4080.25 | 2747.9 | 2756 | 8.1 | 1324.25 | 42 | FALSE | Completed
2004 | TRUE | 2004-04-01 | 2004-09-15 04:45 | 167.1979 | 4012.75 | 2747.9 | 2756 | 8.1 | 1256.75 | 42 | FALSE | Completed
2005 | TRUE | 2005-04-01 | 2005-09-26 23:45 | 178.9896 | 4295.75 | 2747.9 | 2756 | 8.1 | 1539.75 | 42 | FALSE | Completed
2006 | TRUE | 2006-04-01 | 2006-09-08 10:15 | 160.4271 | 3850.25 | 2747.9 | 2756 | 8.1 | 1094.25 | 42 | FALSE | Completed
2007 | TRUE | 2007-04-01 | 2007-09-14 23:15 | 166.9688 | 4007.25 | 2747.9 | 2756 | 8.1 | 1251.25 | 42 | FALSE | Completed
2008 | TRUE | 2008-04-01 | 2008-09-18 08:45 | 170.3646 | 4088.75 | 2747.9 | 2756 | 8.1 | 1332.75 | 42 | FALSE | Completed
2009 | TRUE | 2009-04-01 | 2009-09-20 13:30 | 172.5625 | 4141.5 | 2747.9 | 2756 | 8.1 | 1385.5 | 42 | FALSE | Completed
2010 | TRUE | 2010-04-01 | 2010-09-17 05:45 | 169.2396 | 4061.75 | 2747.9 | 2756 | 8.1 | 1305.75 | 42 | FALSE | Completed
2011 | TRUE | 2011-04-01 | 2011-09-08 21:15 | 160.8854 | 3861.25 | 2747.9 | 2756 | 8.1 | 1105.25 | 42 | FALSE | Completed
2012 | TRUE | 2012-04-01 | 2012-10-22 21:15 | 204.8854 | 4917.25 | 2747.9 | 2756 | 8.1 | 2161.25 | 42 | FALSE | Completed
2013 | TRUE | 2013-04-01 | 2013-09-28 00:15 | 180.0104 | 4320.25 | 2747.9 | 2756 | 8.1 | 1564.25 | 42 | FALSE | Completed
2014 | TRUE | 2014-04-01 | 2014-09-16 16:45 | 168.6979 | 4048.75 | 2747.9 | 2756 | 8.1 | 1292.75 | 42 | FALSE | Completed
2015 | TRUE | 2015-04-01 | 2015-10-26 14:30 | 208.6042 | 5006.5 | 2747.9 | 2756 | 8.1 | 2250.5 | 42 | FALSE | Completed
2016 | TRUE | 2016-04-01 | 2016-09-02 22:45 | 154.9479 | 3718.75 | 2747.9 | 2756 | 8.1 | 962.75 | 42 | FALSE | Completed
2017 | TRUE | 2017-04-01 | 2017-09-09 19:45 | 161.8229 | 3883.75 | 2747.9 | 2756 | 8.1 | 1127.75 | 42 | FALSE | Completed
2018 | TRUE | 2018-04-01 | 2018-10-22 08:45 | 204.3646 | 4904.75 | 2747.9 | 2756 | 8.1 | 2148.75 | 42 | FALSE | Completed
2019 | TRUE | 2019-04-01 | 2019-10-22 06:15 | 204.2604 | 4902.25 | 2747.9 | 2756 | 8.1 | 2146.25 | 42 | FALSE | Completed
2020 | TRUE | 2020-04-01 | 2020-09-09 19:15 | 161.8021 | 3883.25 | 2747.9 | 2756 | 8.1 | 1127.25 | 42 | FALSE | Completed
2021 | TRUE | 2021-04-01 | 2021-09-22 04:45 | 174.1979 | 4180.75 | 2747.9 | 2756 | 8.1 | 1424.75 | 42 | FALSE | Completed
2022 | TRUE | 2022-04-01 | 2022-10-06 20:15 | 188.8438 | 4532.25 | 2747.9 | 2756 | 8.1 | 1776.25 | 42 | FALSE | Completed
2023 | FALSE | 2023-04-01 |  |  |  | 2747.9 | 907.5 | 0 | 532.75 | 12 | TRUE | Unable to assess - End of available weather data

## OUT_planning summary
OUT_planning summary
Planning scenarios mapped to the 2030 campaign calendar.
Planning scenario summary
Scenario | Representative weather year | Duration [days] | Planned start | Estimated finish | Basis
P0 (no weather) |  | 114.4958 | 2030-04-01 | 2030-07-24 11:54 | No-weather deterministic sequence
Best historical scenario | 2016 | 154.9479 | 2030-04-01 | 2030-09-02 22:45 | Actual weather sequence from 2016
P50 | 1984 | 169.1979 | 2030-04-01 | 2030-09-17 04:45 | Percentile across all successful historical start-year simulations
P75 | 2005 | 179.0312 | 2030-04-01 | 2030-09-27 00:45 | Percentile across all successful historical start-year simulations
P90 | 1997 | 190.8635 | 2030-04-01 | 2030-10-08 20:44 | Percentile across all successful historical start-year simulations
Worst historical scenario | 2015 | 208.6042 | 2030-04-01 | 2030-10-26 14:30 | Actual weather sequence from 2015
Representative hindcast years
Planning scenario | Statistical duration [days] | Estimated finish | Representative hindcast year | Representative duration [days] | Difference from target [days]
P50 | 169.1979 | 2030-09-17 04:45 | 1984 | 169.1562 | 0.041667
P75 | 179.0312 | 2030-09-27 00:45 | 2005 | 178.9896 | 0.041667
P90 | 190.8635 | 2030-10-08 20:44 | 1997 | 191.7292 | 0.86562
[6 empty] | Scenario | Duration [days]
[6 empty] | P50 | 169.1979
[6 empty] | P75 | 179.0312
[6 empty] | P90 | 190.8635

## OUT_planning MS
OUT_planning MS
Planning milestone dates and elapsed durations by position for P0, best, P50, P75, P90 and worst profiles.
Position | P0 elapsed [days] | P0 completion date | Best elapsed [days] | Best completion date | P50 elapsed [days] | P50 completion date | P75 elapsed [days] | P75 completion date | P90 elapsed [days] | P90 completion date | Worst elapsed [days] | Worst completion date
1 | 4.2271 | 2030-04-05 05:27 | 4.2708 | 2030-04-05 06:30 | 7.724 | 2030-04-08 17:23 | 10.3594 | 2030-04-11 08:38 | 12.8354 | 2030-04-13 20:03 | 15.6667 | 2030-04-16 16:00
2 | 6.4667 | 2030-04-07 11:12 | 6.5312 | 2030-04-07 12:45 | 11.6302 | 2030-04-12 15:08 | 16.5547 | 2030-04-17 13:19 | 17.8604 | 2030-04-18 20:39 | 26.1042 | 2030-04-27 02:30
3 | 10.9104 | 2030-04-11 21:51 | 13.4375 | 2030-04-14 10:30 | 19.0156 | 2030-04-20 00:22 | 23.4661 | 2030-04-24 11:11 | 25.3542 | 2030-04-26 08:30 | 30.5938 | 2030-05-01 14:15
4 | 13.15 | 2030-04-14 03:36 | 16.3021 | 2030-04-17 07:15 | 22.9896 | 2030-04-23 23:45 | 26.5156 | 2030-04-27 12:22 | 28.7333 | 2030-04-29 17:36 | 33.5104 | 2030-05-04 12:15
5 | 17.5938 | 2030-04-18 14:15 | 21.1771 | 2030-04-22 04:15 | 29.401 | 2030-04-30 09:37 | 32.651 | 2030-05-03 15:37 | 36.6698 | 2030-05-07 16:04 | 40.6979 | 2030-05-11 16:45
6 | 19.8333 | 2030-04-20 20:00 | 24.8021 | 2030-04-25 19:15 | 32.6927 | 2030-05-03 16:38 | 35.2708 | 2030-05-06 06:30 | 39.1688 | 2030-05-10 04:03 | 51.5625 | 2030-05-22 13:30
7 | 24.2771 | 2030-04-25 06:39 | 29.6562 | 2030-04-30 15:45 | 39.1615 | 2030-05-10 03:53 | 41.7135 | 2030-05-12 17:07 | 46.5094 | 2030-05-17 12:14 | 56.1979 | 2030-05-27 04:45
8 | 26.5167 | 2030-04-27 12:24 | 32.1354 | 2030-05-03 03:15 | 41.625 | 2030-05-12 15:00 | 44.8568 | 2030-05-15 20:34 | 49.8698 | 2030-05-20 20:52 | 58.4583 | 2030-05-29 11:00
9 | 29.9917 | 2030-04-30 23:48 | 35.9479 | 2030-05-06 22:45 | 46.9948 | 2030-05-17 23:52 | 50.0677 | 2030-05-21 01:38 | 55.9531 | 2030-05-26 22:52 | 61.9375 | 2030-06-01 22:30
10 | 31.6792 | 2030-05-02 16:18 | 37.6354 | 2030-05-08 15:15 | 49.0938 | 2030-05-20 02:15 | 52.3307 | 2030-05-23 07:56 | 57.6406 | 2030-05-28 15:22 | 63.8854 | 2030-06-03 21:15
11 | 35.1542 | 2030-05-06 03:42 | 41.1146 | 2030-05-12 02:45 | 53.2552 | 2030-05-24 06:08 | 56.3516 | 2030-05-27 08:26 | 62.1573 | 2030-06-02 03:47 | 69.2812 | 2030-06-09 06:45
12 | 36.8417 | 2030-05-07 20:12 | 43.0208 | 2030-05-14 00:30 | 55.7552 | 2030-05-26 18:08 | 60.3854 | 2030-05-31 09:15 | 64.3792 | 2030-06-04 09:06 | 72.75 | 2030-06-12 18:00
13 | 40.3167 | 2030-05-11 07:36 | 46.5 | 2030-05-17 12:00 | 60.8542 | 2030-05-31 20:30 | 65.5078 | 2030-06-05 12:11 | 68.5573 | 2030-06-08 13:22 | 77.3125 | 2030-06-17 07:30
14 | 42.0042 | 2030-05-13 00:06 | 48.1875 | 2030-05-19 04:30 | 63.2292 | 2030-06-03 05:30 | 67.7083 | 2030-06-07 17:00 | 70.326 | 2030-06-10 07:50 | 79 | 2030-06-19
15 | 45.4792 | 2030-05-16 11:30 | 51.7604 | 2030-05-22 18:15 | 68.6771 | 2030-06-08 16:15 | 73.3359 | 2030-06-13 08:04 | 75.8062 | 2030-06-15 19:21 | 82.8438 | 2030-06-22 20:15
16 | 47.1667 | 2030-05-18 04:00 | 53.6667 | 2030-05-24 16:00 | 71.3854 | 2030-06-11 09:15 | 75.5859 | 2030-06-15 14:04 | 78.5167 | 2030-06-18 12:24 | 84.5312 | 2030-06-24 12:45
17 | 50.6417 | 2030-05-21 15:24 | 62.9688 | 2030-06-02 23:15 | 75.6615 | 2030-06-15 15:53 | 81.2865 | 2030-06-21 06:53 | 82.9729 | 2030-06-22 23:21 | 88.1146 | 2030-06-28 02:45
18 | 52.3292 | 2030-05-23 07:54 | 64.8542 | 2030-06-04 20:30 | 78.9479 | 2030-06-18 22:45 | 84.7135 | 2030-06-24 17:07 | 86.7479 | 2030-06-26 17:57 | 89.8021 | 2030-06-29 19:15
19 | 55.8042 | 2030-05-26 19:18 | 71.2604 | 2030-06-11 06:15 | 83.9583 | 2030-06-23 23:00 | 89.5286 | 2030-06-29 12:41 | 92.8 | 2030-07-02 19:12 | 96.7604 | 2030-07-06 18:15
20 | 57.4917 | 2030-05-28 11:48 | 73.7292 | 2030-06-13 17:30 | 87.0729 | 2030-06-27 01:45 | 91.5365 | 2030-07-01 12:53 | 94.9396 | 2030-07-04 22:33 | 98.4479 | 2030-07-08 10:45
21 | 60.9667 | 2030-05-31 23:12 | 81.5 | 2030-06-21 12:00 | 90.7188 | 2030-06-30 17:15 | 95.2812 | 2030-07-05 06:45 | 98.9719 | 2030-07-08 23:20 | 103.4062 | 2030-07-13 09:45
22 | 62.6542 | 2030-06-02 15:42 | 83.1875 | 2030-06-23 04:30 | 93.4062 | 2030-07-03 09:45 | 97.388 | 2030-07-07 09:19 | 100.6594 | 2030-07-10 15:50 | 105.2083 | 2030-07-15 05:00
23 | 66.1292 | 2030-06-06 03:06 | 87.8333 | 2030-06-27 20:00 | 98.4688 | 2030-07-08 11:15 | 103.5833 | 2030-07-13 14:00 | 106.2177 | 2030-07-16 05:13 | 112.6667 | 2030-07-22 16:00
24 | 67.8167 | 2030-06-07 19:36 | 89.8854 | 2030-06-29 21:15 | 101.5625 | 2030-07-11 13:30 | 105.2708 | 2030-07-15 06:30 | 109.6719 | 2030-07-19 16:08 | 115.3125 | 2030-07-25 07:30
25 | 71.2917 | 2030-06-11 07:00 | 93.625 | 2030-07-03 15:00 | 106.2135 | 2030-07-16 05:07 | 109.7396 | 2030-07-19 17:45 | 113.8438 | 2030-07-23 20:15 | 120.7708 | 2030-07-30 18:30
26 | 72.9792 | 2030-06-12 23:30 | 95.3125 | 2030-07-05 07:30 | 108.9635 | 2030-07-18 23:07 | 112.2839 | 2030-07-22 06:49 | 115.7531 | 2030-07-25 18:05 | 122.4583 | 2030-08-01 11:00
27 | 76.4542 | 2030-06-16 10:54 | 100.6875 | 2030-07-10 16:30 | 113.4219 | 2030-07-23 10:08 | 118.5208 | 2030-07-28 12:30 | 121.0656 | 2030-07-31 01:35 | 125.9375 | 2030-08-04 22:30
28 | 78.1417 | 2030-06-18 03:24 | 102.6042 | 2030-07-12 14:30 | 116.8021 | 2030-07-26 19:15 | 121.0208 | 2030-07-31 00:30 | 124.401 | 2030-08-03 09:37 | 127.625 | 2030-08-06 15:00
29 | 81.6167 | 2030-06-21 14:48 | 106.9792 | 2030-07-16 23:30 | 121.901 | 2030-07-31 21:37 | 125.2135 | 2030-08-04 05:07 | 130.649 | 2030-08-09 15:34 | 138.3958 | 2030-08-17 09:30
30 | 83.3042 | 2030-06-23 07:18 | 108.6667 | 2030-07-18 16:00 | 123.8385 | 2030-08-02 20:07 | 129.401 | 2030-08-08 09:37 | 134.1781 | 2030-08-13 04:16 | 140.0833 | 2030-08-19 02:00
31 | 86.7792 | 2030-06-26 18:42 | 115.7917 | 2030-07-25 19:00 | 128.9115 | 2030-08-07 21:53 | 134.9375 | 2030-08-13 22:30 | 138.4563 | 2030-08-17 10:57 | 148.9167 | 2030-08-27 22:00
32 | 88.4667 | 2030-06-28 11:12 | 117.5417 | 2030-07-27 13:00 | 131.6302 | 2030-08-10 15:08 | 137.3958 | 2030-08-16 09:30 | 140.2188 | 2030-08-19 05:15 | 152.0104 | 2030-08-31 00:15
33 | 91.9417 | 2030-07-01 22:36 | 121.6667 | 2030-07-31 16:00 | 135.5312 | 2030-08-14 12:45 | 142.0312 | 2030-08-21 00:45 | 144.1083 | 2030-08-23 02:36 | 155.4896 | 2030-09-03 11:45
34 | 93.6292 | 2030-07-03 15:06 | 124.2708 | 2030-08-03 06:30 | 137.9531 | 2030-08-16 22:52 | 144.9922 | 2030-08-23 23:49 | 148.0979 | 2030-08-27 02:21 | 157.1771 | 2030-09-05 04:15
35 | 97.1042 | 2030-07-07 02:30 | 127.75 | 2030-08-06 18:00 | 144.3698 | 2030-08-23 08:52 | 149.2656 | 2030-08-28 06:22 | 152.2271 | 2030-08-31 05:27 | 167.9688 | 2030-09-15 23:15
36 | 98.7917 | 2030-07-08 19:00 | 129.4375 | 2030-08-08 10:30 | 146.5625 | 2030-08-25 13:30 | 151.0182 | 2030-08-30 00:26 | 154.0146 | 2030-09-02 00:21 | 170.4688 | 2030-09-18 11:15
37 | 102.2667 | 2030-07-12 06:24 | 134.9375 | 2030-08-13 22:30 | 151.6198 | 2030-08-30 14:52 | 155.9922 | 2030-09-03 23:49 | 158.8906 | 2030-09-06 21:22 | 174.3542 | 2030-09-22 08:30
38 | 103.9542 | 2030-07-13 22:54 | 137.6771 | 2030-08-16 16:15 | 154.4427 | 2030-09-02 10:38 | 158.5625 | 2030-09-06 13:30 | 163.4719 | 2030-09-11 11:20 | 176.0417 | 2030-09-24 01:00
39 | 107.4292 | 2030-07-17 10:18 | 142.9167 | 2030-08-21 22:00 | 159.0104 | 2030-09-07 00:15 | 163.5859 | 2030-09-11 14:04 | 172.6573 | 2030-09-20 15:47 | 184.3542 | 2030-10-02 08:30
40 | 109.1167 | 2030-07-19 02:48 | 146.4167 | 2030-08-25 10:00 | 161.25 | 2030-09-09 06:00 | 165.5026 | 2030-09-13 12:04 | 175.2302 | 2030-09-23 05:31 | 186.3125 | 2030-10-04 07:30
41 | 112.5917 | 2030-07-22 14:12 | 150.375 | 2030-08-29 09:00 | 166.7188 | 2030-09-14 17:15 | 175.375 | 2030-09-23 09:00 | 186.3385 | 2030-10-04 08:07 | 202.9792 | 2030-10-20 23:30
42 | 114.2792 | 2030-07-24 06:42 | 154.7292 | 2030-09-02 17:30 | 168.9792 | 2030-09-16 23:30 | 178.8125 | 2030-09-26 19:30 | 190.6448 | 2030-10-08 15:29 | 208.3854 | 2030-10-26 09:15

## OUT_overall DT
OUT_overall DT
Representative P50, P75 and P90 time summary with clustered workable-time and downtime columns, plus selected P0 downtime by activity.
Representative scenario summary | [7 empty] | Planning scenario | Workable time [hours] | Downtime [hours]
Planning scenario | Statistical duration [days] | Representative hindcast year | Representative duration [days] | Workable time [hours] | Downtime [hours] | Workable time [% campaign] | Downtime [% campaign] | P50 | 2756 | 1303.75
P50 | 169.1979 | 1984 | 169.1562 | 2756 | 1303.75 | 67.89% | 32.11% | P75 | 2756 | 1539.75
P75 | 179.0312 | 2005 | 178.9896 | 2756 | 1539.75 | 64.16% | 35.84% | P90 | 2756 | 1845.5
P90 | 190.8635 | 1997 | 191.7292 | 2756 | 1845.5 | 59.89% | 40.11%
Activity downtime by planning scenario
Planning scenario | Representative hindcast year | Activity | Downtime hours | % of total downtime | % of campaign time
P50 | 1984 | Blade #2 Lifting (safe-to-safe) | 198 | 15.187 | 4.8771
P50 | 1984 | Jacking down at site | 197 | 15.1103 | 4.8525
P50 | 1984 | Blade yoke rigging and attachement to Blade #1 | 194.5 | 14.9185 | 4.7909
P50 | 1984 | DP field check | 126.5 | 9.7028 | 3.116
P50 | 1984 | Loadout Nacelle #1 | 87.25 | 6.6922 | 2.1491
P50 | 1984 | Tower rigging-up (attached lifting equipment) | 85.75 | 6.5772 | 2.1122
P50 | 1984 | Blade #3 Lifting (safe-to-safe) | 83.75 | 6.4238 | 2.0629
P50 | 1984 | Remove TP cover and Preparation of TP | 79.25 | 6.0786 | 1.9521
P50 | 1984 | Loadout Tower #1 | 77.25 | 5.9252 | 1.9028
P50 | 1984 | Loadout Blade 1 | 76 | 5.8293 | 1.872
P50 | 1984 | Lifting HSBM and lifting tools from Nacelle | 42.5 | 3.2598 | 1.0469
P50 | 1984 | Preload and jacking up at site | 22.5 | 1.7258 | 0.55422
P50 | 1984 | Loadout Blade 2 | 15.75 | 1.2081 | 0.38795
P50 | 1984 | Loadout Blade 3 | 13.5 | 1.0355 | 0.33253
P50 | 1984 | Positioning at WTG location | 4.25 | 0.32598 | 0.10469
P75 | 2005 | Blade yoke rigging and attachement to Blade #1 | 418.25 | 27.1635 | 9.7364
P75 | 2005 | Loadout Blade 1 | 267 | 17.3405 | 6.2154
P75 | 2005 | Jacking down at site | 156.25 | 10.1478 | 3.6373
P75 | 2005 | DP field check | 145 | 9.4171 | 3.3754
P75 | 2005 | Preload and jacking up at site | 117.25 | 7.6149 | 2.7294
P75 | 2005 | Loadout Tower #2 | 92.5 | 6.0075 | 2.1533
P75 | 2005 | Blade #3 Lifting (safe-to-safe) | 80 | 5.1956 | 1.8623
P75 | 2005 | Remove TP cover and Preparation of TP | 77.25 | 5.017 | 1.7983
P75 | 2005 | Loadout Blade 2 | 58.25 | 3.7831 | 1.356
P75 | 2005 | Blade #2 Lifting (safe-to-safe) | 49 | 3.1823 | 1.1407
P75 | 2005 | Loadout Blade 3 | 46.5 | 3.02 | 1.0825
P75 | 2005 | Loadout Nacelle #1 | 8.25 | 0.5358 | 0.19205
P75 | 2005 | Nacelle preparation and rigging | 7.5 | 0.48709 | 0.17459
P75 | 2005 | Preload and jacking up at port | 4.75 | 0.30849 | 0.11057
P75 | 2005 | Turbine general completion works | 4.5 | 0.29226 | 0.10475
P75 | 2005 | Positioning at WTG location | 4.5 | 0.29226 | 0.10475
P75 | 2005 | Tower rigging-up (attached lifting equipment) | 3 | 0.19484 | 0.069836
P90 | 1997 | Blade yoke rigging and attachement to Blade #1 | 332.75 | 18.0303 | 7.2313
P90 | 1997 | Loadout Blade 1 | 310.75 | 16.8383 | 6.7532
P90 | 1997 | Preload and jacking up at site | 189.5 | 10.2682 | 4.1182
P90 | 1997 | DP field check | 142.25 | 7.7079 | 3.0914
P90 | 1997 | Jacking down at site | 134 | 7.2609 | 2.9121
P90 | 1997 | Blade #3 Lifting (safe-to-safe) | 117.75 | 6.3804 | 2.5589
P90 | 1997 | Nacelle preparation and rigging | 109.75 | 5.9469 | 2.3851
P90 | 1997 | Loadout Blade 3 | 103.25 | 5.5947 | 2.2438
P90 | 1997 | Remove TP cover and Preparation of TP | 82 | 4.4432 | 1.782
P90 | 1997 | Tower rigging-up (attached lifting equipment) | 75.5 | 4.091 | 1.6408
P90 | 1997 | Loadout Nacelle #1 | 72 | 3.9014 | 1.5647
P90 | 1997 | Loadout Tower #2 | 71.25 | 3.8607 | 1.5484
P90 | 1997 | Loadout Blade 2 | 26 | 1.4088 | 0.56503
P90 | 1997 | Blade #2 Lifting (safe-to-safe) | 26 | 1.4088 | 0.56503
P90 | 1997 | Positioning at WTG location | 25.5 | 1.3817 | 0.55417
P90 | 1997 | Loadout Tower #1 | 15.25 | 0.82633 | 0.33141
P90 | 1997 | Loadout Nacelle #2 | 12 | 0.65023 | 0.26078